## Weekly report
[Coal Hauling Team]
October 25th, 2023
| This Week | [8 empty] | Next Week
Main | - DT queues at the stockpile | [8 empty] | - Weekly meeting with all Contractors
Issues | - Monthly meeting with all Contractors | [8 empty] | - Mud handling acceleration in Pit SMD, RTM & RTS G
| - Construction ROM at SM6, RTM | [8 empty] | - Temporay ROM Inspection all area
| - Commissioning temporary rom SMD, RTS2C3 | [8 empty] | - Support mud handling all area
| - Investigation findings of SOP violations | [8 empty] | - Dust management control all Pits
| - Control the number of operation Coal Hauler to TMCT | [8 empty] | - Control the number of operation Coal Hauler to TMCT
| - Coal Production & Coal Hauling | [17 empty] | (Unit : Kton, Kbcm)
Coal Prod. |  | Class |  | Month to Date (01~25 Octo) | [5 empty] | Weekly (19 ~25 Oct) | [5 empty] | A/Plan of Sept
& Coal Hauling |  |  |  | Plan |  | Actual |  | Diff |  | Plan |  | Actual |  | Diff
|  | Coal Prod |  | 1521775.4 |  | 2162818 |  | 641042.6 |  | 549919.55 |  | 538349.3 |  | -11570.25 |  | 2775 |  | Kton
|  | Coal Haul |  | 1621052.4 |  | 2171977 |  | 550924.6 |  | 638596.4 |  | 644262 |  | 5665.6 |  | 2750 |  | Kton
Exposed | - Exposed Coal (Target : Exposed 4days, Ready 2 days) | [17 empty] | (Unit : Kton) |  | * Caculation for coal stock days
Coal |  | Class |  |  | This Week (16 Oct) |  |  |  | This Week (23 Oct) |  |  |  | Diff |  |  |  | Remarks (Main Area) |  |  |  |  | Nov
[5 empty] | Exposed |  | Ready |  | Exposed |  | Ready |  | Exposed |  | Ready | [5 empty] | area | Daily Plan | Exposed | Ready
|  | R S |  |  | 32 |  | 24 |  | 32 |  | 28 |  | 0 | -0.13258 | 4 | -1.1326 | RT N, M,S, SSB |  |  |  | RS | 24903.3 | 1.285 | 1.1243
|  | S M |  |  | 357 |  | 113 |  | 313 |  | 128 |  | -44 | -0.13258 | 15 | -0.13258 | SM-A,B,C,D,6 |  |  |  | SM | 64612.9 | 4.8442 | 1.981
|  | TOTAL |  |  | 389 |  | 137 |  | 345 |  | 156 |  | -44 | 0.86742 | 19 | 0.86742 | [5 empty] | 89516.2
|  | Stock Days |  |  | RS Coal: 1 day, SM Coal:4 day
Quality & | - Supervise loading point all area | [8 empty] | - Supervise loading point as potency foreign material
Recovery | - Keep inspection of coal conservation all area | [8 empty] | - Inspection to Pit all area
Hauling | - Safety- Lighting Inspection | [8 empty] | - Supervise random fatiq test in rest area Km16
Silo-TMC | - Control the number of operation fleet coal production | [8 empty] | - Control performance SUK & TMP as PA>85%
Pit | - Dewatering control in all Pit | [8 empty] | - Optimal Mud handling all area
Maintenance | - Dust management control all Pits | [8 empty] | - Limiting production according to daily targets
| o Sump Status (As of 21. 11. 22) | [18 empty] | (Unit : KM³, KM³/day)
| Class |  |  | Catchment Area(ha) |  | Volume of Water | [8 empty] | Pumping Capa. |  | Pump Line (Including Transfer) |  |  |  | Class |  | Weekly Rain Fall | In-flow | 전주 잔여량 +강우유입량 | 주간 펌핑량 | 예상잔여량 | diff
[6 empty] | This Week(11/10) |  |  | This Week(11/10) |  |  | Diff.
| Ex -Pit | RN | 7W | 426 |  | 255 |  |  | 260 |  |  | 5 |  |  | 54 |  | 6 Line |  |  |  | RN | 7W | 28 | 119.2801 | 374.2801 | 378 | -3.7199 | 263.7199
|  |  | 4W | 87 |  | 350 |  |  | 355 |  |  | 5 |  |  | 22 |  | 2 Line |  |  |  |  | 4W | 28 | 24.36 | 374.36 | 154 | 220.36 | 134.64
|  | RM |  | 328 |  | 510 |  |  | 520 |  |  | 10 |  |  | 46.08 |  | 4 Line |  |  |  | RM |  | 22 | 72.1601 | 582.1601 | 322.56 | 259.6001 | 260.3999
|  |  | C3 | 430 |  | 85 |  |  | 90 |  |  | 5 |  |  | 50.4 |  | 4 Line |  |  |  | RTS | C3 | 32 | 137.6 | 222.6 | 352.8 | -130.2 | 220.2
|  |  | D1 | 0 |  | 0 |  |  | 0 |  |  | 0 |  |  | 86.4 |  | 3 Line |  |  |  |  | D1 | 32 | 0 | 0 | 604.8 | -604.8 | 604.8
|  |  | D2 | 496 |  | 195 |  |  | 200 |  |  | 5 |  |  | 87.4 |  | 5 Line |  |  |  |  | D2 | 32 | 158.72 | 353.72 | 611.8 | -258.08 | 458.08
|  |  | E1 | 181 |  | 150 |  |  | 155 |  |  | 5 |  |  | 43.2 |  | 1 Line |  |  |  |  | E1 | 32 | 57.92 | 207.92 | 302.4 | -94.48 | 249.48
|  |  | F | 327 |  | 180 |  |  | 185 |  |  | 5 |  |  | 34.92 |  | 3 Line |  |  |  |  | F | 24 | 78.48 | 258.48 | 244.44 | 14.04 | 170.96
|  |  | G1 | 114 |  | 20 |  |  | 25 |  |  | 5 |  |  | 20 |  | 2 Line
|  |  | G2 | 40 |  | 20 |  |  | 20 |  |  | 0 |  |  | 10 |  | 1 Line |  |  |  |  | G | 41.5 | 16.6 | 36.6 | 70 | -33.4 | 53.4
|  | SM | Aw | 416 |  | 45 |  |  | 50 |  |  | 5 |  |  | 10 |  | 5 Line |  |  |  | SM | A | 53.5 | 222.56 | 267.56 | 70 | 197.56 | -147.56
|  |  | A1 | 50 |  | 70 |  |  | 80 |  |  | 10 |  |  | 50 |  | 1 Line |  |  |  |  | A1 | 53.5 | 26.75 | 96.75 | 350 | -253.25 | 333.25
|  |  | #6 | 175 |  | 60 |  |  | 65 |  |  | 5 |  |  | 15 |  | 2 Line |  |  |  |  | #6 | 53.5 | 93.625 | 153.625 | 105 | 48.625 | 16.375
|  |  | B | 284 |  | 455 |  |  | 460 |  |  | 5 |  |  | 15 |  | 2 Line |  |  |  |  | B | 60.5 | 171.82 | 626.82 | 105 | 521.82 | -61.82
|  |  | D1 | 382 |  | 455 |  |  | 465 |  |  | 10 |  |  | 26.1 |  | 4 Line |  |  |  |  | D1 | 36.5 | 139.4301 | 594.4301 | 182.7 | 411.7301 | 53.2699
|  |  | D2 | 189 |  | 165 |  |  | 175 |  |  | 10 |  |  | 27.6 |  | 2 Line |  |  |  |  | D2 | 0 | 0 | 165 | 193.2 | -28.2 | 203.2
|  | SSB |  | 86 |  | 75 |  |  | 80 |  |  | 5 |  |  | 17.8 |  | 2 Line |  |  |  | SSB |  | 29.5 | 25.37 | 100.37 | 124.6 | -24.23 | 104.23
| Total |  |  | 4011 |  | 3090 |  |  | 3185 |  |  | 95 |  |  | 615.9 | [8 empty] | 1344.6755 | 4414.6755 | 4171.3 | 243.3755 | 2941.6245

## Weekly Statistics
<Coal Hauling Team> | [7 empty] | Weekly Coal Production Statistics
| [October Plan : Coal Mining 2.775 Kton] | [12 empty] | (Weekly: 10/19~10/25, Monthly: 10/01~10/25)
|  | Coal Haul | Weekly | [5 empty] | Monthly
|  | (Ton) | Plan |  | Actual |  | Diff. |  | Plan |  | Actual |  | Diff.
|  | SUK | 250877.25 |  | 251191 |  | 313.75 |  | 636842.25 |  | 852223 |  | 215380.75
|  | TMP | 250877.25 |  | 231850 |  | -19027.25 |  | 636842.25 |  | 790371 |  | 153528.75
|  | MHA | 136841.9 |  | 161221 |  | 24379.1 |  | 347367.9 |  | 529383 |  | 182015.1
|  | Sum | 638596.4 |  | 644262 |  | 5665.6 |  | 1621052.4 |  | 2171977 |  | 550924.6
|  | Coal | Weekly | [5 empty] | Monthly
| (톤) | (Ton) | Plan |  | Actual |  | Diff. |  | Plan |  | Actual |  | Diff.
|  | RN | 12580.75 |  | 17271 |  | 4690.25 |  | 32903.5 |  | 45462.2 |  | 12558.7
|  | RN(B) | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  | AC(P) | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  | C/D | 44451.55 |  | 39010.4 |  | -5441.15 |  | 116257.9 |  | 193928.1 |  | 77670.2
|  | SM-6 | 36693.8 |  | 41469.3 |  | 4775.5 |  | 95968.4 |  | 158811.9 |  | 62843.5
|  | G | 12580.75 |  | 11757.3 |  | -823.45 |  | 32903.5 |  | 43976.1 |  | 11072.6
|  | RTM | 5806.5 |  | 22632.7 |  | 16826.2 |  | 98710.5 |  | 111105.5 |  | 12395
|  | SM-A | 100645.35 |  | 125071.8 |  | 24426.45 |  | 263226.3 |  | 485224.3 |  | 221998
|  | SM-B | 38790.05 |  | 55598.2 |  | 16808.15 |  | 101450.9 |  | 200857.4 |  | 99406.5
|  | SM-C | 39419.25 |  | 25967.6 |  | -13451.65 |  | 103096.5 |  | 115066.9 |  | 11970.4
|  | SM-D | 241129.2 |  | 183829.4 |  | -57299.8 |  | 630645.6 |  | 745742.1 |  | 115096.5
|  | SSB | 17822.35 |  | 15741.6 |  | -2080.75 |  | 46612.3 |  | 62643.5 |  | 16031.2
|  | Sum | 549919.55 |  | 538349.3 |  | -11570.25 |  | 1521775.4 |  | 2162818 |  | 641042.6
|  | Exposed | 10/16 |  |  |  | 10/25 |  |  |  | Diff.
|  | Coal(Kton) | Exposed |  | Ready |  | Exposed |  | Ready |  | Exposed |  | Ready
|  | RTN | 2 |  | 1 |  | 2 |  | 2 |  | 0 |  | 1
|  | C/DF | 6 |  | 5 |  | 4 |  | 4 |  | -2 |  | -1
|  | SM6 | 6 |  | 6 |  | 6 |  | 6 |  | 0 |  | 0
|  | G | 2 |  | 2 |  | 2 |  | 1 |  | 0 |  | -1
|  | RTM | 4 |  | 4 |  | 4 |  | 4 |  | 0 |  | 0
|  | SM-A | 192 |  | 32 |  | 152 |  | 44 |  | -40 |  | 12
|  | SM-BC | 14 |  | 13 |  | 13 |  | 13 |  | -1 |  | 0
|  | SM-D | 151 |  | 68 |  | 148 |  | 71 |  | -3 |  | 3
|  | SSB | 12 |  | 6 |  | 14 |  | 11 |  | 2 |  | 5
|  | Sum | 389 |  | 137 |  | 345 |  | 156 |  | -44 |  | 19
| ROM Temporary (Kton) |  | PTP |  | SIMS |  | Pama |  | PTP |  | BIMA |  | TOTAL
|  |  | (ROM RTM) |  | (ROM_SMA) |  | ROM 2C |  | ROM SMD |  | SSB
|  |  | 0 |  | 0 |  | 0 |  | 0 |  | 2.5 |  | 2.5
| Rain |  | Weekly(1/07~1/13) | [5 empty] | Monthly(1/1~1/31) | [5 empty] | 7 | weekly
| (mm,hr) |  | Rain fall | Rain hour | Road Maintenance | Fog hour | Disturb Hour(mm/hr) |  | Rain fall | Rain hour | Road Maintenance | Fog hour | Disturb Hour(mm/hr) |  | 17 | monthly
[7 empty] | Sum | Avg. Daily |  |  |  |  | Sum | Avg. Daily
|  | RTN | 28 | 16.85 | 5.5667 | 0 | 22.4167 | 3.2024 | 28 | 16.85 | 5.5667 | 0 | 22.4167 | 1.3186
|  | A/B | 46 | 19.25 | 4.2333 | 0 | 23.4833 | 3.3548 | 46 | 19.25 | 4.2333 | 0 | 23.4833 | 1.3814
|  | C/D | 32 | 18.1 | 3.2667 | 0 | 21.3667 | 3.0524 | 32 | 18.1 | 3.2667 | 0 | 21.3667 | 1.2569
|  | E | 24 | 21.9333 | 3.4 | 0 | 25.3333 | 3.619 | 24 | 21.9333 | 3.4 | 0 | 25.3333 | 1.4902
|  | F | 38 | 15.6833 | 2.7667 | 0 | 18.45 | 2.6357 | 38 | 15.6833 | 2.7667 | 0 | 18.45 | 1.0853
|  | G | 41.5 | 15.6833 | 2.7667 | 0 | 18.45 | 2.6357 | 41.5 | 15.6833 | 2.7667 | 0 | 18.45 | 1.0853
|  | RTM | 22 | 10.55 | 9.5167 | 0 | 20.0667 | 2.8667 | 22 | 10.55 | 9.5167 | 0 | 20.0667 | 1.1804
|  | SM-A | 53.5 | 20.1833 | 8.5 | 0 | 28.6833 | 4.0976 | 53.5 | 20.1833 | 8.5 | 0 | 28.6833 | 1.6873
|  | SM-B | 60.5 | 20.1 | 14.35 | 0 | 34.45 | 4.9214 | 60.5 | 20.1 | 14.35 | 0 | 34.45 | 2.0265
|  | SM-D1 | 36.5 | 14.3 | 3.1833 | 0 | 17.4833 | 2.4976 | 36.5 | 14.3 | 3.1833 | 0 | 17.4833 | 1.0284
|  | SM-D2 |  |  |  | 0 | 0 | 0 |  |  |  | 0 | 0 | 0
|  | SSB | 29.5 | 7.1167 | 1.9167 | 0 | 9.0333 | 1.2905 | 29.5 | 7.1167 | 1.9167 | 0 | 9.0333 | 0.53137
|  | Avg. | 37.4091 | 16.3409 | 5.4061 | 0 | 19.9347 | 2.8478 | 37.4091 | 16.3409 | 5.4061 | 0 | 19.9347 | 1.1726
※ Plan Rain Disturb hour Jan : 1.10 hr/day

## Weekly Raw Data (hidden)
[14 empty] | Weekly sum |  |  | Weekly Daily Plan |  |  | Monthly cum
Class | Pit/Area | Thu |  | Fri |  | Sat |  | Sun | Mon |  | Tue |  | Wed | Weekly |  |  | 2023-10-25 | Aug |  |  |  | 2023-10-25
|  | 2023-10-19 |  | 2023-10-20 |  | 2023-10-21 |  | 2023-10-22 | 2023-10-23 |  | 2023-10-24 |  | 2023-10-25 | Actual | Plan | w/days | daily plan | daily plan | w/days | plan | MTD/days | Plan | Actual
Coal Hauling | SUK | 31046 |  | 28709 |  | 41229 |  | 28551 | 39782 |  | 40034 |  | 41840 | 251191 | 250877.25 | 6.5 | 38596.5 |  | 3 | 0 | 16.5 | 636842.25 | 852223
(Ton) | TMP | 29444 |  | 30527 |  | 35408 |  | 25446 | 37809 |  | 35767 |  | 37449 | 231850 | 250877.25 | 6.5 | 38596.5 |  | 3 | 0 | 16.5 | 636842.25 | 790371
| MHA | 21789 |  | 21195 |  | 25942 |  | 17852 | 26919 |  | 23893 |  | 23631 | 161221 | 136841.9 | 6.5 | 21052.6 |  | 3 | 0 | 16.5 | 347367.9 | 529383
| total | 82279 |  | 80431 |  | 102579 |  | 71849 | 104510 |  | 99694 |  | 102920 | 644262 | 638596.4 |  | 98245.6 | 0 |  | 0 |  | 1621052.4 | 2171977 |  | 550924.6
Coal | RTN Pama | 869.1 |  | 2196.4 |  | 4425.9 |  | 1988.9 | 2808.9 |  | 3419.3 |  | 1562.5 | 17271 | 12580.75 | 6.5 | 1935.5 |  | 3 |  | 17 | 32903.5 | 45462.2
(ton) | RN(Buma) | [12 empty] | 0
| RS_AB(Pama) | [12 empty] | 0
| RS_CD(Pama) | 1027.9 |  | 3527.9 |  | 5094.1 |  | 7177.8 | 7890.2 |  | 7067.3 |  | 7225.2 | 39010.4 | 44451.55 | 6.5 | 6838.7 |  | 3 |  | 17 | 116257.9 | 193928.1
| SM6(Pama) | 3594.3 |  | 5688.6 |  | 7550.7 |  | 6362.6 | 5837.8 |  | 5994.8 |  | 6440.5 | 41469.3 | 36693.8 | 6.5 | 5645.2 |  | 3 |  | 17 | 95968.4 | 158811.9
| RS_G(Pama) | 900.3 |  | 1183 |  | 3194.6 |  | 2035.2 | 1717.2 |  | 1403.2 |  | 1323.8 | 11757.3 | 12580.75 | 6.5 | 1935.5 |  | 3 |  | 17 | 32903.5 | 43976.1
| RM(Pama) | 829.6 |  | 2509.5 |  | 3394.7 |  | 5009.5 | 5027.2 |  | 3323.5 |  | 2538.7 | 22632.7 | 5806.5 |  | 5806.5 |  | 3 |  | 17 | 98710.5 | 111105.5
| SM-A(Sims) | 11234.1 |  | 19560.4 |  | 24974.3 |  | 20696.8 | 16921.6 |  | 15501.7 |  | 16182.9 | 125071.8 | 100645.35 | 6.5 | 15483.9 |  | 3 |  | 17 | 263226.3 | 485224.3
| SM-B(Pama) | 2655.8 |  | 9920.5 |  | 8355.6 |  | 8479.1 | 8410.1 |  | 8708.3 |  | 9068.8 | 55598.2 | 38790.05 | 6.5 | 5967.7 |  | - |  | 17 | 101450.9 | 200857.4
| SM-C | 4373.6 |  | 4002 |  | 5705.3 |  | 4651.1 | 3311.4 |  | 2276.7 |  | 1647.5 | 25967.6 | 39419.25 | 6.5 | 6064.5 |  | - |  | 17 | 103096.5 | 115066.9
| SM-D(Petro) | 11459 |  | 29762.3 |  | 31837.4 |  | 30327 | 21933.9 |  | 32201.8 |  | 26308 | 183829.4 | 241129.2 | 6.5 | 37096.8 |  | 3 |  | 17 | 630645.6 | 745742.1
| SSB(Bima) | 904.4 |  | 1303.6 |  | 2921.9 |  | 2614.6 | 2440.1 |  | 3160.4 |  | 2396.6 | 15741.6 | 17822.35 | 6.5 | 2741.9 |  | 3 |  | 17 | 46612.3 | 62643.5
| total | 37848.1 |  | 79654.2 |  | 97454.5 |  | 89342.6 | 76298.4 |  | 83057 |  | 74694.5 | 538349.3 | 549919.55 |  | 89516.2 | 0 |  | 0 |  | 1521775.4 | 2162818 | 641042.6 | 641042.6
Rain | RN | 0 |  | 6.5 |  | 7 |  |  | 4.5 |  | 0 |  |  | 18 |  |  | 82 |  |  | 64 |  | 355.5
(mm) | B | 2 |  | 3 |  | 10 |  |  | 21 |  | 0 |  |  | 36 |  |  | 101 |  |  | 65 |  | 258
| C | 1 |  | 5.5 |  | 7.5 |  |  | 8 |  | 0 |  |  | 22 |  |  | 86.5 |  |  | 64.5 |  | 271.5
| E | 1.5 |  | 2 |  | 9.5 |  |  | 1 |  | 0 |  |  | 14 |  |  | 121.5 |  |  | 107.5 |  | 281.5
| F | 1 |  | 7.5 |  | 18.5 |  |  | 1 |  | 0 |  |  | 28 |  |  | 85.5 |  |  | 57.5 |  | 134.5
| G | 0 |  | 11 |  | 19.5 |  |  | 1 |  | 0 |  |  | 31.5 |  |  | 71 |  |  | 39.5 |  | 157.5
| M | 0 |  | 4 |  | 10 |  |  | 8 |  | 1 |  |  | 23 |  |  | 88 |  |  | 65 |  | 325.8
| SM-A | 18.5 |  | 5.5 |  | 3 |  |  | 11 |  | 15.5 |  |  | 53.5 |  |  | 137 |  |  | 83.5 |  | 180
| SM-B | 21.8 |  | 6 |  | 5.5 |  |  | 9.3 |  | 18 |  |  | 60.6 |  |  | 147.1 |  |  | 86.5 |  | 185.5
| SM-D1 | 0 |  | 3 |  | 2.5 |  |  | 21 |  | 0 |  |  | 26.5 |  |  | 127.5 |  |  | 101 |  | 184.5
| SM-D2 | 0 |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0
| SSB | 0 |  | 12.5 |  | 2 |  |  | 1 |  | 14 |  |  | 29.5 |  |  | 138 |  |  | 108.5 |  | 228
| TCMT | [12 empty] | 0 |  |  | 0
| A-Bay | [12 empty] | 0 |  |  | 0
Rain+R/main | RN | 0 | 0 | 2 | 1.85 | 4.2167 | 0.41667 |  | 4.6333 | 2.3 | 6 | 0 |  | 16.85 | 4.5667 | 21.4167 | 65.7833 | 19.7833 |  | 48.9333 | 15.2167 | 147.7 | 40.4167
(hr) | B | 5.8167 | 0.033333 | 1.4167 | 1 | 3.9167 | 0.7 |  | 3.8 | 0.5 | 4.3 | 2 |  | 19.25 | 4.2333 | 23.4833 | 59.75 | 7.3 |  | 40.5 | 3.0667 | 115.6167 | 10.5
| C | 4.65 | 0.38333 | 1.4 | 0.76667 | 3.2667 | 1.4167 |  | 3.8333 | 0.46667 | 4.95 | 0.23333 |  | 18.1 | 3.2667 | 21.3667 | 59.5833 | 7.5833 |  | 41.4833 | 4.3167 | 119.2167 | 12.6333
| E | 7.85 | 0.016667 | 1.6333 | 0.8 | 4.75 | 1.3 |  | 3.2833 | 0.26667 | 4.4167 | 1.0167 |  | 21.9333 | 3.4 | 25.3333 | 60.5 | 7.9167 |  | 38.5667 | 4.5167 | 112.3333 | 11.7667
| F | 5.7833 | 0 | 1.5667 | 1.4833 | 3.7 | 1.0333 |  | 0.16667 | 0 | 4.4667 | 0.25 |  | 15.6833 | 2.7667 | 18.45 | 57.3833 | 5.7333 |  | 41.7 | 2.9667 | 107.3667 | 11.5667
| G | 5.7833 | 0 | 1.5667 | 1.4833 | 3.7 | 1.0333 |  | 0.16667 | 0 | 4.4667 | 0.25 |  | 15.6833 | 2.7667 | 18.45 | 57.3833 | 5.7333 |  | 41.7 | 2.9667 | 107.3667 | 11.5667
| M | 0 | 0 | 1.5 | 1.55 | 5.1667 | 4.2667 |  | 3.8833 | 3.7 | 7.0667 | 0.66667 |  | 17.6167 | 10.1833 | 27.8 | 64.2 | 23.1 |  | 46.5833 | 12.9167 | 139.25 | 32.6167
| SM-A | 7.5333 | 1.65 | 1.55 | 2.1333 | 3.2167 | 0.76667 |  | 3.55 | 2.8167 | 4.3333 | 1.6667 |  | 20.1833 | 9.0333 | 29.2167 | 60.45 | 24.15 |  | 40.2667 | 15.1167 | 120.5833 | 38.9
| SM-B | 7.3667 | 2.35 | 2.55 | 2.85 | 2.6167 | 1.3667 |  | 4.0667 | 5.2833 | 3.5 | 2.5 |  | 20.1 | 14.35 | 34.45 | 60.8333 | 28.8667 |  | 40.7333 | 14.5167 | 116.2667 | 50.0333
| SM-D1 | 0 | 0 | 0.66667 | 0 | 3.3667 | 1 |  | 4.2667 | 2.1833 | 6 | 0 |  | 14.3 | 3.1833 | 17.4833 | 56.5333 | 13.55 |  | 42.2333 | 10.3667 | 94.6667 | 22.1667
| SM-D2 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
| SSB | 0 | 0 | 1.25 | 0.66667 | 1.5 | 0.25 |  | 1.3667 | 0.083333 | 3 | 0.91667 |  | 7.1167 | 1.9167 | 9.0333 | 38.5833 | 19.3 |  | 31.4667 | 17.3833 | 79.4667 | 36.2
| TCMT | [12 empty] | 0 | 0 | 0 | 0 | 0
| A-Bay | [12 empty] | 0 | 0 | 0 | 0 | 0
Fog | RN | [12 empty] | 0 |  |  | 0
(hr) | B | [12 empty] | 0 |  |  | 0
| C | [12 empty] | 0 |  |  | 0
| E | [12 empty] | 0 |  |  | 0
| F | [12 empty] | 0 |  |  | 0
| G | [12 empty] | 0 |  |  | 0
| M | [12 empty] | 0 |  |  | 0
| SM-A | [12 empty] | 0 |  |  | 0
| SM-B | [12 empty] | 0 |  |  | 0
| SM-D1 | [12 empty] | 0 |  |  | 0
| SM-D2 | [12 empty] | 0 |  |  | 0
| SSB | [12 empty] | 0 |  |  | 0
| TMCT | [12 empty] | 0 |  |  | 0 |  |  |  |  | 0
| A-Bay | [12 empty] | 0 |  |  | 0