## LAYANG 10 RENOV (hidden)
ROAD MAINTENANCE & CONSTRUCTION
( SHORT REPORT )
TYPE |  | Occasional |  |  |  | Daily |  |  | Weekly | [5 empty] | Monthly | [5 empty] | Yearly
AREA |  | LAYANG 10
SECTION |  | ENGINEER |  | FIELD |  |  |  | W/SHOP |  | PLANT | [5 empty] | SAFETY |  |  |  | ADMIN & LOGISTIC
- Day / Date |  | : | 2018-10-09 | [8 empty] | No. Document :
- Project Name |  | : | Renovasi Post Jaga Layang 10 Lama | [9 empty] | - Weather |  |  |  |  | : | Clear |  |  |  | Rain
- Contractor / Dev. |  | : | PT. KANDILO PUTRA PRIMA UTAMA
- Priod |  | : | 1 AGUSTUS - 31 OKTOBER2018 | [10 empty] | - Progress |  |  |  |  | Plan |  |  | : | 85.45% |  |  | 26.06% | 2.87% | 0.41% | 0.05857%
- Reported by |  | : | Azwar Rakhman | [15 empty] | Actual |  |  | : | 100%
[19 empty] | Acceleration |  |  |  | 14.55%
No | I S S U E | [10 empty] | REMARKS
Tidak Ada kegiatan hari ini, hari ini melakukan inspeksi keseluruhan
A C T I V I T I E S | [11 empty] | MAN POWER (Man-Day)
No | Description | [10 empty] | No |  | Description | [7 empty] | Unit |  |  | Qty
[14 empty] | T o t a l | [7 empty] | prs |  |  | 0
CONSUMABLE MATERIAL | [9 empty] | EQUIPMENT (Unit-Day)
No | Description |  |  |  | Unit |  | Qty | Prev. | Cum. | No | Description | [7 empty] | Unit | Qty |  |  |  | Remarks
1
2
3
4
5
6
No | Activity Plan of Tomorrow
P H O T O / M A P | [16 empty] | A C T I V I T Y
Tampak Depan Toilet
Tampak Belakang Toilet
Tampak Samping Toilet
Pagar Balakang
Halte
Pemasangan Kansteen
Pos Jaga
Pos Jaga

## Agustus 2023
MINE FACILITY
( SHORT REPORT )
TYPE |  |  |  |  | Occasional |  |  | Daily |  |  | Weekly | [6 empty] | M.Ilfian.M.S
AREA |  |  |  |  | SMCP 35
SECTION |  |  |  |  | STOCKPILE (ENGINEERING)
- Day / Date |  |  |  |  | : | 2023-08-24 | [6 empty] | No.Document | [7 empty] | : | FM/MF-SP/015
- Project Name |  |  |  |  | : | [10 empty] | - Weather |  |  |  |  | : |  |  |  | Fine
- Pelaksana |  |  |  |  | :
- Periode |  |  |  |  | : | 01 ~ 31 Agustus 2023 | [9 empty] | - Progress | [5 empty] | Plan |  | : |  |  |  | 26.06% | 2.87% | 0.41% | 0.05857%
- Reported by |  |  |  |  | : | M.Ilfian.Mustika.S | [15 empty] | Actual |  | :
[19 empty] | Acceleration |  |  |  |  | :
No | I S S U E | [13 empty] | REMARKS
A C T I V I T I E S | [14 empty] | MAN POWER (Man-Day)
No | Description | [13 empty] | No |  | Description | [6 empty] | Unit |  |  | Qty
| SHIFT | [7 empty] | NON SHIFT | [7 empty] | SHIFT
1 | Production | [6 empty] | 1 | Maintenance S.Pile Khusus | [5 empty] | A |  | Pengawas | [6 empty] | Prs |  |  | 2
| Target Prod |  |  |  |  | = |  | 2 | Spreading Top Soil Slope SM_E | [7 empty] | Operator | [6 empty] | Prs |  |  | 25
| Target Hauling |  |  |  |  | = |  | 3 | Support Project New Fuel Station | [7 empty] | Helper | [6 empty] | Prs |  |  | 2
| Produksi Achieve |  |  |  |  | = |  | 4 | Support Project Office & Operator Room | [5 empty] | B |  | Pengawas | [6 empty] | Prs |  |  | 3
| Hauling Achieve |  |  |  |  | = |  |  | Stockpile | [7 empty] | Operator | [6 empty] | Prs |  |  | 26
| Deviasi |  |  |  |  | = | [10 empty] | Helper | [6 empty] | Prs |  |  | 2
| Stock |  |  | P |  | = | [8 empty] | C |  | Pengawas | [6 empty] | Prs |  |  | 1
|  |  |  | M |  | = | [10 empty] | Operator | [6 empty] | Prs |  |  | 23
|  |  |  | SM |  | = | [10 empty] | Helper | [6 empty] | Prs |  |  | 2
| Total |  |  |  |  | = | [20 empty] | 0
| Crushing / a day |  |  |  |  | = | [10 empty] | Non - SHIFT
|  | Empty |  | A |  | = | [8 empty] | 1 |  | Pengawas | [6 empty] | Prs |  |  | 2
|  |  |  | B |  | = | [10 empty] | Operator | [6 empty] | Prs |  |  | 11
|  |  |  | C |  | =
|  | Silo Full |  | A |  | =
|  |  |  | B |  | =
|  |  |  | C |  | =
2 | Washing A2B |  |  |  | A | = |  |  | 7
| Prog % (a day) |  | 0 |  | B | = |  |  | 7
[5 empty] | C | = |  |  | 0 | [7 empty] | T o t a l | [6 empty] | prs |  |  | 99
CONSUMABLE MATERIAL | [12 empty] | EQUIPMENT (Unit-Day)
No | Description | [5 empty] | Unit |  | Qty | Prev. | Cum. | % | No | Description | [7 empty] | Unit | Qty |  |  | Remarks
1 | Spoil | [5 empty] | Ton | [5 empty] | 1 | Bulldozer | [7 empty] | Unit |  |  |  | 0 Trouble
2 | Fine Coal | [5 empty] | Ton | [5 empty] | 2 | Wheel Loader | [7 empty] | Unit |  |  |  | 0 Trouble
3 | Rejected Coal | [5 empty] | Ton | [5 empty] | 3 | Excavator | [7 empty] | Unit |  |  |  | 0 Trouble
4 | Material Batu | [5 empty] | m3 | [5 empty] | 4 | Motor Grader | [7 empty] | Unit |  |  |  | 0 Trouble
5 | Ditch | [5 empty] | m' | [5 empty] | 5 | Vibro Roller | [7 empty] | Unit |  |  |  | 0 Trouble
6 | Safety Bump | [5 empty] | m' | [5 empty] | 6 | Dumpt Truck | [7 empty] | Unit |  |  |  | 0 Trouble
7 | Support Fuel Ma'r OB | [5 empty] | m3 | [5 empty] | 7 | Water Truck | [7 empty] | Unit |  |  |  | 0 Trouble
8 | Material Tanah at Settling Pond A5 | [5 empty] | m3 | [6 empty] | Total | [7 empty] | Unit |  |  |  | 0 Trouble
No | Activity Plan of Tomorrow
1 | Preparation New Area Stock Room Stockpile 35
2 | Support Project New Fuel Station (2 DT)
3 | Support Project Operator Room
4 | Support Project Sediment Pond
P H O T O / M A P | [19 empty] | A C T I V I T Y
CONTOH

## HOIST CRANE WS (hidden)
ROAD MAINTENANCE & CONSTRUCTION
( SHORT REPORT )
TYPE |  | Occasional |  |  |  | Daily |  |  | Weekly | [5 empty] | Monthly | [5 empty] | Yearly
AREA |  | Workshop PT. MHA Km 23
SECTION |  | ENGINEER |  | FIELD |  |  |  | W/SHOP |  | PLANT | [5 empty] | SAFETY |  |  |  | ADMIN & LOGISTIC
- Day / Date |  | : | 11/102018 | [8 empty] | No. Document :
- Project Name |  | : | HOIST CRANE 10 TON | [9 empty] | - Weather |  |  |  |  | : | Clear |  |  |  | Rain
- Contractor / Dev. |  | : | PT. MHE DEMAG INDONESIA
- Priod |  | : | 1 MARET - 31 AGUSTUS 2018 | [10 empty] | - Progress |  |  |  |  | Plan |  |  | : |  |  |  | 26.06% | 2.87% | 0.41% | 0.05857%
- Reported by |  | : | Azwar Rakhman | [15 empty] | Actual |  |  | :
Acceleration
No | I S S U E | [10 empty] | REMARKS
A C T I V I T I E S | [11 empty] | MAN POWER (Man-Day)
No | Description | [10 empty] | No |  | Description | [7 empty] | Unit |  |  | Qty
#REF!
1 | Commisioning Hoist Crane
[14 empty] | T o t a l | [7 empty] | prs |  |  | 0
CONSUMABLE MATERIAL | [9 empty] | EQUIPMENT (Unit-Day)
No | Description |  |  |  | Unit |  | Qty | Prev. | Cum. | No | Description | [7 empty] | Unit | Qty |  |  |  | Remarks
1
2
3
4
5
6
No | Activity Plan of Tomorrow
P H O T O / M A P | [16 empty] | A C T I V I T Y
Commisioning Hoist Crane
Commisioning Hoist Crane
Commisioning Hoist Crane

## MHA (hidden)
ROAD MAINTENANCE & CONSTRUCTION
( SHORT REPORT )
TYPE |  | Occasional |  |  |  | Daily |  |  | Weekly | [5 empty] | Monthly | [5 empty] | Yearly
AREA
SECTION |  | ENGINEER |  | FIELD |  |  |  | W/SHOP |  | PLANT | [5 empty] | SAFETY |  |  |  | ADMIN & LOGISTIC
- Day / Date |  | : | #REF! | [8 empty] | No. Document :
- Project Name |  | : | MHA | [9 empty] | - Weather |  |  |  |  | : | Clear |  |  |  | Rain
- Contractor / Dev. |  | :
- Priod |  | : | [11 empty] | - Progress |  |  |  |  | Plan |  |  | : |  |  |  | 26.06% | 2.87% | 0.41% | 0.05857%
- Reported by |  | : | Azwar | [15 empty] | Actual |  |  | :
Acceleration
No | I S S U E | [10 empty] | REMARKS
A C T I V I T I E S | [11 empty] | MAN POWER (Man-Day)
No | Description | [10 empty] | No |  | Description | [7 empty] | Unit |  |  | Qty
1 | Pemasangan Patok untuk Bangunan Rest Room Operator
2 | #REF!
3 | #REF!
4 | #REF!
[14 empty] | T o t a l | [7 empty] | prs |  |  | 0
CONSUMABLE MATERIAL | [9 empty] | EQUIPMENT (Unit-Day)
No | Description |  |  |  | Unit |  | Qty | Prev. | Cum. | No | Description | [7 empty] | Unit | Qty |  |  |  | Remarks
1
2
3
4
5
6
No | Activity Plan of Tomorrow
P H O T O / M A P | [16 empty] | A C T I V I T Y
Pemasangan Patok untuk Bangunan Rest Room Operator
Pemasangan Patok untuk Bangunan Rest Room Operator

## POND ISO TANK (hidden)
ROAD MAINTENANCE & CONSTRUCTION
( SHORT REPORT )
TYPE |  | Occasional |  |  |  | Daily |  |  | Weekly | [5 empty] | Monthly | [5 empty] | Yearly
AREA |  | Workshop PT. MHA Km 23
SECTION |  | ENGINEER |  | FIELD |  |  |  | W/SHOP |  | PLANT | [5 empty] | SAFETY |  |  |  | ADMIN & LOGISTIC
- Day / Date |  | : | 2018-10-09 | [8 empty] | No. Document :
- Project Name |  | : | Ppondasi ISO Tank TMCT | [9 empty] | - Weather |  |  |  |  | : | Clear |  |  |  | Rain
- Contractor / Dev. |  | : | #REF!
- Priod |  | : | [11 empty] | - Progress |  |  |  |  | Plan |  |  | : |  |  |  | 26.06% | 2.87% | 0.41% | 0.05857%
- Reported by |  | : | Azwar Rakhman | [15 empty] | Actual |  |  | :
Acceleration
No | I S S U E | [10 empty] | REMARKS
A C T I V I T I E S | [11 empty] | MAN POWER (Man-Day)
No | Description | [10 empty] | No |  | Description | [7 empty] | Unit |  |  | Qty
1 | Pelepasan Beksiting Pondasi
2 | Pelepasan Beksiting Pondasi
3 | 0
4 | 0
0
[14 empty] | T o t a l | [7 empty] | prs |  |  | 0
CONSUMABLE MATERIAL | [9 empty] | EQUIPMENT (Unit-Day)
No | Description |  |  |  | Unit |  | Qty | Prev. | Cum. | No | Description | [7 empty] | Unit | Qty |  |  |  | Remarks
1
2
3
4
5
6
No | Activity Plan of Tomorrow
pengecoran pilecap A1
P H O T O / M A P | [16 empty] | A C T I V I T Y
Pelepasan Beksiting Pondasi
Pelepasan Beksiting Pondasi
Pelepasan Beksiting Pondasi