## Cover
Mine Site Batu Kajang, Kalimantan Timur
SLURRY REMOVAL REPORT
Y 2023
CONTENTS:
1. Summary Report
2. Achievement
3. Schedule
4. Mud Progress
- PT SIMS
- PT PAMA
- PT PETROSEA
- PT BIMA NUSA
Production Department

## Summary Report
■ Slurry Removal Y2023
>> InPit
Plan | [15 empty] | Unit : m3
Class |  | Plan | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Remaks
SIMS | SM A1 | 280000 | Jan: 50000; Feb: 50000; Mar: 100000; Apr: 80000
| SM A3 | 510000 | 50000 | 80000 | 30000 | 50000 | 50000 | 50000 | 50000 | 50000 | 50000 | 50000
| SM B2 | 150000 | Jun: 50000; Jul: 50000; Aug: 50000
PAMA | RTS-C3 West | 681582 | Jul: 168711; Aug: 132470; Sep: 133119; Oct: 130113; Nov: 117169
| RTS-C3 East | 56561 | Jan: 56561
| RTS-D1 | 156371 | Jan: 45492; Feb: 110879
| RTS-D2 | 1500000 | 125000 | 125000 | 125000 | 125000 | 125000 | 125000 | 125000 | 125000 | 125000 | 125000 | 125000 | 125000
| RTS-G | 334743 | Feb: 99791; Mar: 101477; Apr: 94761; May: 38714
| RTN | 0
| RTM | 1539016 | 128251.3333 | 128251.3333 | 128251.3333 | 128251.3333 | 128251.3333 | 128251.3333 | 128251.3333 | 128251.3333 | 128251.3333 | 128251.3333 | 128251.3333 | 128251.3333
| SM 6 | 397204 | Apr: 89824; May: 83898; Jun: 119063; Jul: 104419
PTP | SM-B | 900000 | 75000 | 75000 | 75000 | 75000 | 75000 | 75000 | 75000 | 75000 | 75000 | 75000 | 75000 | 75000
| SM-D | 1100000 |  |  | 116666.6667 | 116666.6667 | 116666.6667 | 85714.2857 | 85714.2857 | 85714.2857 | 85714.2857 | 85714.2857 | 160714.2857 | 160714.2857
BIMA | SSB | 31805 | Jan: 11000; Feb: 7592; Mar: 13213
Total |  | 7637282 | 541304.3333 | 676513.3333 | 689608 | 759503 | 617530 | 633028.619 | 787095.619 | 646435.619 | 597084.619 | 594078.619 | 606134.619 | 488965.619
Actual (Until May) | [15 empty] | Unit : m3
Class |  | Plan | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Total | Remain
SIMS | SM A1 | 280000 | Jan: 132996.9544; Feb: 17408.25; Mar: 101797.8879; Apr: 39030.4935; May: 89145.3529 | 380378.9388 | 100378.9388
| SM A3 | 510000 | Jan: 39100.3367; Feb: 77417.8431; Mar: 49886.86 | 166405.0398 | -343594.9602
| SM B2 | 150000 | [12 empty] | 0 | -150000
PAMA | RTS-C3 West | 681582 | May: 53936 | 53936 | -627646
| RTS-C3 East | 56561 | Jan: 74014; Feb: 34518; Mar: 19020; Apr: 20 | 127572 | 71011
| RTS-D1 | 156371 | Jan: 114930; Feb: 75430; Apr: 4760 | 195120 | 38749
| RTS-D2 | 1500000 | Jan: 135161; Feb: 313857.1; Mar: 166127.1; Apr: 114132; May: 147252 | 876529.2 | -623470.8
| RTS-G | 334743 | Mar: 8960 | 8960 | -325783
| RTN | 0 | Apr: 38 | 38 | 38
| RTM | 1539016 | Jan: 225836; Feb: 234157.95; Mar: 255494.35; Apr: 120148.7; May: 125976 | 961613 | -577403
| SM 6 | 397204 | Mar: 190 | 190 | -397014
PTP | SM-B | 900000 | Mar: 12668; Apr: 98617; May: 21203 | 132488 | -767512
| SM-D | 1100000 | Jan: 33325; Feb: 66802; Mar: 31325; Apr: 41025; May: 100350 | 272827 | -827173
BIMA | SSB | 31805 | Jan: 2502.5; Feb: 14209 | 16711.5 | -15093.5
Total |  | 7637282 | 757865.7911 | 833800.1431 | 645469.1979 | 417771.1935 | 537862.3529 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3192768.6786 | -4444513.3214
2023-05-01 | Comment
Sims | Plan volume SM-A1 0 km3
Week 1 | • No Activity
Week 2 | • No Activity
Week 3 | • 2 X Dragflow
Week 4 | • 2 X Dragflow
Week 5 | • No Activity
Plan volume SM A3 50 km3
Week 1 | • No Activity
Week 2 | • No Activity
Week 3 | • No Activity
Week 4 | • No Activity
Week 5 | • No Activity
Plan volume SM B2 0 km3
Week 1 | • No Activity
Week 2 | • No Activity
Week 3 | • No Activity
Week 4 | • HT 2702
Week 5 | • No Activity
Plan volume SM B 0 km3
Week 1 | • No Activity
Week 2 | • No Activity
Week 3 | • No Activity
Week 4 | • No Activity
Week 5 | • No Activity
Pama | Plan volume RTS-C3 West 0 km3
Week 1 | • No Activity
Week 2 | • 1 X PC2000
Week 3 | • 1 X PC2000
Week 4 | • 1 X PC1250
Week 5 | • No Activity
Plan volume RTS-C3 East 0 km3
Week 1 | • No Activity
Week 2 | • No Activity
Week 3 | • No Activity
Week 4 | • No Activity
Week 5 | • No Activity
Plan volume RTS-D1 0 km3
Week 1 | • No Activity
Week 2 | • No Activity
Week 3 | • No Activity
Week 4 | • No Activity
Week 5 | • No Activity
Plan volume RTS-D2 125 km3
Week 1 | • 1 X LINE ARTAMA
Week 2 | • 2 X LINE ARTAMA
Week 3 | • 2 X LINE ARTAMA
Week 4 | • 2 X LINE ARTAMA + 1 X PC1250
Week 5 | • No Activity
Plan volume RTS-G 38.7 km3
Week 1 | • No Activity
Week 2 | • No Activity
Week 3 | • No Activity
Week 4 | • No Activity
Week 5 | • No Activity
Plan volume RTN 0 km3
Week 1 | • No Activity
Week 2 | • No Activity
Week 3 | • No Activity
Week 4 | • 1 X PC 850
Week 5 | • No Activity
Plan volume RTM 128.2 km3
Week 1 | • 1 LINE ARTAMA + 2 X Dragflow
Week 2 | • 1 LINE ARTAMA + 2 X Dragflow
Week 3 | • 1 LINE ARTAMA + 1 X Dragflow
Week 4 | • No Activity
Week 5 | • No Activity
Plan volume SM-6 83.8 km3
Week 1 | • No Activity
Week 2 | • No Activity
Week 3 | • No Activity
Week 4 | • No Activity
Week 5 | • No Activity
PTP | Plan volume SM B 75 km3
Week 1 | • Dragflow
Week 2 | • No Activity
Week 3 | • No Activity
Week 4 | • No Activity
Week 5 | • No Activity
Plan volume SM D 116.6 km3
Week 1 | • Digger AL 52
Week 2 | • Digger AL 52
Week 3 | • Digger AL 52
Week 4 | • Digger AL 52
Week 5 | • No Activity
Plan volume SM-D1 0 km3
Week 1 | • No Activity
Week 2 | • No Activity
Week 3 | • No Activity
Week 4 | • No Activity
Week 5 | • No Activity
Plan volume SM-D2 0 km3
Week 1 | • No Activity
Week 2 | • No Activity
Week 3 | • No Activity
Week 4 | • No Activity
Week 5 | • No Activity
BIMA | Plan volume SSB 0 km3
Week 1 | • No Activity
Week 2 | • No Activity
Week 3 | • No Activity
Week 4 | • No Activity
Week 5 | • No Activity
>> Company (Contractors) | [15 empty] | Unit : m3
Company |  | Plan | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Total | Remain
SIMS |  | 940000 | 172097.2911 | 94826.0931 | 151684.7479 | 39030.4935 | 89145.3529 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 546783.9786 | -393216.0214
PAMA |  | 4665477 | 549941 | 657963.05 | 449601.45 | 239098.7 | 327164 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2223768.2 | -2441708.8
PTP |  | 2000000 | 33325 | 66802 | 43993 | 139642 | 121553 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 405315 | -1594685
BIMA |  | 31805 | 2502.5 | 14209 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16711.5 | -15093.5
Total |  | 7637282 | 757865.7911 | 833800.1431 | 645279.1979 | 417771.1935 | 537862.3529 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3192578.6786 | -4444703.3214
>> OutPit
Plan & Actual (Progress)
Class |  | Plan | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Total | Remain
SIMS | SM AW | 0 | [12 empty] | 0 | 0
| WD SM B1 (S/P AL-61) | 160000 | [12 empty] | 0 | -160000
WD SM B2 | bar: Jul to Nov
BIMA
PAMA | Sump C4 | [13 empty] | 0 | 0
PTP | [14 empty] | 0 | 0
Total |  | 160000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -160000
Plan & Actual (Settling Pond) | [15 empty] | Unit : m3
Class |  | Plan | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Total | Remain
SIMS | WD SM B1 (S/P AL-61) | 160000 | [12 empty] | 0 | -160000
BIMA | S/Pond AL-SSB02 | 25000 | [12 empty] | 0 | -25000
| S/Pond AL-SSB03 | 3000 | [12 empty] | 0 | -3000
| S/Pond AL-SSB04 | 4000 | [12 empty] | 0 | -4000
| S/Pond AL-SSB05 | 7000 | [12 empty] | 0 | -7000
| S/Pond AL-SSB06 | 15000 | [12 empty] | 0 | -15000
[15 empty] | 0 | 0
[15 empty] | 0 | 0
|  | 0 | [12 empty] | 0 | 0
| S/Pond AB 03 | 0 | Feb: 0; Mar: 0; Apr: 0 | 0 | 0
| S/Pond AL 54 | 0 | [12 empty] | 0 | 0
| S/Pond AL 59 | 0 | Jan: 0; Apr: 0 | 0 | 0
| S/Pond AL 66 | 0 | [12 empty] | 0 | 0
| S/Pond AL 28 | 0 | Apr: 0; May: 0; Jun: 0; Jul: 0; Aug: 0; Sep: 0 | 0 | 0
| S/Pond AL 57 | 0 | [12 empty] | 0 | 0
| S/Pond AL 55 | 0 | [12 empty] | 0 | 0
| S/Pond AL 56 | 0 | [12 empty] | 0 | 0
| S/Pond AL 11 | 0 | Sep: 0; Oct: 0; Nov: 0 | 0 | 0
PAMA |  |  | Jan: 0; Mar: 70960; Apr: 16460; May: 62120; Sep: 0; Oct: 0; Nov: 0 | 149540 | 149540
| EX S/Pond Temporary | 0 | [12 empty] | 0 | 0
PTP | EX S/Pond AL 52 | 950000 | [12 empty] | 0 | -950000
Total |  | 1164000 | 0 | 0 | 70960 | 16460 | 62120 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 149540 | -1014460
Plan & Actual (Control Box) | [15 empty] | Unit : m3
Class |  | Plan | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Total | Remain
PAMA | CB 7B | 400000 | Mar: 70960; Apr: 16460; May: 62120 | 149540 | -250460
[15 empty] | 0 | 0
[15 empty] | 0 | 0
PTP | Control Box AL 52 | 390000 | [12 empty] | 0 | -390000
| Control Box AL 68 | 280000 | [12 empty] | 0 | -280000
| Control Box SMD | [13 empty] | 0 | 0
BIMA | Control Box AL-SSB02 | 7846 | [12 empty] | 0 | -7846
| Control Box AL-SSB07 | 14704 | [12 empty] | 0 | -14704
Total |  | 1092550 | 0 | 0 | 70960 | 16460 | 62120 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 149540 | -943010

## Achive
27
Class |  | Plan & Actual(~04/30) |  |  | Monthly(05/01~05/27 |  |  |  | Yearly(~05/27) | [5 empty] | RemainY2023 (Survey)
|  | Plan | Actual | Achiv | Plan | Actual | Achiv | Remain | Plan | Actual | Achiv (Plan/Actual) |  |  | Remain | Elev (ML) | Volume | Elv. Update |  |  | Class |  | Plan | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Remaks
SIMS | SM A1 | 280 | 289.6623 | 103.5% | 0 | 89.1454 | 0% | -89.1454 | 280 | 378.8076 | 100% | / | 135.3% | 0 |  | 400000 | 2022-06-02 | --> Survey by Cont. | -9.6623 | SIMS | SM A1 | 280000 | Jan: 50000; Feb: 50000; Mar: 100000; Apr: 80000
| SM A3 | 210 | 166.405 | 79.24% | 93.595 | 0 | 0% | 93.595 | 510 | 166.405 | 100% | / | 32.63% | 343.595 |  |  | 2022-06-02 |  | 43.595 |  | SM A3 | 510000 | 50000 | 80000 | 30000 | 50000 | 50000 | 50000 | 50000 | 50000 | 50000 | 50000
| SM B2 | 0 | 0 | 0% | 0 | 0 | 0% | 0 | 150 | 0 | 100% | / | 0% | 150 |  | 0 | 2022-06-02 | --> Survey by Cont. | 0 |  | SM B2 | 150000 | Jun: 50000; Jul: 50000; Aug: 50000
| Total | 490 | 456.0673 | 93.07% | 93.595 | 89.1454 | 95.25% | 4.4496 | 940 | 545.2127 | 100% | / | 58% | 493.595 |  | 400000 | [5 empty] | 940000 | 100000 | 130000 | 130000 | 130000 | 50000 | 100000 | 100000 | 100000 | 50000 | 50000 | 0 | 0
Class |  | Plan & Actual(~04/30) |  |  | Monthly(05/01~05/27 |  |  |  | Yearly(~05/27) | [5 empty] | RemainY2023 (Survey)
|  | Plan | Actual | Achiv | Plan | Actual | Achiv | Remain | Plan | Actual | Achiv (Plan/Actual) | 0 | 0 | Remain | Elev (ML) | Volume
PAMA | RTS-C3 West | 0 | 0 | 0% | 0 | 55.4 | 0% | 0 | 681.582 | 55.4 | 100% | / | 8.128% | 626.182 |  | 108644.78 | 2022-06-02 | --> Survey by Cont. | 0 | PAMA | RTS-C3 West | 681582 | Jul: 168711; Aug: 132470; Sep: 133119; Oct: 130113; Nov: 117169
| RTS-C3 East | 56.561 | 127.572 | 225.5% | 0 | 0 | 0% | 0 | 56.561 | 127.572 | 100% | / | 225.5% | 0 |  | 108644.78 | 2022-06-02 | --> Survey by Cont. | -71.011 |  | RTS-C4 | 56561 | Jan: 56561
| RTS-D1 | 156.371 | 195.12 | 124.8% | 0 | 0 | 0% | 0 | 156.371 | 195.12 | 100% | / | 124.8% | 0 |  | 692200 | 2022-06-02 | --> Survey by Cont. | -38.749 |  | RTS-D1 | 156371 | Jan: 45492; Feb: 110879
| RTS-D2 | 500 | 729.2772 | 145.9% | 125 | 156.54 | 125.2% | 0 | 1500 | 885.8172 | 98.92% | / | 59.05% | 614.1828 |  | 1500000 | 2022-06-02 | --> Survey by Cont. | -229.2772 |  | RTS-D2 | 1500000 | 125000 | 125000 | 125000 | 125000 | 125000 | 125000 | 125000 | 125000 | 125000 | 125000 | 125000 | 125000
| RTS-G | 296.029 | 8.96 | 3.027% | 325.783 | 0 | 0% | 325.783 | 334.743 | 8.96 | 100% | / | 2.677% | 325.783 |  | 300000 | 2022-06-02 | --> Survey by Cont. | 287.069 |  | RTS-G | 334743 | Feb: 99791; Mar: 101477; Apr: 94761; May: 38714
| RTN | 0 | 0.228 | 0% | 0 | 0.72 | 0% | -0.72 | 0 | 0.948 | 0% |  | 0% | 0 |  |  | 2022-06-02 | --> Survey by Cont. | -0.228 |  | RTN | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| RTM | 513.0053 | 835.637 | 162.9% | 128.2513 | 125.976 | 98.23% | 2.2753 | 1539.016 | 961.613 | 98.92% | / | 62.48% | 577.403 |  | 1900000 | 2022-06-02 | --> Survey by Cont. | -322.6317 |  | RTM | 1539016 | 128251.3333 | 128251.3333 | 128251.3333 | 128251.3333 | 128251.3333 | 128251.3333 | 128251.3333 | 128251.3333 | 128251.3333 | 128251.3333 | 128251.3333 | 128251.3333
| SM 6 | 89.824 | 0.19 | 0.2115% | 173.532 | 0 | 0% | 173.532 | 397.204 | 0.19 | 100% | / | 0.04783% | 397.014 |  | 2921908.668 | 2022-06-02 | --> Survey by Cont. | 89.634 |  | SM 6 | 397204 | Apr: 89824; May: 83898; Jun: 119063; Jul: 104419
| Total | 1611.7903 | 1896.9842 | 117.7% | 752.5663 | 338.636 | 45% | 500.8703 | 4665.477 | 2235.6202 | 93.55% | / | 47.92% | 2540.5648 |  | 7531398.228 | [5 empty] | 4665477 | 355304.3333 | 463921.3333 | 354728.3333 | 437836.3333 | 375863.3333 | 372314.3333 | 526381.3333 | 385721.3333 | 386370.3333 | 383364.3333 | 370420.3333 | 253251.3333
Class |  | Plan & Actual(~04/30) |  |  | Monthly(05/01~05/27 |  |  |  | Yearly(~05/27) | [5 empty] | RemainY2023 (Survey)
|  | Plan | Actual | Achiv | Plan | Actual | Achiv | Remain | Plan | Actual | Achiv (Plan/Actual) | 0 | 0 | Remain | Elev (ML) | Volume
PTP | SM-B | 300 | 111.285 | 37.1% | 263.715 | 21.203 | 8.04% | 242.512 | 900 | 132.488 | 98.92% | / | 14.72% | 767.512 |  | 2000000 | 2022-06-02 | --> Survey by Cont. | 188.715 | PTP | SM-B | 900000 | 75000 | 75000 | 75000 | 75000 | 75000 | 75000 | 75000 | 75000 | 75000 | 75000 | 75000 | 75000
| SM-D | 233.334 | 179.277 | 76.83% | 170.724 | 100.35 | 58.78% | 70.374 | 1099.999 | 279.627 | 98.11% | / | 25.42% | 820.372 |  | 1500000 | 2022-06-02 | --> Survey by Cont. | 54.057 |  | SM-D | 1100000 |  |  | 116666.6667 | 116666.6667 | 116666.6667 | 85714.2857 | 85714.2857 | 85714.2857 | 85714.2857 | 85714.2857 | 160714.2857 | 160714.2857
[17 empty] | 2022-06-02 | --> Survey by Cont. | 0 | bar: Jan to Mar; Jun to Nov
[17 empty] | 2022-06-02 | --> Survey by Cont. | 0 | bar: Sep to Dec
| Total | 533.334 | 290.562 | 54.48% | 434.439 | 121.553 | 27.98% | 312.886 | 1999.999 | 412.115 | 86.69% | / | 20.61% | 1587.884 |  | 0 | [5 empty] | 2000000 | 75000 | 75000 | 191666.6667 | 191666.6667 | 191666.6667 | 160714.2857 | 160714.2857 | 160714.2857 | 160714.2857 | 160714.2857 | 235714.2857 | 235714.2857
Class |  | Plan & Actual(~04/30) |  |  | Monthly(05/01~05/27 |  |  |  | Yearly(~05/27) | [5 empty] | RemainY2023 (Survey)
|  | Plan | Actual | Achiv | Plan | Actual | Achiv | Remain | Plan | Actual | Achiv (Plan/Actual) | 0 | 0 | Remain | Elev (ML) | Volume
BIMA | SSB | 31.805 | 16.7115 | 52.54% | 15.0935 | 0 | 0% | 15.0935 | 31.805 | 16.7115 | 100% | / | 52.54% | 15.0935 |  | 40000 | 2022-06-02 | --> Survey by Cont. | 15.0935 | BIMA | SSB | 31805 | 11000 | 7592 | 13213 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Total | 31.805 | 16.7115 | 52.54% | 15.0935 | 0 | 0% | 15.0935 | 31.805 | 16.7115 | 100% | / | 52.54% | 15.0935 |  | 40000 | [5 empty] | 31805 | 11000 | 7592 | 13213 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total |  | 2666.9293 | 2660.325 | 99.75% | 1295.6938 | 549.3344 | 42.4% | 833.2994 | 7637.281 | 3209.6594 | 92.57% | / | 42.03% | 4637.1373 |  | 7971398.228 |  |  | 6.6043 | Total |  | 7637282 | 541304.3333 | 676513.3333 | 689608 | 759503 | 617530 | 633028.619 | 787095.619 | 646435.619 | 597084.619 | 594078.619 | 606134.619 | 488965.619
Class |  | Plan & Actual(~04/30) |  |  | Monthly(05/01~05/27 |  |  |  | Yearly(~05/27) | [5 empty] | RemainY2023 (Survey) |  |  |  | %
|  | Plan | Actual | Achiv | Plan | Actual | Achiv | Remain | Plan | Actual | Achiv (Plan/Actual) | 0 | 0 | Remain | Elev (ML) | Volume |  | Plan (Actual+Remain Survey)
SIMS |  | 490 | 456.0673 | 93.07% | 93.595 | 89.1454 | 95.25% | 4.4496 | 940 | 545.2127 | 100% | / | 58% | 493.595 |  | 400000 |  | 400545.2127 | 0.0013612 | SIMS |  | 940000 | 100000 | 130000 | 130000 | 130000 | 50000 | 100000 | 100000 | 100000 | 50000 | 50000 | 0 | 0
PAMA |  | 1611.7903 | 1896.9842 | 117.7% | 752.5663 | 338.636 | 45% | 413.9303 | 4665.477 | 2235.6202 | 99.3% | / | 47.92% | 2540.5648 |  | 7531398.228 |  | 7533633.8482 | 0.02968% | PAMA |  | 4665477 | 355304.3333 | 463921.3333 | 354728.3333 | 437836.3333 | 375863.3333 | 372314.3333 | 526381.3333 | 385721.3333 | 386370.3333 | 383364.3333 | 370420.3333 | 253251.3333
PTP |  | 533.334 | 290.562 | 54.48% | 434.439 | 121.553 | 27.98% | 312.886 | 1999.999 | 412.115 | 98.48% | / | 20.61% | 1587.884 |  | 0 |  | 412.115 | 100% | PTP |  | 2000000 | 75000 | 75000 | 191666.6667 | 191666.6667 | 191666.6667 | 160714.2857 | 160714.2857 | 160714.2857 | 160714.2857 | 160714.2857 | 235714.2857 | 235714.2857
BIMA |  | 31.805 | 16.7115 | 52.54% | 15.0935 | 0 | 0% | 15.0935 | 31.805 | 16.7115 | 100% | / | 52.54% | 15.0935 |  | 40000 |  | 40016.7115 | 0.04176% | BIMA |  | 31805 | 11000 | 7592 | 13213 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TOTAL |  | 2666.9293 | 2660.325 | 99.75% | 1295.6938 | 549.3344 | 42.4% | 746.3594 | 7637.281 | 3209.6594 | 92.57% | / | 42.03% | 4637.1373 |  | 7971398.228 |  | 7974607.8874 | 0.04025% | Total |  | 7637282 | 541304.3333 | 676513.3333 | 689608 | 759503 | 617530 | 633028.619 | 787095.619 | 646435.619 | 597084.619 | 594078.619 | 606134.619 | 488965.619
Note on U4: Gusti Elissa Damayanti: ditambah kalo +

## Schedule
KOMITMEN PENGERJAAN SLURRY REMOVAL 2022
Unit : Km3
Class |  |  | '23 Total | Jan |  |  |  |  | Feb |  |  |  |  | Mar |  |  |  |  | Apr |  |  |  |  | YTD | May |  |  |  |  | Jun |  |  |  |  | Jul |  |  |  |  | Aug |  |  |  |  | Sep |  |  |  |  | Oct |  |  |  |  | Nov |  |  |  |  | Dec |  |  |  |  | Total
|  |  |  | I (1-7) | II (8-14) | III (15-21) | IV (22-28) | V (29-31) | I (1-4) | II (5-11) | III (12-18) | IV (19-25) | V (26-28) | I (1-4) | II (5-11) | III (12-18) | IV (19-25) | V (26-31) | I (1) | II (2-8) | III (9-15) | IV (16-22) | V (23-30) | (04/01) | I (1-6) | II (7-13) | III (14-20) | IV (21-27) | V (28-31) | I (1-3) | II (4-10) | III (11-17) | IV (18-24) | V (25-30) | I (1) | II (2-8) | III (9-15) | IV (16-22) | V (23-31) | I (1-5) | II (6-12) | III (13-19) | IV (20-26) | V (27-31) | I (1-2) | II (3-9) | III (10-16) | IV (17-23) | V (24-30) | I (1) | II (2-7) | III (8-14) | IV (15-21) | V (22-31) | I (1-4) | II (5-11) | III (12-18) | IV (19-25) | V (26-30) | I (1-2) | II (3-9) | III (10-16) | IV (17-23) | V (24-31)
SIMS | SM A1 | Plan | 280 | 50 |  |  |  |  | 50 |  |  |  |  | 100 |  |  |  |  | 80 |  |  |  |  | 280 | [40 empty] | 280
|  | Actual | 378.8076 | 25.8944 | 36.2531 | 35.7416 | 28.2583 | 6.8496 | 7.0811 | 10.3271 | 0 | 0 | 0 | 0 | 7.1471 | 19.0024 | 29.3045 | 46.3439 | 1.9821 | 35.4771 |  |  |  | 289.6623 |  |  | 44.9614 | 44.184 | [6 empty] | 0 | 0 | 0 | [27 empty] | 378.8076
| SM A3 | Plan | 510 | 50 |  |  |  |  | 80 |  |  |  |  | 30 |  |  |  |  | 50 |  |  |  |  | 210 | 50 |  |  |  |  | 50 |  |  |  |  | 50 |  |  |  |  | 50 |  |  |  |  | 50 |  |  |  |  | 50 | [14 empty] | 510
|  | Actual | 166.405 | 0 | 9.4671 | 14.5323 | 11.4078 | 3.6932 | 5.4417 | 16.3375 | 11.4309 | 34.9899 | 9.2178 | 15.0822 | 18.443 | 6.4254 | 9.9362 | 0 | [5 empty] | 166.405 |  |  |  |  | 0 | [21 empty] | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 166.405
| SM B2 | Plan | 150 | [20 empty] | 0 | [5 empty] | 50 |  |  |  |  | 50 |  |  |  |  | 50 | [24 empty] | 150
|  | Actual | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | [9 empty] | 0 |  |  |  | 0 | [36 empty] | 0
| #REF! | Plan | 0 | [20 empty] | 0 | [40 empty] | 0
|  | Actual | 0 | [20 empty] | 0 | [40 empty] | 0
| S-Tot Plan |  | 940 | 100 |  |  |  |  | 130 |  |  |  |  | 130 |  |  |  |  | 130 |  |  |  |  | 490 | 50 |  |  |  |  | 100 |  |  |  |  | 100 |  |  |  |  | 100 |  |  |  |  | 50 |  |  |  |  | 50 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 940
| S-Tot Actual |  | 467.7948 | 172.0973 |  |  |  |  | 17.4083 |  |  |  |  | 151.6847 |  |  |  |  | 37.4592 |  |  |  |  | 378.6495 | 89.1454 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 467.7948
PAMA | RTS-C3 West | Plan | 681.582 | [20 empty] | 0 | [10 empty] | 168.711 |  |  |  |  | 132.47 |  |  |  |  | 133.119 |  |  |  |  | 130.113 |  |  |  |  | 117.169 | [9 empty] | 681.582
|  | Actual | 55.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 10.184 | 32.928 | 12.288 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 55.4
| RTS-C3 East | Plan | 56.561 | 56.561 | [19 empty] | 56.561 | [40 empty] | 56.561
|  | Actual | 127.572 | 9.338 | 3.198 | 17.102 | 32.092 | 12.284 | 13.482 | 0 | 5.26 | 4.78 | 10.996 | 0.02 | 0 | 6.2 | 12.2 | 0.6 | 0 | 0 | 0.02 |  |  | 127.572 | [9 empty] | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 127.572
| RTS-D1 | Plan | 156.371 | 45.492 |  |  |  |  | 110.879 | [14 empty] | 156.371 | [40 empty] | 156.371
|  | Actual | 195.12 | 17.99 | 35.796 | 22.562 | 33.736 | 4.846 | 16.036 | 59.394 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0.38 | 4.38 |  |  | 195.12 | [9 empty] | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 195.12
| RTS-D2 | Plan | 1500 | 125 |  |  |  |  | 125 |  |  |  |  | 125 |  |  |  |  | 125 |  |  |  |  | 500 | 125 |  |  |  |  | 125 |  |  |  |  | 125 |  |  |  |  | 125 |  |  |  |  | 125 |  |  |  |  | 125 |  |  |  |  | 125 |  |  |  |  | 125 |  |  |  |  | 1500
|  | Actual | 885.8172 | 14.239 | 22.63 | 49.462 | 41.5112 | 7.3188 | 33.7426 | 43.375 | 93.71 | 99.2215 | 43.808 | 37.7733 | 43.3968 | 15.7392 | 29.4936 | 39.7242 | 3.96 | 24.942 | 11.484 | 44.904 | 28.842 | 729.2772 | 9.156 | 43.23 | 60.795 | 43.359 |  | 0 | [11 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 885.8172
| RTS-G | Plan | 334.743 | [5 empty] | 99.791 |  |  |  |  | 101.477 |  |  |  |  | 94.761 |  |  |  |  | 296.029 | 38.714 | [39 empty] | 334.743
|  | Actual | 8.96 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 8.26 | 0.7 | 0 | 0 | 0 | [5 empty] | 8.96 | [40 empty] | 8.96
| RTN | Plan | 0 | [20 empty] | 0 | [40 empty] | 0
|  | Actual | 0.948 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.19 | 0 | 0 | 0 | 0 | 0.038 | 0 | 0.228 |  |  |  | 0.72 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.948
| RTM | Plan | 1539.016 | 128.2513 |  |  |  |  | 128.2513 |  |  |  |  | 128.2513 |  |  |  |  | 128.2513 |  |  |  |  | 513.0053 | 128.2513 |  |  |  |  | 128.2513 |  |  |  |  | 128.2513 |  |  |  |  | 128.2513 |  |  |  |  | 128.2513 |  |  |  |  | 128.2513 |  |  |  |  | 128.2513 |  |  |  |  | 128.2513 |  |  |  |  | 1539.016
|  | Actual | 961.613 | 40.347 | 32.687 | 28.294 | 96.005 | 28.503 | 27.3898 | 55.2931 | 51.2132 | 73.1323 | 27.1295 | 30.1876 | 53.3017 | 44.6192 | 64.8953 | 62.4905 | 9.9148 | 38.5483 | 16.8442 | 31.8412 | 23.0002 | 835.637 | 16.3435 | 42.0737 | 44.557 | 23.0018 | [27 empty] | 0 | 0 | 0 |  | 0 |  |  |  |  | 961.613
| SM 6 | Plan | 397.204 | [15 empty] | 89.824 |  |  |  |  | 89.824 | 83.898 |  |  |  |  | 119.063 |  |  |  |  | 104.419 | [29 empty] | 397.204
|  | Actual | 0.19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0.19 | 0 | 0 | 0 | 0 | 0 | 0.19 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.19
| S-Tot Plan |  | 4665.477 | 355.3043 |  |  |  |  | 463.9213 |  |  |  |  | 354.7283 |  |  |  |  | 437.8363 |  |  |  |  | 1611.7903 | 375.8633 |  |  |  |  | 372.3143 |  |  |  |  | 526.3813 |  |  |  |  | 385.7213 |  |  |  |  | 386.3703 |  |  |  |  | 383.3643 |  |  |  |  | 370.4203 |  |  |  |  | 253.2513 |  |  |  |  | 4665.477
| S-Tot Actual |  | 2108.0682 | 475.927 |  |  |  |  | 623.445 |  |  |  |  | 430.9614 |  |  |  |  | 239.0987 |  |  |  |  | 1769.4322 | 338.636 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 2108.0682
PTP | SM-B | Plan | 900 | 75 |  |  |  |  | 75 |  |  |  |  | 75 |  |  |  |  | 75 |  |  |  |  | 300 | 75 |  |  |  |  | 75 |  |  |  |  | 75 |  |  |  |  | 75 |  |  |  |  | 75 |  |  |  |  | 75 |  |  |  |  | 75 |  |  |  |  | 75 |  |  |  |  | 900
|  | Actual | 132.488 | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 3 | 9.668 | 0 | 13.265 | 19.562 | 28.206 | 37.584 | 111.285 | 21.203 | 0 | 0 | [37 empty] | 132.488
| SM-D | Plan | 1099.999 | [10 empty] | 116.667 |  |  |  |  | 116.667 |  |  |  |  | 233.334 | 116.667 |  |  |  |  | 85.714 |  |  |  |  | 85.714 |  |  |  |  | 85.714 |  |  |  |  | 85.714 |  |  |  |  | 85.714 |  |  |  |  | 160.714 |  |  |  |  | 160.714 |  |  |  |  | 1099.999
|  | Actual | 279.627 | 0 | 8.575 | 9.45 | 15.3 | 0 | 7.606 | 8.821 | 16.6 | 31.525 | 2.25 | 4.525 | 13.3 | 1.45 | 12.05 | 6.8 | 0 | 7.7 | 4.6 | 20.05 | 8.675 | 179.277 | 20.05 | 44.375 | 30 | 5.925 | [36 empty] | 279.627
| #REF! | Plan | 0 | [20 empty] | 0 | [40 empty] | 0
|  | Actual | 0 | [20 empty] | 0 | [40 empty] | 0
| SM-D | Plan | 0 | [20 empty] | 0 | [40 empty] | 0
|  | Actual | 0 | [20 empty] | 0 | [40 empty] | 0
| S-Tot Plan |  | 1174.999 | 0 |  |  |  |  | 0 |  |  |  |  | 116.667 |  |  |  |  | 116.667 |  |  |  |  | 233.334 | 116.667 |  |  |  |  | 85.714 |  |  |  |  | 85.714 |  |  |  |  | 160.714 |  |  |  |  | 85.714 |  |  |  |  | 85.714 |  |  |  |  | 160.714 |  |  |  |  | 160.714 |  |  |  |  | 1174.999
| S-Tot Actual |  | 412.115 | 33.325 |  |  |  |  | 66.802 |  |  |  |  | 50.793 |  |  |  |  | 139.642 |  |  |  |  | 290.562 | 121.553 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 412.115
BIMA | SSB | Plan | 31.805 | 11 |  |  |  |  | 7.592 |  |  |  |  | 13.213 | [9 empty] | 31.805 | [10 empty] | 0 | [29 empty] | 31.805
|  | Actual | 16.7115 |  |  |  | 1.339 | 1.1635 | 2.262 | 8.632 | 1.846 | 1.469 | [11 empty] | 16.7115 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | [10 empty] | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 16.7115
Total (Weekly) | Plan |  |  | 31.2738 | 109.4582 | 109.4582 | 109.4582 | 125.0951 | 144.9671 | 169.1283 | 169.1283 | 169.1283 | 193.2895 | 133.4726 | 155.718 | 155.718 | 155.718 | 88.9817 | 75.9503 | 177.2174 | 177.2174 | 177.2174 | 151.9007 | 144.9671 | 19.9203 | 139.4423 | 139.4423 | 139.4423 | 179.283 | 105.5047 | 147.7066 | 147.7066 | 147.7066 | 84.4038 | 76.1705 | 177.7312 | 177.7312 | 177.7312 | 177.7312 | 145.9693 | 145.9693 | 145.9693 | 145.9693 | 62.5583 | 79.6112 | 139.3197 | 139.3197 | 139.3197 | 99.5141 | 38.3276 | 134.1467 | 134.1467 | 134.1467 | 153.3105 | 121.2269 | 141.4313 | 141.4313 | 141.4313 | 60.6134 | 63.0923 | 110.4115 | 110.4115 | 110.4115 | 94.6385 | 6564.4305
| Actual |  |  | 98.4704 | 145.4082 | 160.0419 | 227.5573 | 52.3741 | 99.5592 | 202.1798 | 174.8001 | 240.3377 | 82.4054 | 95.8281 | 136.2886 | 87.2363 | 148.8697 | 165.2166 | 15.8569 | 120.3124 | 56.8702 | 125.0392 | 98.1012 | 2532.753 | 66.7525 | 139.8627 | 213.2414 | 129.4778 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4131.7065
| Diff |  |  | 199.1085 |  |  |  |  | -46.3595 |  |  |  |  | -56.1691 |  |  |  |  | -343.3234 | [5 empty] | -68.196 |  |  |  |  | -633.0283 |  |  |  |  | -787.0953 |  |  |  |  | -646.4353 |  |  |  |  | -597.0843 |  |  |  |  | -594.0783 |  |  |  |  | -606.1343 |  |  |  |  | -488.9653 |  |  |  |  | -4820.5099
Total | Plan |  | 6812.281 | 466.3043 |  |  |  |  | 601.5133 |  |  |  |  | 614.6083 |  |  |  |  | 684.5033 |  |  |  |  | 1299.1117 | 542.5303 |  |  |  |  | 558.0283 |  |  |  |  | 712.0953 |  |  |  |  | 646.4353 |  |  |  |  | 522.0843 |  |  |  |  | 519.0783 |  |  |  |  | 531.1343 |  |  |  |  | 413.9653 |  |  |  |  | 6428.9667
| Actual |  | 3004.6895 | 683.8518 |  |  |  |  | 721.8643 |  |  |  |  | 633.4392 |  |  |  |  | 416.1999 |  |  |  |  | 1049.6391 | 549.3344 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 2015.1733
| Diff |  | -3807.5915 | 217.5475 |  |  |  |  | 120.351 |  |  |  |  | 18.8309 |  |  |  |  | -268.3034 |  |  |  |  | -249.4726 | 6.804 |  |  |  |  | -558.0283 |  |  |  |  | -712.0953 |  |  |  |  | -646.4353 |  |  |  |  | -522.0843 |  |  |  |  | -519.0783 |  |  |  |  | -531.1343 |  |  |  |  | -413.9653 |  |  |  |  | -4413.7933
*Catatan : Hanya lumpur di dalam Pit (lokasi sump)
Sebelumnya izinkan kami untuk menyampaikan terima kasih atas kerjasama yang baik selama ini dalam mendukung kelancaran kegiatan operasional. Dalam usaha mendukung tercapainya target produksi tahun 2022 maka dengan ini PT. Kideco Jaya Agung dan Mitra Kerja berkomitmen dalam pengerjaan slurry removal sesuai dengan target volume dan jadwal tersebut di atas dengan mengacu pada prosedur manajemen loading lumpur yang memberikan arahan dan pedoman perlakuan material lumpur dengan aman, melindungi manusia dan alat yang bekerja, serta tidak memberikan efek pencemaran lingkungan ataupun menimbulkan gangguan kestabilan waste dump

## PTP
■ Hasil Loading Lumpur
2021-01-01
Class | Pit | Volume |  |  | 2021-01-01 | 2021-01-02 | 2021-01-03 | 2021-01-04 | 2021-01-05 | 2021-01-06 | 2021-01-07 | 2021-01-08 | 2021-01-09 | 2021-01-10 | 2021-01-11 | 2021-01-12 | 2021-01-13 | 2021-01-14 | 2021-01-15 | 2021-01-16 | 2021-01-17 | 2021-01-18 | 2021-01-19 | 2021-01-20 | 2021-01-21 | 2021-01-22 | 2021-01-23 | 2021-01-24 | 2021-01-25 | 2021-01-26 | 2021-01-27 | 2021-01-28 | 2021-01-29 | 2021-01-30 | 2021-01-31 | Total
SM-D2 |  | Vol. Target | Monthly Plan Vol. | Remain
| Unit | 900000 | 75000 | 900000
| SM-B | [34 empty] | 0
| Unit | 1100000 |  | 1066675 | Digger AL52 | Digger AL52 | Digger AL52 | Digger AL52 | Digger AL52 | Digger AL52 | Digger AL52 | Digger AL52 | Digger AL52 | Digger AL52 | Digger AL52 | Digger AL52 | Digger AL52 | Digger AL52 | Digger AL52 | Digger AL52 | Digger AL52 | Digger AL52 | Digger AL52 | Digger AL52 | Digger AL52 | Digger AL52 | Digger AL52 | Digger AL52 | Digger AL52 | Digger AL52 | Digger AL52 | Digger AL52 | Digger AL52 | Digger AL52 | Digger AL52
| SM-D |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8575 | 0 | 0 | 0 | 0 | 0 | 3150 | 6300 | 0 | 0 | 0 | 10950 | 0 | 0 | 0 | 0 | 4350 | 0 | 0 | 0 | 33325
Unit
0
Unit
| SM-D | [34 empty] | 0
Total |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8575 | 0 | 0 | 0 | 0 | 0 | 3150 | 6300 | 0 | 0 | 0 | 10950 | 0 | 0 | 0 | 0 | 4350 | 0 | 0 | 0 | 33325
2021-02-01
Class | Pit | Volume |  |  | 2021-02-01 | 2021-02-02 | 2021-02-03 | 2021-02-04 | 2021-02-05 | 2021-02-06 | 2021-02-07 | 2021-02-08 | 2021-02-09 | 2021-02-10 | 2021-02-11 | 2021-02-12 | 2021-02-13 | 2021-02-14 | 2021-02-15 | 2021-02-16 | 2021-02-17 | 2021-02-18 | 2021-02-19 | 2021-02-20 | 2021-02-21 | 2021-02-22 | 2021-02-23 | 2021-02-24 | 2021-02-25 | 2021-02-26 | 2021-02-27 | 2021-02-28 | 2021-03-01 | 2021-03-02 | 2021-03-03 | Total
Roto / SM |  | Vol. Target | Monthly Plan Vol. | Remain
| Unit | 900000 | 75000 | 900000
| SM-B | [34 empty] | 0
| Unit | 1066675 |  | 999873 | Digger AL52 | Digger AL52 | Digger AL52 | Digger AL52 | Digger AL52 | Digger AL52 | Digger AL52 | Digger AL52 | Digger AL52 | Digger AL52 | Digger AL52 | Digger AL52 | Digger AL52 | Digger AL52 | Digger AL52 | Digger AL52 | Digger AL52 | Digger AL52 | Digger AL52 | Digger AL52 | Digger AL52 | Digger AL52 | Digger AL52 | Digger AL52 | Digger AL52 | Digger AL52 | Digger AL52 | Digger AL52 | Digger AL52 | Digger AL52 | Digger AL52
| SM-D |  |  |  | 0 | 0 | 5050 | 2556 | 0 | 0 | 0 | 3071 | 0 | 5750 | 0 | 0 | 5500 | 4725 | 0 | 3225 | 1100 | 2050 | 5025 | 3075 | 4075 | 4050 | 6775 | 2125 | 6400 | 0 | 0 | 2250 |  |  |  | 66802
| Unit | 0 |  | 0
| 0 | [34 empty] | 0
| Unit | 0 |  | 0
| SM-D | [34 empty] | 0
Total |  |  |  |  | 0 | 0 | 5050 | 2556 | 0 | 0 | 0 | 3071 | 0 | 5750 | 0 | 0 | 5500 | 4725 | 0 | 3225 | 1100 | 2050 | 5025 | 3075 | 4075 | 4050 | 6775 | 2125 | 6400 | 0 | 0 | 2250 |  |  |  | 66802
2021-03-01
Class | Pit | Volume |  |  | 2021-03-01 | 2021-03-02 | 2021-03-03 | 2021-03-04 | 2021-03-05 | 2021-03-06 | 2021-03-07 | 2021-03-08 | 2021-03-09 | 2021-03-10 | 2021-03-11 | 2021-03-12 | 2021-03-13 | 2021-03-14 | 2021-03-15 | 2021-03-16 | 2021-03-17 | 2021-03-18 | 2021-03-19 | 2021-03-20 | 2021-03-21 | 2021-03-22 | 2021-03-23 | 2021-03-24 | 2021-03-25 | 2021-03-26 | 2021-03-27 | 2021-03-28 | 2021-03-29 | 2021-03-30 | 2021-03-31 | Total
Roto / SM |  | Vol. Target | Monthly Plan Vol. | Remain
| Unit | 900000 | 75000 | 887332 | 2021-03-25: Dragflow; 2021-03-26: Dragflow; 2021-03-27: Dragflow; 2021-03-28: Dragflow; 2021-03-29: Dragflow; 2021-03-30: Dragflow; 2021-03-31: Dragflow
| SM-B |  |  |  | 2021-03-25: 3000; 2021-03-26: 2250; 2021-03-27: 1750; 2021-03-28: 2685; 2021-03-29: 975; 2021-03-30: 2008; 2021-03-31: 0 | 12668
| Unit | 999873 | 116666.6667 | 968548 | Digger AL52 | Digger AL52 | Digger AL52 | Digger AL52 | Digger AL52 | Digger AL52 | Digger AL52 | Digger AL52 | Digger AL52 | Digger AL52 | Digger AL52 | Digger AL52 | Digger AL52 | Digger AL52 | Digger AL52 | Digger AL52 | Digger AL52 | Digger AL52 | Digger AL52 | Digger AL52 | Digger AL52 | Digger AL52 | Digger AL52 | Digger AL52 | Digger AL52 | Digger AL52 | Digger AL52 | Digger AL52 | Digger AL52 | Digger AL52 | Digger AL52
| SM-D |  |  |  | 0 | 0 | 2650 | 1875 | 4775 | 2375 | 3925 | 0 | 0 | 2225 | 0 | 0 | 0 | 0 | 1450 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5250 | 6800 | 0 | 0 | 0 | 0 |  | 31325
| Unit | 0 |  | 0
| 0 | [34 empty] | 0
| Unit | 0 |  | 0
| SM-D | [34 empty] | 0
Total |  |  |  |  | 0 | 0 | 2650 | 1875 | 4775 | 2375 | 3925 | 0 | 0 | 2225 | 0 | 0 | 0 | 0 | 1450 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8250 | 9050 | 1750 | 2685 | 975 | 2008 | 0 | 43993
2021-04-01
Class | Pit | Volume |  |  | 2021-04-01 | 2021-04-02 | 2021-04-03 | 2021-04-04 | 2021-04-05 | 2021-04-06 | 2021-04-07 | 2021-04-08 | 2021-04-09 | 2021-04-10 | 2021-04-11 | 2021-04-12 | 2021-04-13 | 2021-04-14 | 2021-04-15 | 2021-04-16 | 2021-04-17 | 2021-04-18 | 2021-04-19 | 2021-04-20 | 2021-04-21 | 2021-04-22 | 2021-04-23 | 2021-04-24 | 2021-04-25 | 2021-04-26 | 2021-04-27 | 2021-04-28 | 2021-04-29 | 2021-04-30 | 2021-05-01 | Total
Roto / SM |  | Vol. Target | Monthly Plan Vol. | Remain
| Unit | 887332 | 75000 | 788715 | Dragflow | Dragflow | Dragflow | Dragflow | Dragflow | Dragflow | Dragflow | Dragflow | Dragflow | Dragflow | Dragflow | Dragflow | Dragflow | Dragflow | Dragflow | Dragflow | Dragflow | Dragflow | Dragflow | Dragflow | Dragflow | Dragflow | Dragflow | Dragflow | Dragflow | Dragflow | Dragflow | Dragflow | Dragflow | Dragflow
| SM-B |  |  |  | 0 | 0 | 2917 | 4167 | 2811 | 1225 | 2145 | 0 | 0 | 621 | 2585 | 2605 | 4115 | 3546 | 6090 | 6423 | 6377 | 5104 | 4845 | 5457 | 0 | 0 | 2242 | 6440 | 5509 | 5406 | 6703 | 0 | 5461 | 5823 |  | 98617
| Unit | 968548 | 116666.6667 | 927523 | Digger AL52 | Digger AL52 | Digger AL52 | Digger AL52 | Digger AL52 | Digger AL52 | Digger AL52 | Digger AL52 | Digger AL52 | Digger AL52 | Digger AL52 | Digger AL52 | Digger AL52 | Digger AL52 | Digger AL52 | Digger AL52 | Digger AL52 | Digger AL52 | Digger AL52 | Digger AL52 | Digger AL52 | Digger AL52 | Digger AL52 | Digger AL52 | Digger AL52 | Digger AL52 | Digger AL52 | Digger AL52 | Digger AL52 | Digger AL52
| SM-D |  |  |  | 0 | 0 | 0 | 0 | 3175 | 2775 | 1750 | 0 | 0 | 0 | 2675 | 0 | 0 | 1925 | 0 | 0 | 0 | 2825 | 9350 | 3300 | 4575 | 0 | 0 | 0 | 1900 | 2250 | 2675 | 1850 | 0 | 0 |  | 41025
| Unit | 0 | 100000 | 0
| 0 | [34 empty] | 0
| Unit | 0 |  | 0
| SM-D | [34 empty] | 0
Total |  |  |  |  | 0 | 0 | 2917 | 4167 | 2811 | 1225 | 2145 | 0 | 0 | 621 | 2585 | 2605 | 4115 | 3546 | 6090 | 6423 | 6377 | 5104 | 4845 | 5457 | 0 | 0 | 2242 | 6440 | 5509 | 5406 | 6703 | 0 | 5461 | 5823 | 0 | 98617
2021-05-01
Class | Pit | Volume |  |  | 2021-05-01 | 2021-05-02 | 2021-05-03 | 2021-05-04 | 2021-05-05 | 2021-05-06 | 2021-05-07 | 2021-05-08 | 2021-05-09 | 2021-05-10 | 2021-05-11 | 2021-05-12 | 2021-05-13 | 2021-05-14 | 2021-05-15 | 2021-05-16 | 2021-05-17 | 2021-05-18 | 2021-05-19 | 2021-05-20 | 2021-05-21 | 2021-05-22 | 2021-05-23 | 2021-05-24 | 2021-05-25 | 2021-05-26 | 2021-05-27 | 2021-05-28 | 2021-05-29 | 2021-05-30 | 2021-05-31 | Total
Roto / SM |  | Vol. Target | Monthly Plan Vol. | Remain
| Unit | 788715 | 75000 | 767512 | 2021-05-01: Dragflow; 2021-05-02: Dragflow; 2021-05-03: Dragflow; 2021-05-04: Dragflow
| SM-B |  |  |  | 2021-05-01: 6419; 2021-05-02: 5445; 2021-05-03: 5461; 2021-05-04: 3878 | 21203
| Unit | 927523 | 116666.6667 | 827173 | Digger AL52 | Digger AL52 | Digger AL52 | Digger AL52 | Digger AL52 | Digger AL52 | Digger AL52 | Digger AL52 | Digger AL52 | Digger AL52 | Digger AL52 | Digger AL52 | Digger AL52 | Digger AL52 | Digger AL52 | Digger AL52 | Digger AL52 | Digger AL52 | Digger AL52 | Digger AL52 | Digger AL52 | Digger AL52 | Digger AL52
| SM-D |  |  |  | 6025 | 4000 | 3200 | 2000 | 950 | 3875 | 7525 | 7075 | 4075 | 8150 | 1600 | 5775 | 10175 | 13250 | 0 | 0 | 0 | 2300 | 9725 | 4725 | 0 | 1875 | 4050 | [8 empty] | 100350
| Unit | 0 |  | 0
| 0 | [34 empty] | 0
| Unit | 0 |  | 0
| SM-D | [34 empty] | 0
Total |  |  |  |  | 12444 | 9445 | 8661 | 5878 | 950 | 3875 | 7525 | 7075 | 4075 | 8150 | 1600 | 5775 | 10175 | 13250 | 0 | 0 | 0 | 2300 | 9725 | 4725 | 0 | 1875 | 4050 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 121553
2021-06-01
Class | Pit | Volume |  |  | 2021-06-01 | 2021-06-02 | 2021-06-03 | 2021-06-04 | 2021-06-05 | 2021-06-06 | 2021-06-07 | 2021-06-08 | 2021-06-09 | 2021-06-10 | 2021-06-11 | 2021-06-12 | 2021-06-13 | 2021-06-14 | 2021-06-15 | 2021-06-16 | 2021-06-17 | 2021-06-18 | 2021-06-19 | 2021-06-20 | 2021-06-21 | 2021-06-22 | 2021-06-23 | 2021-06-24 | 2021-06-25 | 2021-06-26 | 2021-06-27 | 2021-06-28 | 2021-06-29 | 2021-06-30 | 2021-07-01 | Total
Roto / SM |  | Vol. Target | Monthly Plan Vol. | Remain
| Unit | 767512 | 75000 | 767512
| SM-B | [34 empty] | 0
| Unit | 827173 | 85714.2857 | 827173
| SM-D | [34 empty] | 0
| Unit | 0 |  | 0
| 0 | [34 empty] | 0
| Unit | 0 |  | 0
| SM-D | [34 empty] | 0
Total |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2021-07-01
Class | Pit | Volume |  |  | 2021-07-01 | 2021-07-02 | 2021-07-03 | 2021-07-04 | 2021-07-05 | 2021-07-06 | 2021-07-07 | 2021-07-08 | 2021-07-09 | 2021-07-10 | 2021-07-11 | 2021-07-12 | 2021-07-13 | 2021-07-14 | 2021-07-15 | 2021-07-16 | 2021-07-17 | 2021-07-18 | 2021-07-19 | 2021-07-20 | 2021-07-21 | 2021-07-22 | 2021-07-23 | 2021-07-24 | 2021-07-25 | 2021-07-26 | 2021-07-27 | 2021-07-28 | 2021-07-29 | 2021-07-30 | 2021-07-31 | Total
Roto / SM |  | Vol. Target | Monthly Plan Vol. | Remain
| Unit | 767512 | 75000 | 767512
| SM-B | [34 empty] | 0
| Unit | 827173 | 85714.2857 | 827173
| SM-D | [34 empty] | 0
| Unit | 0 |  | 0
| 0 | [34 empty] | 0
| Unit | 0 |  | 0
| SM-D | [34 empty] | 0
Total |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2021-08-01
Class | Pit | Volume |  |  | 2021-08-01 | 2021-08-02 | 2021-08-03 | 2021-08-04 | 2021-08-05 | 2021-08-06 | 2021-08-07 | 2021-08-08 | 2021-08-09 | 2021-08-10 | 2021-08-11 | 2021-08-12 | 2021-08-13 | 2021-08-14 | 2021-08-15 | 2021-08-16 | 2021-08-17 | 2021-08-18 | 2021-08-19 | 2021-08-20 | 2021-08-21 | 2021-08-22 | 2021-08-23 | 2021-08-24 | 2021-08-25 | 2021-08-26 | 2021-08-27 | 2021-08-28 | 2021-08-29 | 2021-08-30 | 2021-08-31 | Total
Roto / SM |  | Vol. Target | Monthly Plan Vol. | Remain
| Unit | 767512 | 75000 | 767512
| SM-B | [34 empty] | 0
| Unit | 827173 | 85714.2857 | 827173
| SM-D | [34 empty] | 0
| Unit | 0 |  | 0
| 0 | [34 empty] | 0
| Unit | 0 |  | 0
| SM-D | [34 empty] | 0
Total |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2021-09-01
Class | Pit | Volume |  |  | 2021-09-01 | 2021-09-02 | 2021-09-03 | 2021-09-04 | 2021-09-05 | 2021-09-06 | 2021-09-07 | 2021-09-08 | 2021-09-09 | 2021-09-10 | 2021-09-11 | 2021-09-12 | 2021-09-13 | 2021-09-14 | 2021-09-15 | 2021-09-16 | 2021-09-17 | 2021-09-18 | 2021-09-19 | 2021-09-20 | 2021-09-21 | 2021-09-22 | 2021-09-23 | 2021-09-24 | 2021-09-25 | 2021-09-26 | 2021-09-27 | 2021-09-28 | 2021-09-29 | 2021-09-30 | 2021-10-01 | Total
Roto / SM |  | Vol. Target | Monthly Plan Vol. | Remain
| Unit | 767512 | 75000 | 767512
| SM-B | [34 empty] | 0
| Unit | 827173 | 85714.2857 | 827173
| SM-D | [34 empty] | 0
| Unit | 0 |  | 0
| 0 | [34 empty] | 0
| Unit | 0 |  | 0
| SM-D | [34 empty] | 0
Total |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2021-10-01
Class | Pit | Volume |  |  | 2021-10-01 | 2021-10-02 | 2021-10-03 | 2021-10-04 | 2021-10-05 | 2021-10-06 | 2021-10-07 | 2021-10-08 | 2021-10-09 | 2021-10-10 | 2021-10-11 | 2021-10-12 | 2021-10-13 | 2021-10-14 | 2021-10-15 | 2021-10-16 | 2021-10-17 | 2021-10-18 | 2021-10-19 | 2021-10-20 | 2021-10-21 | 2021-10-22 | 2021-10-23 | 2021-10-24 | 2021-10-25 | 2021-10-26 | 2021-10-27 | 2021-10-28 | 2021-10-29 | 2021-10-30 | 2021-10-31 | Total
Roto / SM |  | Vol. Target | Monthly Plan Vol. | Remain
| Unit | 767512 | 75000 | 767512
| SM-B | [34 empty] | 0
| Unit | 827173 | 85714.2857 | 827173
| SM-D | [34 empty] | 0
| Unit | 0 |  | 0
| 0 | [34 empty] | 0
| Unit | 0 |  | 0
| SM-D | [34 empty] | 0
Total |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2021-11-01
Class | Pit | Volume |  |  | 2021-11-01 | 2021-11-02 | 2021-11-03 | 2021-11-04 | 2021-11-05 | 2021-11-06 | 2021-11-07 | 2021-11-08 | 2021-11-09 | 2021-11-10 | 2021-11-11 | 2021-11-12 | 2021-11-13 | 2021-11-14 | 2021-11-15 | 2021-11-16 | 2021-11-17 | 2021-11-18 | 2021-11-19 | 2021-11-20 | 2021-11-21 | 2021-11-22 | 2021-11-23 | 2021-11-24 | 2021-11-25 | 2021-11-26 | 2021-11-27 | 2021-11-28 | 2021-11-29 | 2021-11-30 | 2021-12-01 | Total
Roto / SM |  | Vol. Target | Monthly Plan Vol. | Remain
| Unit | 767512 | 75000 | 767512
| SM-B | [34 empty] | 0
| Unit | 827173 | 160714.2857 | 827173
| SM-D | [34 empty] | 0
| Unit | 0 |  | 0
| 0 | [34 empty] | 0
| Unit | 0 |  | 0
| SM-D | [34 empty] | 0
Total |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2021-12-01
Class | Pit | Volume |  |  | 2021-12-01 | 2021-12-02 | 2021-12-03 | 2021-12-04 | 2021-12-05 | 2021-12-06 | 2021-12-07 | 2021-12-08 | 2021-12-09 | 2021-12-10 | 2021-12-11 | 2021-12-12 | 2021-12-13 | 2021-12-14 | 2021-12-15 | 2021-12-16 | 2021-12-17 | 2021-12-18 | 2021-12-19 | 2021-12-20 | 2021-12-21 | 2021-12-22 | 2021-12-23 | 2021-12-24 | 2021-12-25 | 2021-12-26 | 2021-12-27 | 2021-12-28 | 2021-12-29 | 2021-12-30 | 2021-12-31 | Total
Roto / SM |  | Vol. Target | Monthly Plan Vol. | Remain
| Unit | 767512 | 75000 | 767512
| SM-B | [34 empty] | 0
| Unit | 827173 | 160714.2857 | 827173
| SM-D | [34 empty] | 0
| Unit | 0 |  | 0
| 0 | [34 empty] | 0
| Unit | 0 |  | 0
| SM-D | [34 empty] | 0
Total |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## Sims
■ Hasil Loading Lumpur
2021-01-01
Class | Pit | Volume |  |  | 2021-01-01 | 2021-01-02 | 2021-01-03 | 2021-01-04 | 2021-01-05 | 2021-01-06 | 2021-01-07 | 2021-01-08 | 2021-01-09 | 2021-01-10 | 2021-01-11 | 2021-01-12 | 2021-01-13 | 2021-01-14 | 2021-01-15 | 2021-01-16 | 2021-01-17 | 2021-01-18 | 2021-01-19 | 2021-01-20 | 2021-01-21 | 2021-01-22 | 2021-01-23 | 2021-01-24 | 2021-01-25 | 2021-01-26 | 2021-01-27 | 2021-01-28 | 2021-01-29 | 2021-01-30 | 2021-01-31 | Total
SM-A |  | Vol. Target | Monthly Plan Vol. | Remain
| Unit | 280000 |  | 147003.0456 | Dragflow | Dragflow | Dragflow | Dragflow | Dragflow | Dragflow | Dragflow | Dragflow | Dragflow | Dragflow | Dragflow | Dragflow | Dragflow | Dragflow | Dragflow | Dragflow | Dragflow | Dragflow | Dragflow | Dragflow | Dragflow | Dragflow | Dragflow | Dragflow | Dragflow | Dragflow | Dragflow | Dragflow | Dragflow | Dragflow | Dragflow
| SM A1 |  |  |  | 3782.8 | 4590 | 5088 | 4896 | 5243.2 | 624 | 1670.4 | 4756 | 5266.4 | 4970.2941 | 5217.8824 | 5378.8235 | 5242.5 | 5421.1765 | 4844.8235 | 5357.6471 | 5069.6471 | 5378.8235 | 4780.5882 | 5442.3529 | 4867.6765 | 4730.5588 | 2230.9412 | 0 | 4848.8824 | 5306.2941 | 5127.5294 | 6014.1176 | 3727.0588 | 1744.9412 | 1377.5956 | 132996.9544
| Unit | 880000 |  | 840899.6633 | [7 empty] | EX 2701 | EX 2701 | EX 2701 | EX 2701 | EX 2701 | EX 2701 | EX 2701 | EX 2701 | EX 2701 | EX 2702 | EX 2702 | EX 2702 | EX 2702 | EX 2702 | EX 2702 | EX 2702 | EX 2702 | EX 2702 | EX 2702 | EX2701,EX2702 | EX2701,EX2702 | EX2701,EX2702 | EX2701,EX2702 | EX2701,EX2702
| SM A3 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1041.5 | 784.4167 | 604.3333 | 1061.5833 | 1801.1667 | 1578 | 2596.0833 | 2350.25 | 2770.9167 | 2044.1667 | 2586.5 | 1984.75 | 2300.5 | 495.25 | 123.5833 | 2714.8333 | 1116.9167 | 2549.33 | 2387.92 | 1289.92 | 1225.25 | 914.9167 | 1049.25 | 1729 | 39100.3367
| Unit | 150000 |  | 150000
| SM B2 | [34 empty] | 0
Total |  |  |  |  | 3782.8 | 4590 | 5088 | 4896 | 5243.2 | 624 | 1670.4 | 5797.5 | 6050.8167 | 5574.6275 | 6279.4657 | 7179.9902 | 6820.5 | 8017.2598 | 7195.0735 | 8128.5637 | 7113.8137 | 7965.3235 | 6765.3382 | 7742.8529 | 5362.9265 | 4854.1422 | 4945.7745 | 1116.9167 | 7398.2124 | 7694.2141 | 6417.4494 | 7239.3676 | 4641.9755 | 2794.1912 | 3106.5956 | 172097.2911
2021-02-01
Class | Pit | Volume |  |  | 2021-02-01 | 2021-02-02 | 2021-02-03 | 2021-02-04 | 2021-02-05 | 2021-02-06 | 2021-02-07 | 2021-02-08 | 2021-02-09 | 2021-02-10 | 2021-02-11 | 2021-02-12 | 2021-02-13 | 2021-02-14 | 2021-02-15 | 2021-02-16 | 2021-02-17 | 2021-02-18 | 2021-02-19 | 2021-02-20 | 2021-02-21 | 2021-02-22 | 2021-02-23 | 2021-02-24 | 2021-02-25 | 2021-02-26 | 2021-02-27 | 2021-02-28 |  |  |  | Total
SM-A |  | Vol. Target | Monthly Plan Vol. | Remain
| Unit | 147003.0456 |  | 129594.7956 | 2021-02-01: Dragflow; 2021-02-02: Dragflow; 2021-02-03: Dragflow; 2021-02-04: Dragflow; 2021-02-05: Dragflow; 2021-02-06: Dragflow; 2021-02-07: Dragflow; 2021-02-08: Dragflow; 2021-02-09: Dragflow; 2021-02-10: Dragflow; 2021-02-11: Dragflow
| SM A1 |  |  |  | 2021-02-01: 2436.1765; 2021-02-02: 1600.8088; 2021-02-03: 1803.3088; 2021-02-04: 1240.8088; 2021-02-05: 1355.2941; 2021-02-06: 1356.1544; 2021-02-07: 1535.625; 2021-02-08: 1679.6912; 2021-02-09: 1599.7059; 2021-02-10: 2557.9412; 2021-02-11: 242.7353 |  |  |  | 17408.25
| Unit | 840899.6633 |  | 763481.8202 | EX 2701 | EX 2702 | EX 2702 | EX 2702 | EX 2702 | EX 2702 | EX 2702 | EX 2702 | EX 2702 | EX 2702 x Dragflow | EX 2702 x Dragflow |  |  |  |  | EX 2702 | EX 2702 x Dragflow | EX 2702 x Dragflow | EX 2702 x Dragflow | EX 2702 | EX 2702 | EX 2702 x Dragflow | EX 2702 x Dragflow | EX 2702 x Dragflow | EX 2702 x Dragflow | EX 2702 x Dragflow | EX 2702 x Dragflow | EX 278
| SM A3 |  |  |  | 1707.33 | 933.0833 | 1026.83 | 1774.42 | 1575.33 | 2178.75 | 2124 | 2075.5 | 1155.4167 | 3587.8284 | 3640.7206 | 0 | 0 | 0 | 0 | 2875.17 | 4227.5882 | 4328.1373 | 4355.598 | 3071.5 | 2113.8333 | 4534.9853 | 7079.8578 | 7027.7696 | 6806.348 | 3706.6241 | 3331.3024 | 2179.92 |  |  |  | 77417.8431
| Unit | 150000 |  | 150000
| SM B2 | [34 empty] | 0
Total |  |  |  |  | 4143.5065 | 2533.8922 | 2830.1388 | 3015.2288 | 2930.6241 | 3534.9044 | 3659.625 | 3755.1912 | 2755.1225 | 6145.7696 | 3883.4559 | 0 | 0 | 0 | 0 | 2875.17 | 4227.5882 | 4328.1373 | 4355.598 | 3071.5 | 2113.8333 | 4534.9853 | 7079.8578 | 7027.7696 | 6806.348 | 3706.6241 | 3331.3024 | 2179.92 | 0 | 0 | 0 | 94826.0931
2021-03-01
Class | Pit | Volume |  |  | 2021-03-01 | 2021-03-02 | 2021-03-03 | 2021-03-04 | 2021-03-05 | 2021-03-06 | 2021-03-07 | 2021-03-08 | 2021-03-09 | 2021-03-10 | 2021-03-11 | 2021-03-12 | 2021-03-13 | 2021-03-14 | 2021-03-15 | 2021-03-16 | 2021-03-17 | 2021-03-18 | 2021-03-19 | 2021-03-20 | 2021-03-21 | 2021-03-22 | 2021-03-23 | 2021-03-24 | 2021-03-25 | 2021-03-26 | 2021-03-27 | 2021-03-28 | 2021-03-29 | 2021-03-30 | 2021-03-31 | Total
SM-A |  | Vol. Target | Monthly Plan Vol. | Remain
| Unit | 129594.7956 | 100000 | 27796.9076 | [8 empty] | Dragflow | Dragflow | Dragflow | Dragflow | Dragflow | Dragflow |  | 2 X Dragflow | 2 X Dragflow | 2 X Dragflow | 2 X Dragflow | 2 X Dragflow | 2 X Dragflow | Dragflow | Dragflow | Dragflow | 2 X Dragflow | 2 X Dragflow | 2 X Dragflow | 2 X Dragflow | 1 X Dragflow + EX 2702 |  | 1 x Dragflow
| SM A1 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1676.4706 | 2625 | 2845.5882 | 2426.4706 | 5292.0882 | 1290.5294 | 0 | 1331.2059 | 2940.1765 | 5721.9706 | 8444.5588 | 7359.3529 | 1927.9412 | 1344 | 1128.4412 | 2768.4706 | 6331.7647 | 10179.8603 | 8023.6765 | 9228.4412 | 8114.4624 | 5778.5947 | 5018.8235 | 101797.8879
| Unit | 763481.8202 |  | 713594.9602 | EX 278 | EX 278 | EX 278 | EX 278 | EX 278 & EX 2702 | EX 2702 | EX 2702 | EX 278 & EX 2702 | EX 278 & EX 2702 | EX 278 & EX 2702 | EX 278 |  | EX 278 |  | EX 278 |  | EX 276 | EX 276 |  |  | EX 276 | EX 276 | EX 276 | EX 276 | EX 276
| SM A3 |  |  |  | 4318.67 | 4183.92 | 3847.92 | 2731.67 | 3169.09 | 3080.08 | 4755.75 | 1490.25 | 2981.58 | 360.84 | 2605.42 | 0 | 2008.75 | 0 | 1266.25 | 0 | 1558.25 | 1592.17 | 0 | 0 | 2884.75 | 1777.17 | 2521 | 2018.33 | 735 | 0 | 0 | 0 | 0 | 0 | 0 | 49886.86
| Unit | 150000 |  | 150000
| SM B2 | [34 empty] | 0
Total |  |  |  |  | 4318.67 | 4183.92 | 3847.92 | 2731.67 | 3169.09 | 3080.08 | 4755.75 | 1490.25 | 4658.0506 | 2985.84 | 5451.0082 | 2426.4706 | 7300.8382 | 1290.5294 | 1266.25 | 1331.2059 | 4498.4265 | 7314.1406 | 8444.5588 | 7359.3529 | 4812.6912 | 3121.17 | 3649.4412 | 4786.8006 | 7066.7647 | 10179.8603 | 8023.6765 | 9228.4412 | 8114.4624 | 5778.5947 | 5018.8235 | 151684.7479
2021-04-01
Class | Pit | Volume |  |  | 2021-04-01 | 2021-04-02 | 2021-04-03 | 2021-04-04 | 2021-04-05 | 2021-04-06 | 2021-04-07 | 2021-04-08 | 2021-04-09 | 2021-04-10 | 2021-04-11 | 2021-04-12 | 2021-04-13 | 2021-04-14 | 2021-04-15 | 2021-04-16 | 2021-04-17 | 2021-04-18 | 2021-04-19 | 2021-04-20 | 2021-04-21 | 2021-04-22 | 2021-04-23 | 2021-04-24 | 2021-04-25 | 2021-04-26 | 2021-04-27 | 2021-04-28 | 2021-04-29 | 2021-04-30 | 2021-05-01 | Total
SM-A |  | Vol. Target | Monthly Plan Vol. | Remain
| Unit | 27796.9076 |  | -11233.5859 | 2021-04-01: Dragflow; 2021-04-02: Dragflow; 2021-04-03: Dragflow; 2021-04-04: Dragflow; 2021-04-05: 1 x Dragflow + EX 276; 2021-04-06: Dragflow; 2021-04-07: Dragflow; 2021-04-08: Dragflow; 2021-04-09: Dragflow
| SM A1 |  |  |  | 2021-04-01: 1982.1176; 2021-04-02: 5844.7059; 2021-04-03: 4810.5882; 2021-04-04: 4634.5588; 2021-04-05: 5099.9641; 2021-04-06: 3377.6471; 2021-04-07: 7643.3824; 2021-04-08: 4066.2353; 2021-04-09: 1571.2941 | 39030.4935
| Unit | 713594.9602 |  | 713594.9602
| SM A3 | [34 empty] | 0
| Unit | 150000 |  | 150000
| SM B2 | [34 empty] | 0
Total |  |  |  |  | 1982.1176 | 5844.7059 | 4810.5882 | 4634.5588 | 5099.9641 | 3377.6471 | 7643.3824 | 4066.2353 | 1571.2941 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 39030.4935
2021-05-01
Class | Pit | Volume |  |  | 2021-05-01 | 2021-05-02 | 2021-05-03 | 2021-05-04 | 2021-05-05 | 2021-05-06 | 2021-05-07 | 2021-05-08 | 2021-05-09 | 2021-05-10 | 2021-05-11 | 2021-05-12 | 2021-05-13 | 2021-05-14 | 2021-05-15 | 2021-05-16 | 2021-05-17 | 2021-05-18 | 2021-05-19 | 2021-05-20 | 2021-05-21 | 2021-05-22 | 2021-05-23 | 2021-05-24 | 2021-05-25 | 2021-05-26 | 2021-05-27 | 2021-05-28 | 2021-05-29 | 2021-05-30 | 2021-05-31 | Total
SM-A |  | Vol. Target | Monthly Plan Vol. | Remain
| Unit | -11233.5859 |  | -100378.9388 | 2021-05-14: Dragflow; 2021-05-15: Dragflow; 2021-05-16: 2 X Dragflow; 2021-05-17: 2 X Dragflow; 2021-05-18: 2 X Dragflow; 2021-05-19: 2 X Dragflow; 2021-05-20: Dragflow; 2021-05-21: Dragflow; 2021-05-22: Dragflow; 2021-05-23: Dragflow; 2021-05-24: Dragflow; 2021-05-25: 2 X Dragflow; 2021-05-26: 2 X Dragflow
| SM A1 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2878.6765 | 4600.5882 | 6475.0588 | 12134.4706 | 9542.9118 | 4830 | 4499.6471 | 5536.4118 | 5355 | 3879.5294 | 4691.0294 | 7292.2941 | 10597.7647 | 6831.9706 |  |  |  | 0 | 89145.3529
| Unit | 713594.9602 |  | 713594.9602
| SM A3 | [34 empty] | 0
| Unit | 150000 |  | 150000
| SM B2 | [34 empty] | 0
Total |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2878.6765 | 4600.5882 | 6475.0588 | 12134.4706 | 9542.9118 | 4830 | 4499.6471 | 5536.4118 | 5355 | 3879.5294 | 4691.0294 | 7292.2941 | 10597.7647 | 6831.9706 | 0 | 0 | 0 | 0 | 89145.3529
2021-06-01
Class | Pit | Volume |  |  | 2021-06-01 | 2021-06-02 | 2021-06-03 | 2021-06-04 | 2021-06-05 | 2021-06-06 | 2021-06-07 | 2021-06-08 | 2021-06-09 | 2021-06-10 | 2021-06-11 | 2021-06-12 | 2021-06-13 | 2021-06-14 | 2021-06-15 | 2021-06-16 | 2021-06-17 | 2021-06-18 | 2021-06-19 | 2021-06-20 | 2021-06-21 | 2021-06-22 | 2021-06-23 | 2021-06-24 | 2021-06-25 | 2021-06-26 | 2021-06-27 | 2021-06-28 | 2021-06-29 | 2021-06-30 | 2021-07-01 | Total
SM-A |  | Vol. Target | Monthly Plan Vol. | Remain
| Unit | -100378.9388 |  | -100378.9388
| SM A1 | [34 empty] | 0
| Unit | 713594.9602 |  | 713594.9602
| SM A3 | [34 empty] | 0
| Unit | 150000 | 50000 | 150000
| SM B2 | [34 empty] | 0
Total |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2021-07-01
Class | Pit | Volume |  |  | 2021-07-01 | 2021-07-02 | 2021-07-03 | 2021-07-04 | 2021-07-05 | 2021-07-06 | 2021-07-07 | 2021-07-08 | 2021-07-09 | 2021-07-10 | 2021-07-11 | 2021-07-12 | 2021-07-13 | 2021-07-14 | 2021-07-15 | 2021-07-16 | 2021-07-17 | 2021-07-18 | 2021-07-19 | 2021-07-20 | 2021-07-21 | 2021-07-22 | 2021-07-23 | 2021-07-24 | 2021-07-25 | 2021-07-26 | 2021-07-27 | 2021-07-28 | 2021-07-29 | 2021-07-30 | 2021-07-31 | Total
SM-A |  | Vol. Target | Monthly Plan Vol. | Remain
| Unit | -100378.9388 |  | -100378.9388
| SM A1 | [34 empty] | 0
| Unit | 713594.9602 |  | 713594.9602
| SM A3 | [34 empty] | 0
| Unit | 150000 | 100000 | 150000
| SM B2 | [34 empty] | 0
Total |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2021-08-01
Class | Pit | Volume |  |  | 2021-08-01 | 2021-08-02 | 2021-08-03 | 2021-08-04 | 2021-08-05 | 2021-08-06 | 2021-08-07 | 2021-08-08 | 2021-08-09 | 2021-08-10 | 2021-08-11 | 2021-08-12 | 2021-08-13 | 2021-08-14 | 2021-08-15 | 2021-08-16 | 2021-08-17 | 2021-08-18 | 2021-08-19 | 2021-08-20 | 2021-08-21 | 2021-08-22 | 2021-08-23 | 2021-08-24 | 2021-08-25 | 2021-08-26 | 2021-08-27 | 2021-08-28 | 2021-08-29 | 2021-08-30 | 2021-08-31 | Total
SM-A |  | Vol. Target | Monthly Plan Vol. | Remain
| Unit | -100378.9388 |  | -100378.9388
| SM A1 | [34 empty] | 0
| Unit | 713594.9602 | 100000 | 713594.9602
| SM A3 | [34 empty] | 0
| Unit | 150000 | 100000 | 150000
| SM B2 | [34 empty] | 0
Total |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2021-09-01
Class | Pit | Volume |  |  | 2021-09-01 | 2021-09-02 | 2021-09-03 | 2021-09-04 | 2021-09-05 | 2021-09-06 | 2021-09-07 | 2021-09-08 | 2021-09-09 | 2021-09-10 | 2021-09-11 | 2021-09-12 | 2021-09-13 | 2021-09-14 | 2021-09-15 | 2021-09-16 | 2021-09-17 | 2021-09-18 | 2021-09-19 | 2021-09-20 | 2021-09-21 | 2021-09-22 | 2021-09-23 | 2021-09-24 | 2021-09-25 | 2021-09-26 | 2021-09-27 | 2021-09-28 | 2021-09-29 | 2021-09-30 | 2021-10-01 | Total
SM-A |  | Vol. Target | Monthly Plan Vol. | Remain
| Unit | -100378.9388 |  | -100378.9388
| SM A1 | [34 empty] | 0
| Unit | 50000 |  | 50000
| SM AW | [34 empty] | 0
| Unit | 713594.9602 | 100000 | 713594.9602
| SM A3 | [34 empty] | 0
| Unit | 150000 | 100000 | 150000
| SM B2 | [34 empty] | 0
Total |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2021-10-01
Class | Pit | Volume |  |  | 2021-10-01 | 2021-10-02 | 2021-10-03 | 2021-10-04 | 2021-10-05 | 2021-10-06 | 2021-10-07 | 2021-10-08 | 2021-10-09 | 2021-10-10 | 2021-10-11 | 2021-10-12 | 2021-10-13 | 2021-10-14 | 2021-10-15 | 2021-10-16 | 2021-10-17 | 2021-10-18 | 2021-10-19 | 2021-10-20 | 2021-10-21 | 2021-10-22 | 2021-10-23 | 2021-10-24 | 2021-10-25 | 2021-10-26 | 2021-10-27 | 2021-10-28 | 2021-10-29 | 2021-10-30 | 2021-10-31 | Total
SM-A |  | Vol. Target | Monthly Plan Vol. | Remain
| Unit | -100378.9388 |  | -100378.9388
| SM A1 | [34 empty] | 0
| Unit |  |  | 0
| SM AW | [34 empty] | 0
| Unit | 713594.9602 | 100000 | 713594.9602
| SM A3 | [34 empty] | 0
| Unit | 150000 | 100000 | 150000
| SM B2 | [34 empty] | 0
Total |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2021-11-01
Class | Pit | Volume |  |  | 2021-11-01 | 2021-11-02 | 2021-11-03 | 2021-11-04 | 2021-11-05 | 2021-11-06 | 2021-11-07 | 2021-11-08 | 2021-11-09 | 2021-11-10 | 2021-11-11 | 2021-11-12 | 2021-11-13 | 2021-11-14 | 2021-11-15 | 2021-11-16 | 2021-11-17 | 2021-11-18 | 2021-11-19 | 2021-11-20 | 2021-11-21 | 2021-11-22 | 2021-11-23 | 2021-11-24 | 2021-11-25 | 2021-11-26 | 2021-11-27 | 2021-11-28 | 2021-11-29 | 2021-11-30 | 2021-12-01 | Total
SM-A |  | Vol. Target | Monthly Plan Vol. | Remain
| Unit | -100378.9388 |  | -100378.9388
| SM A1 | [34 empty] | 0
| Unit | 0 |  | 0
| SM AW | [34 empty] | 0
| Unit | 713594.9602 |  | 713594.9602
| SM A3 | [34 empty] | 0
| Unit | 150000 | 100000 | 150000
| SM B2 | [34 empty] | 0
Total |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2021-12-01
Class | Pit | Volume |  |  | 2021-12-01 | 2021-12-02 | 2021-12-03 | 2021-12-04 | 2021-12-05 | 2021-12-06 | 2021-12-07 | 2021-12-08 | 2021-12-09 | 2021-12-10 | 2021-12-11 | 2021-12-12 | 2021-12-13 | 2021-12-14 | 2021-12-15 | 2021-12-16 | 2021-12-17 | 2021-12-18 | 2021-12-19 | 2021-12-20 | 2021-12-21 | 2021-12-22 | 2021-12-23 | 2021-12-24 | 2021-12-25 | 2021-12-26 | 2021-12-27 | 2021-12-28 | 2021-12-29 | 2021-12-30 | 2021-12-31 | Total
SM-A |  | Vol. Target | Monthly Plan Vol. | Remain
| Unit | -100378.9388 |  | -100378.9388
| SM A1 | [34 empty] | 0
| Unit | 0 |  | 0
| SM AW | [34 empty] | 0
| Unit | 713594.9602 |  | 713594.9602
| SM A3 | [34 empty] | 0
| Unit | 150000 | 100000 | 150000
| SM B2 | [34 empty] | 0
Total |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## Pama
■ Hasil Loading Lumpur
2021-01-01
Class | Pit | Volume |  |  | 2021-01-01 | 2021-01-02 | 2021-01-03 | 2021-01-04 | 2021-01-05 | 2021-01-06 | 2021-01-07 | 2021-01-08 | 2021-01-09 | 2021-01-10 | 2021-01-11 | 2021-01-12 | 2021-01-13 | 2021-01-14 | 2021-01-15 | 2021-01-16 | 2021-01-17 | 2021-01-18 | 2021-01-19 | 2021-01-20 | 2021-01-21 | 2021-01-22 | 2021-01-23 | 2021-01-24 | 2021-01-25 | 2021-01-26 | 2021-01-27 | 2021-01-28 | 2021-01-29 | 2021-01-30 | 2021-01-31 | Total
RTS |  | Vol. Target | Monthly Plan Vol. | Remain
| Unit | 681582 |  | 681582
| RTS-C3 West | [34 empty] | 0
| Unit | 56561 |  | -17453 |  |  |  |  | 1XPC2000 | 1XPC2000 | 1XPC2000 |  | 1XPC2000 |  |  |  |  | 1XPC2000 | 1XPC2000 | 1XPC2000 | 1XPC2000 |  |  | 1XPC2000 | 1XPC2000 | 1XPC2000 | 1XPC2000 | 1XPC2000 | 1XPC2000 | 1XPC2000 | 1XPC2000 | 1XPC2000 | 1XPC2000 | 1XPC2000 | 1XPC2000
| RTS-C3 East |  |  |  | 0 | 0 | 0 | 0 | 4580 | 3900 | 858 | 0 | 40 | 0 | 0 | 0 | 0 | 3158 | 4940 | 2518 | 1826 | 0 | 0 | 3940 | 3878 | 4880 | 4874 | 3366 | 5150 | 8752 | 4446 | 624 | 2004 | 3420 | 6860 | 74014
| Unit | 156371 |  | 41441 |  |  |  | 1XPC1250 | 1XPC1250 | 1XPC1250 | 1XPC1250 | 1XPC1250 | 1XPC1250 | 1XPC1250 | 1XPC1250 | 2XPC1250 | 2XPC1250 | 2XPC1250 | 2XPC1250 | 2XPC1250 | 2XPC1250 | 1XPC1250 | 1XPC1250 |  | 1XPC1250 | 1XPC1250 | 1XPC1250 | 1XPC1250 | 1XPC1250 | 1XPC1250 | 1XPC1250 | 1XPC1250 | 1XPC1250 | 1XPC1250 | 1XPC1250
| RTS-D1 |  |  |  | 0 | 0 | 0 | 496 | 5852 | 4864 | 6778 | 4226 | 2128 | 5396 | 4978 | 2052 | 8214 | 8802 | 6670 | 7524 | 2318 | 2356 | 304 | 1060 | 2330 | 5756 | 6620 | 2736 | 5092 | 5038 | 3934 | 4560 | 2318 | 628 | 1900 | 114930
| Unit | 1500000 |  | 1364839 | 1 LINE ARTAMA | 2 LINE ARTAMA | 2 LINE ARTAMA | 1 LINE ARTAMA | 1 LINE ARTAMA |  |  |  | 1 LINE ARTAMA | 1 LINE ARTAMA | 1 LINE ARTAMA |  | 2 LINE ARTAMA | 1 LINE ARTAMA |  |  | 2 LINE ARTAMA | 2 LINE ARTAMA | 2 LINE ARTAMA | 2 LINE ARTAMA | 2 LINE ARTAMA | 2 LINE ARTAMA |  | 2 LINE ARTAMA | 2 LINE ARTAMA | 2 LINE ARTAMA | 2 LINE ARTAMA | 2 LINE ARTAMA | 2 LINE ARTAMA | 1 LINE ARTAMA | 1 LINE ARTAMA
| RTS-D2 |  |  |  | 4910 | 982 | 1964 | 5892 | 491 | 0 | 0 | 0 | 1964 | 5892 | 1964 | 0 | 3582 | 9228 | 2209.5 | 1200 | 4419 | 13422 | 9110 | 10049.5 | 9052 | 10262 | 0 | 4470 | 11352 | 8281.2 | 1492.8 | 5653.2 | 1228.8 | 1260 | 4830 | 135161
| Unit | 334743 |  | 334743
| RTS-G | [34 empty] | 0
| Unit | 0 |  | 0
| RTN | [34 empty] | 0
| Unit | 1539016 |  | 1313180 | 1 LINE ARTAMA | 1 LINE ARTAMA | 1 LINE ARTAMA | 2xDragflow + 1 LINE ARTAMA | 2xDragflow + 1 LINE ARTAMA | 2xDragflow | 2xDragflow | 2xDragflow | xDragflow | 2xDragflow + 1 LINE ARTAMA | 2xDragflow + 1 LINE ARTAMA | 1 LINE ARTAMA | 1 LINE ARTAMA | 2xDragflow + 1 LINE ARTAMA | 2xDragflow + 1 LINE ARTAMA | 2xDragflow + 1 LINE ARTAMA | 2xDragflow + 1 LINE ARTAMA |  |  | 2xDragflow + 1 LINE ARTAMA | 2xDragflow + 1 LINE ARTAMA | 2xDragflow + 2 LINE ARTAMA | 2xDragflow + 2 LINE ARTAMA | 2xDragflow + 2 LINE ARTAMA | 2xDragflow + 2 LINE ARTAMA | 2xDragflow + 2 LINE ARTAMA | 1xDragflow + 2 LINE ARTAMA | 1xDragflow + 2 LINE ARTAMA | 1xDragflow + 2 LINE ARTAMA | 1xDragflow + 2 LINE ARTAMA | 2xDragflow + 2 LINE ARTAMA
| RTM |  |  |  | 5775 | 4800 | 6060 | 8648 | 6780 | 3572 | 4712 | 5814 | 1976 | 7247 | 7655 | 1925 | 6360 | 1710 | 7030 | 6118 | 1786 | 0 | 4980 | 970 | 7410 | 18724 | 18140 | 16430 | 14355 | 10598 | 9070 | 8688 | 9136 | 11226 | 8141 | 225836
| Unit | 397204 |  | 397204
| SM 6 | [34 empty] | 0
Total |  |  |  |  | 10685 | 5782 | 8024 | 15036 | 17703 | 12336 | 12348 | 10040 | 6108 | 18535 | 14597 | 3977 | 18156 | 22898 | 20849.5 | 17360 | 10349 | 15778 | 14394 | 16019.5 | 22670 | 39622 | 29634 | 27002 | 35949 | 32669.2 | 18942.8 | 19525.2 | 14686.8 | 16534 | 21731 | 549941
2021-02-01
Class | Pit | Volume |  |  | 2021-02-01 | 2021-02-02 | 2021-02-03 | 2021-02-04 | 2021-02-05 | 2021-02-06 | 2021-02-07 | 2021-02-08 | 2021-02-09 | 2021-02-10 | 2021-02-11 | 2021-02-12 | 2021-02-13 | 2021-02-14 | 2021-02-15 | 2021-02-16 | 2021-02-17 | 2021-02-18 | 2021-02-19 | 2021-02-20 | 2021-02-21 | 2021-02-22 | 2021-02-23 | 2021-02-24 | 2021-02-25 | 2021-02-26 | 2021-02-27 | 2021-02-28 | 2021-03-01 | 2021-03-02 | 2021-03-03 | Total
RTS |  | Vol. Target | Monthly Plan Vol. | Remain
| Unit | 681582 |  | 681582
| RTS-C3 West | [34 empty] | 0
| Unit | -17453 |  | -51971 | 2021-02-01: 1XPC2000; 2021-02-02: 1XPC2000; 2021-02-03: 1XPC2000; 2021-02-12: 1XPC2000; 2021-02-16: 1XPC2000; 2021-02-17: 1XPC2000; 2021-02-18: 1XPC2000; 2021-02-19: 1XPC2000; 2021-02-20: 1XPC2000; 2021-02-21: 1XPC2000; 2021-02-25: 1XPC2000; 2021-02-26: 1XPC2000; 2021-02-27: 3XPC2000; 2021-02-28: 3XPC2000
| RTS-C3 East |  |  |  | 6878 | 6064 | 540 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 0 | 0 | 0 | 2200 | 2080 | 960 | 1640 | 320 | 1120 | 0 | 0 | 0 | 1700 | 900 | 4540 | 5556 |  |  |  | 34518
| Unit | 41441 |  | -33989 | 1XPC1250 | 1XPC1250 | 1XPC1250 | 2XPC1250,1XPC2000 | 2XPC1250,1XPC2000 | 2XPC1250,1XPC2000 | 2XPC1250,1XPC2000 | 2XPC1250,1XPC2000 | 2XPC1250,1XPC2000 | 2XPC1250,1XPC2000 | 2XPC1250,1XPC2000 | 1XPC1250 | [5 empty] | 1XPC1250 | 1XPC1250 | 1XPC1250 | 1XPC1250 | 1XPC1250 | 1XPC1250 | 1XPC1250 | 1XPC1250 | 1XPC1250 | 1XPC1250 | 1XPC1250
| RTS-D1 |  |  |  | 1824 | 4180 | 3458 | 6574 | 9348 | 10336 | 12844 | 7638 | 5624 | 8816 | 4788 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 75430
| Unit | -17453 |  | -331310.1 | 1 LINE ARTAMA | 2 LINE ARTAMA | 2 LINE ARTAMA | 3 LINE ARTAMA | 2 LINE ARTAMA | 2 LINE ARTAMA | 2 LINE ARTAMA | 2 LINE ARTAMA | 2 LINE ARTAMA | 2 LINE ARTAMA | 2 LINE ARTAMA | 2 LINE ARTAMA | 2 LINE ARTAMA | 2 LINE ARTAMA | 2 LINE ARTAMA | 2 LINE ARTAMA | 2 LINE ARTAMA | 2 LINE ARTAMA | 2 LINE ARTAMA | 2 LINE ARTAMA | 2 LINE ARTAMA | 2 LINE ARTAMA | 2 LINE ARTAMA | 2 LINE ARTAMA | 2 LINE ARTAMA | 2 LINE ARTAMA | 2 LINE ARTAMA | 2 LINE ARTAMA
| RTS-D2 |  |  |  | 2100 | 5667.6 | 10576 | 15399 | 11175 | 8400 | 3500 | 4550 | 8400 | 3850 | 3500 | 13300 | 16180 | 14770 | 13060 | 13020 | 8260 | 15120 | 12868 | 12222.5 | 15540 | 13704 | 15871 | 18056 | 10960 | 14696 | 13356 | 15756 |  |  |  | 313857.1
| Unit | 41441 |  | 41441
| RTS-G | [34 empty] | 0
| Unit | 1364839 |  | 1364839
| RTN | [34 empty] | 0
| Unit | 0 |  | -234157.95 | 2 LINE ARTAMA + 2xDragflow | 1 LINE ARTAMA + 2xDragflow | 2 LINE ARTAMA + 2xDragflow | 2 LINE ARTAMA + 2xDragflow | 2 LINE ARTAMA + 2xDragflow | 2 LINE ARTAMA + 2xDragflow | 2 LINE ARTAMA + 2xDragflow | 2 LINE ARTAMA + 2xDragflow | 2 LINE ARTAMA + 2xDragflow | 2 LINE ARTAMA + 2xDragflow | 2 LINE ARTAMA + 2xDragflow | 2 LINE ARTAMA + 2xDragflow | 2 LINE ARTAMA + 1xDragflow | 2 LINE ARTAMA + 1xDragflow | 2 LINE ARTAMA + 1xDragflow | 2 LINE ARTAMA + 1xDragflow | 2 LINE ARTAMA + 1xDragflow | 2 LINE ARTAMA + 1xDragflow | 2 LINE ARTAMA + 1xDragflow | 2 LINE ARTAMA + 1xDragflow | 2 LINE ARTAMA + 1xDragflow | 2 LINE ARTAMA + 1xDragflow | 2 LINE ARTAMA + 2xDragflow | 2 LINE ARTAMA + 2xDragflow | 2 LINE ARTAMA + 2xDragflow | 2 LINE ARTAMA + 2xDragflow | 2 LINE ARTAMA + 1xDragflow | 2 LINE ARTAMA + 1xDragflow
| RTM |  |  |  | 6200 | 3742.2 | 5727.6 | 11720 | 13848 | 7068 | 7448 | 5718 | 10282.4 | 6300.4 | 4628.3 | 8164.8 | 6151.5 | 4258.8 | 4258.8 | 8471.6 | 7600.5 | 12307.2 | 14424.8 | 11651.2 | 12914.6 | 3002 | 17455.4 | 6237 | 7447.3 | 6741.35 | 11307.2 | 9081 |  |  |  | 234157.95
| Unit | 397204 |  | 397204
| SM 6 | [34 empty] | 0
Total |  |  |  |  | 17002 | 19653.8 | 20301.6 | 33693 | 34371 | 25804 | 23792 | 17906 | 24306.4 | 18966.4 | 12916.3 | 21484.8 | 22331.5 | 19028.8 | 17318.8 | 23691.6 | 17940.5 | 28387.2 | 28932.8 | 24193.7 | 29574.6 | 16706 | 33326.4 | 24293 | 20107.3 | 22337.35 | 29203.2 | 30393 | 0 | 0 | 0 | 657963.05
2021-03-01
Class | Pit | Volume |  |  | 2021-03-01 | 2021-03-02 | 2021-03-03 | 2021-03-04 | 2021-03-05 | 2021-03-06 | 2021-03-07 | 2021-03-08 | 2021-03-09 | 2021-03-10 | 2021-03-11 | 2021-03-12 | 2021-03-13 | 2021-03-14 | 2021-03-15 | 2021-03-16 | 2021-03-17 | 2021-03-18 | 2021-03-19 | 2021-03-20 | 2021-03-21 | 2021-03-22 | 2021-03-23 | 2021-03-24 | 2021-03-25 | 2021-03-26 | 2021-03-27 | 2021-03-28 | 2021-03-29 | 2021-03-30 | 2021-03-31 | Total
RTS |  | Vol. Target | Monthly Plan Vol. | Remain
| Unit | 681582 | 100000 | 681582
| RTS-C3 West | [34 empty] | 0
| Unit | -51971 | 45000 | -70991 | 2021-03-01: 1XPC2000; 2021-03-12: 1XPC2000; 2021-03-13: 1XPC2000; 2021-03-14: 1XPC2000; 2021-03-15: 1XPC2000; 2021-03-16: 1XPC2000; 2021-03-18: 1XPC2000; 2021-03-19: 1XPC2000; 2021-03-20: 1XPC2000; 2021-03-21: 1XPC2000; 2021-03-22: 1XPC2000; 2021-03-23: 1XPC2000; 2021-03-25: 1XPC1250; 2021-03-26: 1XPC1250
| RTS-C3 East |  |  |  | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 1900 | 700 | 1720 | 540 | 0 | 1300 | 3340 | 2800 | 3280 | 580 | 1680 | 0 | 520 | 600 | [5 empty] | 19020
| Unit | -33989 | 45000 | -33989
| RTS-D1 | [34 empty] | 0
| Unit | -331310.1 | 45000 | -497437.2 | 3 LINE ARTAMA | 3 LINE ARTAMA | 3 LINE ARTAMA | 3 LINE ARTAMA | 3 LINE ARTAMA | 3 LINE ARTAMA | 3 LINE ARTAMA | 3 LINE ARTAMA | 3 LINE ARTAMA | 3 LINE ARTAMA | [6 empty] | 2 LINE ARTAMA | 2 LINE ARTAMA | 2 LINE ARTAMA | 2 LINE ARTAMA | 2 LINE ARTAMA |  | 2 LINE ARTAMA | 2 LINE ARTAMA | 2 LINE ARTAMA | 3 LINE ARTAMA | 2 LINE ARTAMA | 2 LINE ARTAMA | 2 LINE ARTAMA | 2 LINE ARTAMA | 2 LINE ARTAMA
| RTS-D2 |  |  |  | 10004.7 | 10526.4 | 7704.6 | 9537.6 | 8571.6 | 9726 | 9543.6 | 5427.6 | 6840 | 3288 | 0 | 0 | 0 | 0 | 0 | 0 | 8721.6 | 7017.6 | 7602 | 8907.6 | 5082 | 0 | 1476 | 2310 | 4116 | 6132 | 8056.2 | 5922 | 9240 | 4662 | 5712 | 166127.1
| Unit | 41441 |  | 32481 | 2021-03-01: 1XPC2000; 2021-03-02: 1XPC2000; 2021-03-03: 1XPC2000; 2021-03-04: 1XPC2000; 2021-03-05: 1XPC2000
| RTS-G |  |  |  | 2021-03-01: 1260; 2021-03-02: 2980; 2021-03-03: 2620; 2021-03-04: 1400; 2021-03-05: 700 | 8960
| Unit | 1364839 |  | 1364839
| RTN | [34 empty] | 0
| Unit | -234157.95 |  | -489652.3 | 2 LINE ARTAMA + 1xDragflow | 2 LINE ARTAMA + 1xDragflow | 2 LINE ARTAMA + 1xDragflow | 2 LINE ARTAMA + 1xDragflow | 2 LINE ARTAMA + 1xDragflow | 2 LINE ARTAMA + 1xDragflow | 2 LINE ARTAMA + 1xDragflow | 2 LINE ARTAMA + 1xDragflow | 2 LINE ARTAMA + 1xDragflow | 2 LINE ARTAMA + 1xDragflow | 2 LINE ARTAMA + 1xDragflow | 2 LINE ARTAMA + 1xDragflow | 2 LINE ARTAMA + 1xDragflow | 2 LINE ARTAMA + 1xDragflow | 2 LINE ARTAMA + 1xDragflow |  | 2 LINE ARTAMA + 1xDragflow | 2 LINE ARTAMA + 2xDragflow | 2 LINE ARTAMA + 2xDragflow | 2 LINE ARTAMA + 2xDragflow | 2 LINE ARTAMA + 2xDragflow | 2 LINE ARTAMA + 2xDragflow | 2 LINE ARTAMA + 2xDragflow | 2 LINE ARTAMA + 2xDragflow | 2xDragflow | 1 LINE ARTAMA + 2xDragflow | 1 LINE ARTAMA + 2xDragflow | 1 LINE ARTAMA + 2xDragflow | 1 LINE ARTAMA + 2xDragflow | 1 LINE ARTAMA + 2xDragflow | 1 LINE ARTAMA + 2xDragflow
| RTM |  |  |  | 8685.4 | 10224 | 5928 | 5350.2 | 4901.8 | 8247.8 | 14622.35 | 4318.8 | 10394.8 | 2618.4 | 8197.8 | 7660.8 | 4681 | 7869.6 | 5963.2 | 8496.8 | 5045.8 | 4902 | 6749.2 | 9897.8 | 8849.2 | 14014 | 11035.9 | 7775.2 | 6574 | 9956.9 | 5052.4 | 5278.8 | 26286.8 | 8926.8 | 6988.8 | 255494.35
| Unit | 397204 |  | 397014 | 2021-03-26: 1XPC2000
| SM 6 |  |  |  | 2021-03-26: 190 | 190
Total |  |  |  |  | 19970.1 | 23730.4 | 16252.6 | 16287.8 | 14173.4 | 17973.8 | 24165.95 | 9746.4 | 17234.8 | 5906.4 | 8197.8 | 7700.8 | 6581 | 8569.6 | 7683.2 | 9036.8 | 13767.4 | 13219.6 | 17691.2 | 21605.4 | 17211.2 | 14594 | 14191.9 | 10085.2 | 11210 | 16878.9 | 13108.6 | 11200.8 | 35526.8 | 13588.8 | 12700.8 | 449791.45
2021-04-01
Class | Pit | Volume |  |  | 2021-04-01 | 2021-04-02 | 2021-04-03 | 2021-04-04 | 2021-04-05 | 2021-04-06 | 2021-04-07 | 2021-04-08 | 2021-04-09 | 2021-04-10 | 2021-04-11 | 2021-04-12 | 2021-04-13 | 2021-04-14 | 2021-04-15 | 2021-04-16 | 2021-04-17 | 2021-04-18 | 2021-04-19 | 2021-04-20 | 2021-04-21 | 2021-04-22 | 2021-04-23 | 2021-04-24 | 2021-04-25 | 2021-04-26 | 2021-04-27 | 2021-04-28 | 2021-04-29 | 2021-04-30 | 2021-05-01 | Total
RTS |  | Vol. Target | Monthly Plan Vol. | Remain
| Unit | 681582 | 80000 | 681582 | bar: 2021-04-01 to 2021-04-06
| RTS-C3 West | [34 empty] | 0
| Unit | -70991 | 45000 | -71011 | 2021-04-12: 1XPC2000
| RTS-C3 East |  |  |  | 2021-04-01: 0; 2021-04-02: 0; 2021-04-03: 0; 2021-04-04: 0; 2021-04-05: 0; 2021-04-06: 0; 2021-04-07: 0; 2021-04-08: 0; 2021-04-09: 0; 2021-04-10: 0; 2021-04-11: 0; 2021-04-12: 20 | 20
| Unit | -33989 |  | -38749 | 2021-04-11: 1XPC2000,1XPC1250; 2021-04-12: 1XPC1250; 2021-04-14: 1XPC2000; 2021-04-15: 1XPC2000
| RTS-D1 |  |  |  | 0 | 0 | 0 | 0 | 0 | 380 | 0 | 0 | 0 | 0 | 1520 | 140 | 0 | 80 | 2640 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 4760
| Unit | -489652.3 |  | -489652.3 | 2 LINE ARTAMA | 2 LINE ARTAMA | 2 LINE ARTAMA | 2 LINE ARTAMA | 2 LINE ARTAMA | 2 LINE ARTAMA | 2 LINE ARTAMA |  | 2 LINE ARTAMA |  | 2 LINE ARTAMA | 1 LINE ARTAMA |  | 2 LINE ARTAMA | 2 LINE ARTAMA | 2 LINE ARTAMA | 2 LINE ARTAMA | 2 LINE ARTAMA | 2 LINE ARTAMA | 2 LINE ARTAMA | 2 LINE ARTAMA |  | 2 LINE ARTAMA | 2 LINE ARTAMA | 2 LINE ARTAMA |  | 2 LINE ARTAMA | 2 LINE ARTAMA | 2 LINE ARTAMA | 2 LINE ARTAMA
| RTS-D2 |  |  |  | 3960 | 4176 | 7398 | 3192 | 2940 | 4716 | 2520 | 0 | 2244 | 0 | 1680 | 1008 | 0 | 2520 | 4032 | 8073 | 8274 | 8862 | 5754 | 7155 | 6786 | 0 | 6930 | 9072 | 2604 | 0 | 150 | 3780 | 3282 | 3024 |  | 114132
Unit | bar: 2021-04-16 to 2021-04-21
| RTS-G | [34 empty] | 0
| Unit | -489652.3 |  | -609801 | 2021-04-21: 1XPC2000
| RTN |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 38 | 0 | 0 | 0 | 0 | [6 empty] | 38
| Unit |  |  |  | 1 LINE ARTAMA + 2xDragflow | 1 LINE ARTAMA, 2xDragflow,1XPC1200 | 1 LINE ARTAMA, 2xDragflow,1XPC1200 | 1 LINE ARTAMA, 2xDragflow,1XPC1200 | 1 LINE ARTAMA, 2xDragflow,1XPC1200 | 1 LINE ARTAMA + 1xDragflow |  |  |  |  | 1 LINE ARTAMA + 2xDragflow | 1 LINE ARTAMA + 2xDragflow |  | 1 LINE ARTAMA + 2xDragflow+1XPC1250 | 1 LINE ARTAMA + 2xDragflow+1XPC1250 | 1 LINE ARTAMA + 2xDragflow+1XPC1250 | 1 LINE ARTAMA + 2xDragflow+1XPC1250 | 1 LINE ARTAMA + 2xDragflow+1XPC1250 | 1 LINE ARTAMA + 2xDragflow+1XPC1250 | 1 LINE ARTAMA + 2xDragflow+1XPC1250 | 1 LINE ARTAMA + 2xDragflow+1XPC1250 |  | 1 LINE ARTAMA + 2xDragflow | 1 LINE ARTAMA + 2xDragflow | 1 LINE ARTAMA + 2xDragflow | 1 LINE ARTAMA + 2xDragflow | 1 LINE ARTAMA + 2xDragflow | 1 LINE ARTAMA + 2xDragflow | 1 LINE ARTAMA + 1xDragflow | 1 LINE ARTAMA + 1xDragflow
| RTM |  |  |  | 9914.8 | 9267.7 | 7836.8 | 9658.8 | 8941.6 | 2843.4 | 0 | 0 | 0 | 0 | 1193.4 | 759.6 | 0 | 6789.7 | 8101.5 | 6213.2 | 7607.2 | 4992.6 | 2676.4 | 5527.6 | 4824.2 | 0 | 3203.6 | 4255.1 | 4794.5 | 3254.8 | 1140 | 1254 | 2488.2 | 2610 |  | 120148.7
| Unit | 397014 |  | 397014 | bar: 2021-04-16 to 2021-04-21
| SM 6 | [34 empty] | 0
Total |  |  |  |  | 13874.8 | 13443.7 | 15234.8 | 12850.8 | 11881.6 | 7939.4 | 2520 | 0 | 2244 | 0 | 4393.4 | 1927.6 | 0 | 9389.7 | 14773.5 | 14286.2 | 15881.2 | 13854.6 | 8430.4 | 12682.6 | 11648.2 | 0 | 10133.6 | 13327.1 | 7398.5 | 3254.8 | 1290 | 5034 | 5770.2 | 5634 | 0 | 239098.7
2021-05-01
Class | Pit | Volume |  |  | 2021-05-01 | 2021-05-02 | 2021-05-03 | 2021-05-04 | 2021-05-05 | 2021-05-06 | 2021-05-07 | 2021-05-08 | 2021-05-09 | 2021-05-10 | 2021-05-11 | 2021-05-12 | 2021-05-13 | 2021-05-14 | 2021-05-15 | 2021-05-16 | 2021-05-17 | 2021-05-18 | 2021-05-19 | 2021-05-20 | 2021-05-21 | 2021-05-22 | 2021-05-23 | 2021-05-24 | 2021-05-25 | 2021-05-26 | 2021-05-27 | 2021-05-28 | 2021-05-29 | 2021-05-30 | 2021-05-31 | Total
RTS |  | Vol. Target | Monthly Plan Vol. | Remain
| Unit | 681582 | 80000 | 627646 | 2021-05-11: 1PC2000; 2021-05-12: 1PC2000; 2021-05-13: 1PC2000; 2021-05-14: 1PC2000; 2021-05-15: 1PC2000; 2021-05-16: 1PC2000; 2021-05-17: 1PC2000; 2021-05-18: 1PC2000; 2021-05-19: 1PC2000; 2021-05-20: 1XPC1250; 2021-05-21: 1XPC1250; 2021-05-22: 1XPC1250,1PC2000; 2021-05-23: 1XPC1250; 2021-05-26: 1XPC1250; 2021-05-27: 1XPC1250
| RTS-C3 West |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2622 | 4484 | 3078 | 5738 | 5282 | 6194 | 5624 | 5206 | 3420 | 1464 | 1966 | 2398 | 1064 | 0 | 0 | 1444 | 3952 |  |  |  |  | 53936
| Unit | -71011 | 45000 | -71011
| RTS-C3 East |  |  |  | 2021-05-01: 0; 2021-05-02: 0; 2021-05-03: 0; 2021-05-04: 0; 2021-05-05: 0; 2021-05-06: 0; 2021-05-07: 0; 2021-05-08: 0; 2021-05-09: 0; 2021-05-10: 0 | 0
| Unit | -38749 |  | -38749 | bar: 2021-05-01 to 2021-05-10
| RTS-D1 | [34 empty] | 0
| Unit | -489652.3 |  | -636904.3 |  | 1 LINE ARTAMA |  | 1 LINE ARTAMA | 2 LINE ARTAMA | 2 LINE ARTAMA | 1 LINE ARTAMA | 1 LINE ARTAMA | 1 LINE ARTAMA | 1 LINE ARTAMA | 2 LINE ARTAMA | 2 LINE ARTAMA | 2 LINE ARTAMA | 2 LINE ARTAMA | 2 LINE ARTAMA | 2 LINE ARTAMA | 2 LINE ARTAMA | 2 LINE ARTAMA | 2 LINE ARTAMA | 2 LINE ARTAMA | 2 LINE ARTAMA | 2 LINE ARTAMA | 2 LINE ARTAMA,1XPC1250 | 2 LINE ARTAMA,1XPC1250 |  |  | 2 LINE ARTAMA,1XPC1250
| RTS-D2 |  |  |  | 0 | 1680 | 0 | 1470 | 1974 | 4032 | 4176 | 4176 | 3864 | 4032 | 8406 | 9036 | 9540 | 9036 | 9036 | 7812 | 7047 | 9288 | 9288 | 9288 | 9504 | 9036 | 7776 | 4899 | 0 | 0 | 2856 |  |  |  |  | 147252
| Unit | 0 |  | 0 | bar: 2021-05-01 to 2021-05-10
| RTS-G | [34 empty] | 0
| Unit | -609801 |  | -610521 | 2021-05-22: 1XPC850
| RTN |  |  |  | 2021-05-22: 720 | 720
| Unit | 0 |  | -125976 | 2xDragflow | 2xDragflow | 1 LINE ARTAMA + 2xDragflow | 1 LINE ARTAMA + 2xDragflow |  |  |  | 1 LINE ARTAMA + 2xDragflow | 1 LINE ARTAMA + 2xDragflow | 1 LINE ARTAMA + 2xDragflow | 1 LINE ARTAMA + 2xDragflow | 1 LINE ARTAMA + 1xDragflow | 1 LINE ARTAMA + 1xDragflow | 1 LINE ARTAMA + 1xDragflow | 1 LINE ARTAMA + 1xDragflow | 1 LINE ARTAMA + 1xDragflow | 1 LINE ARTAMA + 1xDragflow | 1 LINE ARTAMA + 1xDragflow | 1 LINE ARTAMA + 1xDragflow | 1 LINE ARTAMA + 1xDragflow | 1 LINE ARTAMA + 1xDragflow | 1 LINE ARTAMA + 1xDragflow | 1 LINE ARTAMA + 1xDragflow | 1 LINE ARTAMA + 1xDragflow | 1 LINE ARTAMA + 1xDragflow | 1 LINE ARTAMA + 1xDragflow | 1 LINE ARTAMA + 1xDragflow
| RTM |  |  |  | 3686 | 836 | 4980.5 | 2927 | 1064 | 2850 | 4066 | 6755 | 4151.1 | 5941.1 | 8170.9 | 5696.8 | 7292.8 | 8090.8 | 5685.2 | 6552.6 | 4102.4 | 6494.8 | 7844.8 | 5786.4 | 5562.1 | 6646.8 | 2152.8 | 2674.1 | 2774 | 2128 | 1064 |  |  |  |  | 125976
| Unit | 397014 |  | 397014 | bar: 2021-05-01 to 2021-05-10
| SM 6 | [34 empty] | 0
Total |  |  |  |  | 3686 | 2516 | 4980.5 | 4397 | 3038 | 6882 | 8242 | 10931 | 8015.1 | 9973.1 | 19198.9 | 19216.8 | 19910.8 | 22864.8 | 20003.2 | 20558.6 | 16773.4 | 20988.8 | 20552.8 | 16538.4 | 17032.1 | 18800.8 | 10992.8 | 7573.1 | 2774 | 3572 | 7872 | 0 | 0 | 0 | 0 | 327884
2021-06-01
Class | Pit | Volume |  |  | 2021-06-01 | 2021-06-02 | 2021-06-03 | 2021-06-04 | 2021-06-05 | 2021-06-06 | 2021-06-07 | 2021-06-08 | 2021-06-09 | 2021-06-10 | 2021-06-11 | 2021-06-12 | 2021-06-13 | 2021-06-14 | 2021-06-15 | 2021-06-16 | 2021-06-17 | 2021-06-18 | 2021-06-19 | 2021-06-20 | 2021-06-21 | 2021-06-22 | 2021-06-23 | 2021-06-24 | 2021-06-25 | 2021-06-26 | 2021-06-27 | 2021-06-28 | 2021-06-29 | 2021-06-30 | 2021-07-01 | Total
RTS |  | Vol. Target | Monthly Plan Vol. | Remain
| Unit | 627646 | 80000 | 627646
| RTS-C3 West | [34 empty] | 0
| Unit | -71011 | 45000 | -71011
| RTS-C3 East | [34 empty] | 0
| Unit | -38749 |  | -38749
| RTS-D1 | [34 empty] | 0
| Unit | 397014 |  | 397014
| SM 6 | [34 empty] | 0
| Unit | 0 |  | 0
| RTS-C4 | [34 empty] | 0
Total |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2021-07-01
Class | Pit | Volume |  |  | 2021-07-01 | 2021-07-02 | 2021-07-03 | 2021-07-04 | 2021-07-05 | 2021-07-06 | 2021-07-07 | 2021-07-08 | 2021-07-09 | 2021-07-10 | 2021-07-11 | 2021-07-12 | 2021-07-13 | 2021-07-14 | 2021-07-15 | 2021-07-16 | 2021-07-17 | 2021-07-18 | 2021-07-19 | 2021-07-20 | 2021-07-21 | 2021-07-22 | 2021-07-23 | 2021-07-24 | 2021-07-25 | 2021-07-26 | 2021-07-27 | 2021-07-28 | 2021-07-29 | 2021-07-30 | 2021-07-31 | Total
RTS |  | Vol. Target | Monthly Plan Vol. | Remain
| Unit | 627646 | 80000 | 627646 | bar: 2021-07-30 to 2021-07-31
| RTS-C3 West | [34 empty] | 0
| Unit | -71011 | 45000 | -71011
| RTS-C3 East | [34 empty] | 0
| Unit | -38749 |  | -38749
| RTS-D1 | [34 empty] | 0
| Unit | 397014 |  | 397014
| SM 6 | [34 empty] | 0
Total |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2021-08-01
` | Pit | Volume |  |  | 2021-08-01 | 2021-08-02 | 2021-08-03 | 2021-08-04 | 2021-08-05 | 2021-08-06 | 2021-08-07 | 2021-08-08 | 2021-08-09 | 2021-08-10 | 2021-08-11 | 2021-08-12 | 2021-08-13 | 2021-08-14 | 2021-08-15 | 2021-08-16 | 2021-08-17 | 2021-08-18 | 2021-08-19 | 2021-08-20 | 2021-08-21 | 2021-08-22 | 2021-08-23 | 2021-08-24 | 2021-08-25 | 2021-08-26 | 2021-08-27 | 2021-08-28 | 2021-08-29 | 2021-08-30 | 2021-08-31 | Total
RTS |  | Vol. Target | Monthly Plan Vol. | Remain
| Unit | 627646 | 90000 | 627646
| RTS-C3 West | [34 empty] | 0
| Unit | -71011 | 45000 | -71011
| RTS-C3 East | [34 empty] | 0
| Unit | -38749 |  | -38749 | bar: 2021-08-01 to 2021-08-26
| RTS-D1 | [34 empty] | 0
| Unit | 397014 |  | 397014
| SM 6 | [34 empty] | 0
Total |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2021-09-01
Class | Pit | Volume |  |  | 2021-09-01 | 2021-09-02 | 2021-09-03 | 2021-09-04 | 2021-09-05 | 2021-09-06 | 2021-09-07 | 2021-09-08 | 2021-09-09 | 2021-09-10 | 2021-09-11 | 2021-09-12 | 2021-09-13 | 2021-09-14 | 2021-09-15 | 2021-09-16 | 2021-09-17 | 2021-09-18 | 2021-09-19 | 2021-09-20 | 2021-09-21 | 2021-09-22 | 2021-09-23 | 2021-09-24 | 2021-09-25 | 2021-09-26 | 2021-09-27 | 2021-09-28 | 2021-09-29 | 2021-09-30 | 2021-10-01 | Total
RTS |  | Vol. Target | Monthly Plan Vol. | Remain
| Unit | 627646 | 0 | 627646 | bar: 2021-09-01 to 2021-09-12
| RTS-C3 West | [34 empty] | 0
| Unit | 140000 | 140000 | 140000 | bar: 2021-09-01 to 2021-09-12
| RTS-C4 | [34 empty] | 0
| Unit | -71011 | 0 | -71011 | bar: 2021-09-01 to 2021-09-16
| RTS-C3 East | [34 empty] | 0
| Unit | -38749 | 101000 | -38749 | bar: 2021-09-01 to 2021-09-16
| RTS-D1 | [34 empty] | 0
| Unit | 397014 | 0 | 397014 | bar: 2021-09-01 to 2021-09-10
| RTS-G | [34 empty] | 0
| Unit | 187000 | 187000 | 187000 | bar: 2021-09-01 to 2021-09-10
| RTM | [34 empty] | 0
Total |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2021-10-01
Class | Pit | Volume |  |  | 2021-10-01 | 2021-10-02 | 2021-10-03 | 2021-10-04 | 2021-10-05 | 2021-10-06 | 2021-10-07 | 2021-10-08 | 2021-10-09 | 2021-10-10 | 2021-10-11 | 2021-10-12 | 2021-10-13 | 2021-10-14 | 2021-10-15 | 2021-10-16 | 2021-10-17 | 2021-10-18 | 2021-10-19 | 2021-10-20 | 2021-10-21 | 2021-10-22 | 2021-10-23 | 2021-10-24 | 2021-10-25 | 2021-10-26 | 2021-10-27 | 2021-10-28 | 2021-10-29 | 2021-10-30 | 2021-10-31 | Total
RTS |  | Vol. Target | Monthly Plan Vol. | Remain
| Unit | 627646 | 150000 | 627646
| RTS-C3 West | [34 empty] | 0
| Unit | 140000 | 45000 | 140000
| RTS-C4 | [34 empty] | 0
| Unit | -71011 | 45000 | -71011
| RTS-C3 East | [34 empty] | 0
| Unit | -38749 |  | -38749
| RTS-D1 | [34 empty] | 0
| Unit | 397014 |  | 397014
| RTS-G | [34 empty] | 0
| Unit | 187000 |  | 187000
| RTM | [34 empty] | 0
Total |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2021-11-01
Class | Pit | Volume |  |  | 2021-11-01 | 2021-11-02 | 2021-11-03 | 2021-11-04 | 2021-11-05 | 2021-11-06 | 2021-11-07 | 2021-11-08 | 2021-11-09 | 2021-11-10 | 2021-11-11 | 2021-11-12 | 2021-11-13 | 2021-11-14 | 2021-11-15 | 2021-11-16 | 2021-11-17 | 2021-11-18 | 2021-11-19 | 2021-11-20 | 2021-11-21 | 2021-11-22 | 2021-11-23 | 2021-11-24 | 2021-11-25 | 2021-11-26 | 2021-11-27 | 2021-11-28 | 2021-11-29 | 2021-11-30 | 2021-12-01 | Total
RTS |  | Vol. Target | Monthly Plan Vol. | Remain
| Unit | 627646 |  | 627646
| RTS-C3 West | [34 empty] | 0
| Unit | 140000 |  | 140000
| RTS-C4 | [34 empty] | 0
| Unit | -71011 | 45000 | -71011
| RTS-C3 East | [34 empty] | 0
| Unit | -38749 |  | -38749 | bar: 2021-11-01 to 2021-11-19
| RTS-D1 | [34 empty] | 0
| Unit | 397014 |  | 397014
| RTS-G | [34 empty] | 0
| Unit | 187000 |  | 187000
| RTM | [34 empty] | 0
| Unit | 0
| RTN | [34 empty] | 0
Total |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2021-12-01
Class | Pit | Volume |  |  | 2021-12-01 | 2021-12-02 | 2021-12-03 | 2021-12-04 | 2021-12-05 | 2021-12-06 | 2021-12-07 | 2021-12-08 | 2021-12-09 | 2021-12-10 | 2021-12-11 | 2021-12-12 | 2021-12-13 | 2021-12-14 | 2021-12-15 | 2021-12-16 | 2021-12-17 | 2021-12-18 | 2021-12-19 | 2021-12-20 | 2021-12-21 | 2021-12-22 | 2021-12-23 | 2021-12-24 | 2021-12-25 | 2021-12-26 | 2021-12-27 | 2021-12-28 | 2021-12-29 | 2021-12-30 | 2021-12-31 | Total
RTS |  | Vol. Target | Monthly Plan Vol. | Remain
| Unit | 627646 |  | 627646 | bar: 2021-12-01 to 2021-12-04
| RTS-C3 West | [34 empty] | 0
| Unit | 140000 |  | 140000 | bar: 2021-12-01 to 2021-12-04
| RTS-C4 | [34 empty] | 0
| Unit | -71011 | 45000 | -71011 | bar: 2021-12-01 to 2021-12-26
| RTS-C3 East | [34 empty] | 0
| Unit | -38749 |  | -38749
| RTS-D1 | [34 empty] | 0
| Unit | 397014 | 20000 | 397014
| RTS-G | [34 empty] | 0
| Unit | 187000 | 20000 | 187000
| RTM | [34 empty] | 0
| Unit | 0 | 20000 | 0
| RTN | [34 empty] | 0
Total |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## Bima
■ Hasil Loading Lumpur
2021-01-01
Class | Pit | Volume |  |  | 2021-01-01 | 2021-01-02 | 2021-01-03 | 2021-01-04 | 2021-01-05 | 2021-01-06 | 2021-01-07 | 2021-01-08 | 2021-01-09 | 2021-01-10 | 2021-01-11 | 2021-01-12 | 2021-01-13 | 2021-01-14 | 2021-01-15 | 2021-01-16 | 2021-01-17 | 2021-01-18 | 2021-01-19 | 2021-01-20 | 2021-01-21 | 2021-01-22 | 2021-01-23 | 2021-01-24 | 2021-01-25 | 2021-01-26 | 2021-01-27 | 2021-01-28 | 2021-01-29 | 2021-01-30 | 2021-01-31 | Total
SB1 |  | Vol. Target | Monthly Plan Vol. | Remain
| Unit | 18592 |  | 16089.5 | 2021-01-26: EX-040; 2021-01-27: EX-040; 2021-01-28: EX-040; 2021-01-29: EX-040; 2021-01-30: EX-040; 2021-01-31: EX-040
| Sump 24 |  |  |  | 2021-01-26: 312; 2021-01-27: 370.5; 2021-01-28: 656.5; 2021-01-29: 273; 2021-01-30: 513.5; 2021-01-31: 377 | 2502.5
| Unit | 13213 |  | 13213
| Sump 56 | [34 empty] | 0
Total |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 312 | 370.5 | 656.5 | 273 | 513.5 | 377 | 2502.5
2021-02-01
Class | Pit | Volume |  |  | 2021-02-01 | 2021-02-02 | 2021-02-03 | 2021-02-04 | 2021-02-05 | 2021-02-06 | 2021-02-07 | 2021-02-08 | 2021-02-09 | 2021-02-10 | 2021-02-11 | 2021-02-12 | 2021-02-13 | 2021-02-14 | 2021-02-15 | 2021-02-16 | 2021-02-17 | 2021-02-18 | 2021-02-19 | 2021-02-20 | 2021-02-21 | 2021-02-22 | 2021-02-23 | 2021-02-24 | 2021-02-25 | 2021-02-26 | 2021-02-27 | 2021-02-28 | 2021-03-01 | 2021-03-02 | 2021-03-03 | Total
SB1 |  | Vol. Target | Monthly Plan Vol. | Remain
| Unit | 16089.5 |  | 1880.5 | 2021-02-01: EX-047; 2021-02-02: EX-047; 2021-02-03: EX-047; 2021-02-04: EX-047; 2021-02-05: EX-047; 2021-02-06: EX-040; 2021-02-07: EX-040; 2021-02-08: EX-047; 2021-02-09: EX-047; 2021-02-10: EX-047; 2021-02-11: EX-047; 2021-02-12: EX-047; 2021-02-13: EX-047; 2021-02-14: EX-047; 2021-02-18: EX-047; 2021-02-20: EX-047; 2021-02-21: EX-047; 2021-02-23: EX-055
| Sump 24 |  |  |  | 539.5 | 149.5 | 286 | 1287 | 942.5 | 1664 | 1846 | 598 | 942.5 | 1066 | 1573 | 338 | 702 | 591.5 | 0 | 0 | 0 | 214.5 | 0 | 461.5 | 273 | 0 | 734.5 | [8 empty] | 14209
| Unit | 13213 |  | 13213
| Sump 56 | [34 empty] | 0
Total |  |  |  |  | 539.5 | 149.5 | 286 | 1287 | 942.5 | 1664 | 1846 | 598 | 942.5 | 1066 | 1573 | 338 | 702 | 591.5 | 0 | 0 | 0 | 214.5 | 0 | 461.5 | 273 | 0 | 734.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14209
2021-03-01
Class | Pit | Volume |  |  | 2021-03-01 | 2021-03-02 | 2021-03-03 | 2021-03-04 | 2021-03-05 | 2021-03-06 | 2021-03-07 | 2021-03-08 | 2021-03-09 | 2021-03-10 | 2021-03-11 | 2021-03-12 | 2021-03-13 | 2021-03-14 | 2021-03-15 | 2021-03-16 | 2021-03-17 | 2021-03-18 | 2021-03-19 | 2021-03-20 | 2021-03-21 | 2021-03-22 | 2021-03-23 | 2021-03-24 | 2021-03-25 | 2021-03-26 | 2021-03-27 | 2021-03-28 | 2021-03-29 | 2021-03-30 | 2021-03-31 | Total
SB1 |  | Vol. Target | Monthly Plan Vol. | Remain
| Unit | 1880.5 |  | 1880.5
| Sump 24 | [34 empty] | 0
| Unit | 13213 |  | 13213
| Sump 56 | [34 empty] | 0
Total |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2021-04-01
Class | Pit | Volume |  |  | 2021-04-01 | 2021-04-02 | 2021-04-03 | 2021-04-04 | 2021-04-05 | 2021-04-06 | 2021-04-07 | 2021-04-08 | 2021-04-09 | 2021-04-10 | 2021-04-11 | 2021-04-12 | 2021-04-13 | 2021-04-14 | 2021-04-15 | 2021-04-16 | 2021-04-17 | 2021-04-18 | 2021-04-19 | 2021-04-20 | 2021-04-21 | 2021-04-22 | 2021-04-23 | 2021-04-24 | 2021-04-25 | 2021-04-26 | 2021-04-27 | 2021-04-28 | 2021-04-29 | 2021-04-30 | 2021-05-01 | Total
SB1 |  | Vol. Target | Monthly Plan Vol. | Remain
| Unit | 1880.5 |  | 1880.5
| Sump 24 | [34 empty] | 0
| Unit | 13213 |  | 13213
| Sump 56 | [34 empty] | 0
Total |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2021-05-01
Class | Pit | Volume |  |  | 2021-05-01 | 2021-05-02 | 2021-05-03 | 2021-05-04 | 2021-05-05 | 2021-05-06 | 2021-05-07 | 2021-05-08 | 2021-05-09 | 2021-05-10 | 2021-05-11 | 2021-05-12 | 2021-05-13 | 2021-05-14 | 2021-05-15 | 2021-05-16 | 2021-05-17 | 2021-05-18 | 2021-05-19 | 2021-05-20 | 2021-05-21 | 2021-05-22 | 2021-05-23 | 2021-05-24 | 2021-05-25 | 2021-05-26 | 2021-05-27 | 2021-05-28 | 2021-05-29 | 2021-05-30 | 2021-05-31 | Total
SB1 |  | Vol. Target | Monthly Plan Vol. | Remain
| Unit | 1880.5 |  | 1880.5
| Sump 24 | [34 empty] | 0
| Unit | 13213 |  | 13213
| Sump 56 | [34 empty] | 0
Total |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2021-06-01
Class | Pit | Volume |  |  | 2021-06-01 | 2021-06-02 | 2021-06-03 | 2021-06-04 | 2021-06-05 | 2021-06-06 | 2021-06-07 | 2021-06-08 | 2021-06-09 | 2021-06-10 | 2021-06-11 | 2021-06-12 | 2021-06-13 | 2021-06-14 | 2021-06-15 | 2021-06-16 | 2021-06-17 | 2021-06-18 | 2021-06-19 | 2021-06-20 | 2021-06-21 | 2021-06-22 | 2021-06-23 | 2021-06-24 | 2021-06-25 | 2021-06-26 | 2021-06-27 | 2021-06-28 | 2021-06-29 | 2021-06-30 | 2021-07-01 | Total
SB1 |  | Vol. Target | Monthly Plan Vol. | Remain
| Unit | 1880.5 | 50000 | 1880.5
| Sump 24 | [34 empty] | 0
| Unit | 13213 | 50000 | 13213
| Sump 56 | [34 empty] | 0
Total |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2021-07-01
Class | Pit | Volume |  |  | 2021-07-01 | 2021-07-02 | 2021-07-03 | 2021-07-04 | 2021-07-05 | 2021-07-06 | 2021-07-07 | 2021-07-08 | 2021-07-09 | 2021-07-10 | 2021-07-11 | 2021-07-12 | 2021-07-13 | 2021-07-14 | 2021-07-15 | 2021-07-16 | 2021-07-17 | 2021-07-18 | 2021-07-19 | 2021-07-20 | 2021-07-21 | 2021-07-22 | 2021-07-23 | 2021-07-24 | 2021-07-25 | 2021-07-26 | 2021-07-27 | 2021-07-28 | 2021-07-29 | 2021-07-30 | 2021-07-31 | Total
SB1 |  | Vol. Target | Monthly Plan Vol. | Remain
| Unit | 1880.5 |  | 1880.5
| Sump 24 | [34 empty] | 0
| Unit | 13213 |  | 13213
| Sump 56 | [34 empty] | 0
Total |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2021-08-01
Class | Pit | Volume |  |  | 2021-08-01 | 2021-08-02 | 2021-08-03 | 2021-08-04 | 2021-08-05 | 2021-08-06 | 2021-08-07 | 2021-08-08 | 2021-08-09 | 2021-08-10 | 2021-08-11 | 2021-08-12 | 2021-08-13 | 2021-08-14 | 2021-08-15 | 2021-08-16 | 2021-08-17 | 2021-08-18 | 2021-08-19 | 2021-08-20 | 2021-08-21 | 2021-08-22 | 2021-08-23 | 2021-08-24 | 2021-08-25 | 2021-08-26 | 2021-08-27 | 2021-08-28 | 2021-08-29 | 2021-08-30 | 2021-08-31 | Total
SB1 |  | Vol. Target | Monthly Plan Vol. | Remain
| Unit | 1880.5 |  | 1880.5
| Sump 24 | [34 empty] | 0
| Unit | 13213 |  | 13213
| Sump 56 | [34 empty] | 0
Total |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2021-09-01
Class | Pit | Volume |  |  | 2021-09-01 | 2021-09-02 | 2021-09-03 | 2021-09-04 | 2021-09-05 | 2021-09-06 | 2021-09-07 | 2021-09-08 | 2021-09-09 | 2021-09-10 | 2021-09-11 | 2021-09-12 | 2021-09-13 | 2021-09-14 | 2021-09-15 | 2021-09-16 | 2021-09-17 | 2021-09-18 | 2021-09-19 | 2021-09-20 | 2021-09-21 | 2021-09-22 | 2021-09-23 | 2021-09-24 | 2021-09-25 | 2021-09-26 | 2021-09-27 | 2021-09-28 | 2021-09-29 | 2021-09-30 | 2021-10-01 | Total
SB1 |  | Vol. Target | Monthly Plan Vol. | Remain
| Unit | 1880.5 |  | 1880.5
| Sump 24 | [34 empty] | 0
| Unit | 13213 |  | 13213
| Sump 56 | [34 empty] | 0
Total |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2021-10-01
Class | Pit | Volume |  |  | 2021-10-01 | 2021-10-02 | 2021-10-03 | 2021-10-04 | 2021-10-05 | 2021-10-06 | 2021-10-07 | 2021-10-08 | 2021-10-09 | 2021-10-10 | 2021-10-11 | 2021-10-12 | 2021-10-13 | 2021-10-14 | 2021-10-15 | 2021-10-16 | 2021-10-17 | 2021-10-18 | 2021-10-19 | 2021-10-20 | 2021-10-21 | 2021-10-22 | 2021-10-23 | 2021-10-24 | 2021-10-25 | 2021-10-26 | 2021-10-27 | 2021-10-28 | 2021-10-29 | 2021-10-30 | 2021-10-31 | Total
SB1 |  | Vol. Target | Monthly Plan Vol. | Remain
| Unit | 1880.5 |  | 1880.5
| Sump 24 | [34 empty] | 0
| Unit | 13213 |  | 13213
| Sump 56 | [34 empty] | 0
Total |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2021-11-01
Class | Pit | Volume |  |  | 2021-11-01 | 2021-11-02 | 2021-11-03 | 2021-11-04 | 2021-11-05 | 2021-11-06 | 2021-11-07 | 2021-11-08 | 2021-11-09 | 2021-11-10 | 2021-11-11 | 2021-11-12 | 2021-11-13 | 2021-11-14 | 2021-11-15 | 2021-11-16 | 2021-11-17 | 2021-11-18 | 2021-11-19 | 2021-11-20 | 2021-11-21 | 2021-11-22 | 2021-11-23 | 2021-11-24 | 2021-11-25 | 2021-11-26 | 2021-11-27 | 2021-11-28 | 2021-11-29 | 2021-11-30 | 2021-12-01 | Total
SB1 |  | Vol. Target | Monthly Plan Vol. | Remain
| Unit | 1880.5 |  | 1880.5
| Sump 24 | [34 empty] | 0
| Unit | 13213 |  | 13213
| Sump 56 | [34 empty] | 0
Total |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2021-12-01
Class | Pit | Volume |  |  | 2021-12-01 | 2021-12-02 | 2021-12-03 | 2021-12-04 | 2021-12-05 | 2021-12-06 | 2021-12-07 | 2021-12-08 | 2021-12-09 | 2021-12-10 | 2021-12-11 | 2021-12-12 | 2021-12-13 | 2021-12-14 | 2021-12-15 | 2021-12-16 | 2021-12-17 | 2021-12-18 | 2021-12-19 | 2021-12-20 | 2021-12-21 | 2021-12-22 | 2021-12-23 | 2021-12-24 | 2021-12-25 | 2021-12-26 | 2021-12-27 | 2021-12-28 | 2021-12-29 | 2021-12-30 | 2021-12-31 | Total
SB1 |  | Vol. Target | Monthly Plan Vol. | Remain
| Unit | 1880.5 |  | 1880.5
| Sump 24 | [34 empty] | 0
| Unit | 13213 |  | 13213
| Sump 56 | [34 empty] | 0
Total |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## Outpit-Sims
■ Hasil Loading Lumpur
2021-01-01
Class | Pit | Volume |  |  | 2021-01-01 | 2021-01-02 | 2021-01-03 | 2021-01-04 | 2021-01-05 | 2021-01-06 | 2021-01-07 | 2021-01-08 | 2021-01-09 | 2021-01-10 | 2021-01-11 | 2021-01-12 | 2021-01-13 | 2021-01-14 | 2021-01-15 | 2021-01-16 | 2021-01-17 | 2021-01-18 | 2021-01-19 | 2021-01-20 | 2021-01-21 | 2021-01-22 | 2021-01-23 | 2021-01-24 | 2021-01-25 | 2021-01-26 | 2021-01-27 | 2021-01-28 | 2021-01-29 | 2021-01-30 | 2021-01-31 | Total
SM-A |  | Vol. Target | Monthly Plan Vol. | Remain
| Unit | 160000 |  | 160000
| WD SM B1 (S/P AL-61) | [34 empty] | 0
| Unit |  |  |  | Dragflow | Dragflow | Dragflow | Dragflow | Dragflow | Dragflow | Dragflow | Dragflow | Dragflow | Dragflow | Dragflow | Dragflow | Dragflow | Dragflow | Dragflow | Dragflow | Dragflow | Dragflow | Dragflow | Dragflow | Dragflow | Dragflow | Dragflow | Dragflow | Dragflow | Dragflow | Dragflow | Dragflow | Dragflow | Dragflow | Dragflow
| SM AW |  |  |  | 2638.2353 | 3430.8088 | 2948.1618 | 2068.0147 | 2326.7647 | 3073.2353 | 3667.0037 | 3504.7059 | 3703.4559 | 4323.5294 | 3283.1801 | 3362.6471 | 3742.9412 | 2925 | 3021.0662 | 3463.2353 | 4038.0882 | 2973.9706 | 3155.7353 | 3403.125 | 3431.25 | 2858.8235 | 3543.75 | 3742.0037 | 4237.5 | 3750 | 4143.5846 | 1687.5 | 923.1618 | 0 | 0 | 93370.4779
Unit
| SM AW | [34 empty] | 0
| Unit |  |  | 0
0
Total |  |  |  |  | 2638.2353 | 3430.8088 | 2948.1618 | 2068.0147 | 2326.7647 | 3073.2353 | 3667.0037 | 3504.7059 | 3703.4559 | 4323.5294 | 3283.1801 | 3362.6471 | 3742.9412 | 2925 | 3021.0662 | 3463.2353 | 4038.0882 | 2973.9706 | 3155.7353 | 3403.125 | 3431.25 | 2858.8235 | 3543.75 | 3742.0037 | 4237.5 | 3750 | 4143.5846 | 1687.5 | 923.1618 | 0 | 0 | 93370.4779
2021-02-01
Class | Pit | Volume |  |  | 2021-02-01 | 2021-02-02 | 2021-02-03 | 2021-02-04 | 2021-02-05 | 2021-02-06 | 2021-02-07 | 2021-02-08 | 2021-02-09 | 2021-02-10 | 2021-02-11 | 2021-02-12 | 2021-02-13 | 2021-02-14 | 2021-02-15 | 2021-02-16 | 2021-02-17 | 2021-02-18 | 2021-02-19 | 2021-02-20 | 2021-02-21 | 2021-02-22 | 2021-02-23 | 2021-02-24 | 2021-02-25 | 2021-02-26 | 2021-02-27 | 2021-02-28 | 2021-03-01 | 2021-03-02 | 2021-03-03 | Total
SM-A |  | Vol. Target | Monthly Plan Vol. | Remain
| Unit | 160000 |  | 160000
| WD SM B1 (S/P AL-61) | [34 empty] | 0
| Unit | 0 |  | 0
| SM AW | [34 empty] | 0
| Unit | 0 |  | 0
| SM AW | [34 empty] | 0
| Unit | 0 |  | 0
| 0 | [34 empty] | 0
Total |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2021-03-01
Class | Pit | Volume |  |  | 2021-03-01 | 2021-03-02 | 2021-03-03 | 2021-03-04 | 2021-03-05 | 2021-03-06 | 2021-03-07 | 2021-03-08 | 2021-03-09 | 2021-03-10 | 2021-03-11 | 2021-03-12 | 2021-03-13 | 2021-03-14 | 2021-03-15 | 2021-03-16 | 2021-03-17 | 2021-03-18 | 2021-03-19 | 2021-03-20 | 2021-03-21 | 2021-03-22 | 2021-03-23 | 2021-03-24 | 2021-03-25 | 2021-03-26 | 2021-03-27 | 2021-03-28 | 2021-03-29 | 2021-03-30 | 2021-03-31 | Total
SM-A |  | Vol. Target | Monthly Plan Vol. | Remain
| Unit | 160000 |  | 160000
| WD SM B1 (S/P AL-61) | [34 empty] | 0
| Unit | 0 |  | 0
| SM AW | [34 empty] | 0
| Unit | 0 |  | 0
| SM AW | [34 empty] | 0
| Unit | 0 |  | 0
| 0 | [34 empty] | 0
Total |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2021-04-01
Class | Pit | Volume |  |  | 2021-04-01 | 2021-04-02 | 2021-04-03 | 2021-04-04 | 2021-04-05 | 2021-04-06 | 2021-04-07 | 2021-04-08 | 2021-04-09 | 2021-04-10 | 2021-04-11 | 2021-04-12 | 2021-04-13 | 2021-04-14 | 2021-04-15 | 2021-04-16 | 2021-04-17 | 2021-04-18 | 2021-04-19 | 2021-04-20 | 2021-04-21 | 2021-04-22 | 2021-04-23 | 2021-04-24 | 2021-04-25 | 2021-04-26 | 2021-04-27 | 2021-04-28 | 2021-04-29 | 2021-04-30 | 2021-05-01 | Total
SM-A |  | Vol. Target | Monthly Plan Vol. | Remain
| Unit | 160000 | 180000 | 160000
| WD SM B1 (S/P AL-61) | [34 empty] | 0
| Unit | 0 |  | 0
| SM AW | [34 empty] | 0
| Unit | 0 |  | 0
| SM AW | [34 empty] | 0
| Unit | 0 |  | 0
| 0 | [34 empty] | 0
Total |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2021-05-01
Class | Pit | Volume |  |  | 2021-05-01 | 2021-05-02 | 2021-05-03 | 2021-05-04 | 2021-05-05 | 2021-05-06 | 2021-05-07 | 2021-05-08 | 2021-05-09 | 2021-05-10 | 2021-05-11 | 2021-05-12 | 2021-05-13 | 2021-05-14 | 2021-05-15 | 2021-05-16 | 2021-05-17 | 2021-05-18 | 2021-05-19 | 2021-05-20 | 2021-05-21 | 2021-05-22 | 2021-05-23 | 2021-05-24 | 2021-05-25 | 2021-05-26 | 2021-05-27 | 2021-05-28 | 2021-05-29 | 2021-05-30 | 2021-05-31 | Total
SM-A |  | Vol. Target | Monthly Plan Vol. | Remain
| Unit | 160000 | 120000 | 160000
| WD SM B1 (S/P AL-61) | [34 empty] | 0
| Unit | 0 |  | -32203.3775 | 2021-05-07: EX 2701; 2021-05-08: EX 2701; 2021-05-09: EX 2701; 2021-05-10: EX 2701; 2021-05-11: EX 2701; 2021-05-12: EX 2701; 2021-05-13: EX 2701; 2021-05-14: EX 2701; 2021-05-15: EX 2701; 2021-05-16: EX 2701; 2021-05-17: EX 2701; 2021-05-18: EX 2701; 2021-05-19: EX 2701; 2021-05-22: EX 2701; 2021-05-23: EX 2701; 2021-05-24: EX 2701; 2021-05-25: EX 2701; 2021-05-26: EX 2701
| SM AW |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 2009.88 | 1656 | 380.5 | 648.81 | 1995.75 | 1787.5625 | 850.4375 | 2417.375 | 1142.5 | 2903.3125 | 3537.1875 | 2193.4375 | 1854.625 | 0 | 0 | 2369.56 | 1751.19 | 1374.19 | 1138.81 | 2192.25 | 0 | 0 | 0 | 0 | 0 | 32203.3775
| Unit | 0 | 50000 | 0
| SM-AW | [34 empty] | 0
| Unit | 0 |  | 0
| 0 | [34 empty] | 0
Total |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 2009.88 | 1656 | 380.5 | 648.81 | 1995.75 | 1787.5625 | 850.4375 | 2417.375 | 1142.5 | 2903.3125 | 3537.1875 | 2193.4375 | 1854.625 | 0 | 0 | 2369.56 | 1751.19 | 1374.19 | 1138.81 | 2192.25 | 0 | 0 | 0 | 0 | 0 | 32203.3775
2021-06-01
Class | Pit | Volume |  |  | 2021-06-01 | 2021-06-02 | 2021-06-03 | 2021-06-04 | 2021-06-05 | 2021-06-06 | 2021-06-07 | 2021-06-08 | 2021-06-09 | 2021-06-10 | 2021-06-11 | 2021-06-12 | 2021-06-13 | 2021-06-14 | 2021-06-15 | 2021-06-16 | 2021-06-17 | 2021-06-18 | 2021-06-19 | 2021-06-20 | 2021-06-21 | 2021-06-22 | 2021-06-23 | 2021-06-24 | 2021-06-25 | 2021-06-26 | 2021-06-27 | 2021-06-28 | 2021-06-29 | 2021-06-30 | 2021-07-01 | Total
SM-A |  | Vol. Target | Monthly Plan Vol. | Remain
| Unit | 160000 |  | 160000
| WD SM B1 (S/P AL-61) | [34 empty] | 0
| Unit | -32203.3775 |  | -32203.3775
| SM AW | [34 empty] | 0
| Unit | 0 | 100000 | 0
| SM-AW | [34 empty] | 0
| Unit | 0 |  | 0
| 0 | [34 empty] | 0
Total |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2021-07-01
Class | Pit | Volume |  |  | 2021-07-01 | 2021-07-02 | 2021-07-03 | 2021-07-04 | 2021-07-05 | 2021-07-06 | 2021-07-07 | 2021-07-08 | 2021-07-09 | 2021-07-10 | 2021-07-11 | 2021-07-12 | 2021-07-13 | 2021-07-14 | 2021-07-15 | 2021-07-16 | 2021-07-17 | 2021-07-18 | 2021-07-19 | 2021-07-20 | 2021-07-21 | 2021-07-22 | 2021-07-23 | 2021-07-24 | 2021-07-25 | 2021-07-26 | 2021-07-27 | 2021-07-28 | 2021-07-29 | 2021-07-30 | 2021-07-31 | Total
SM-A |  | Vol. Target | Monthly Plan Vol. | Remain
| Unit | 160000 |  | 160000
| WD SM B1 (S/P AL-61) | [34 empty] | 0
| Unit | -32203.3775 |  | -32203.3775
| SM AW | [34 empty] | 0
| Unit | 0 | 100000 | 0
| SM-AW | [34 empty] | 0
| Unit | 0 |  | 0
| WD SM B2 | [34 empty] | 0
Total |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2021-08-01
Class | Pit | Volume |  |  | 2021-08-01 | 2021-08-02 | 2021-08-03 | 2021-08-04 | 2021-08-05 | 2021-08-06 | 2021-08-07 | 2021-08-08 | 2021-08-09 | 2021-08-10 | 2021-08-11 | 2021-08-12 | 2021-08-13 | 2021-08-14 | 2021-08-15 | 2021-08-16 | 2021-08-17 | 2021-08-18 | 2021-08-19 | 2021-08-20 | 2021-08-21 | 2021-08-22 | 2021-08-23 | 2021-08-24 | 2021-08-25 | 2021-08-26 | 2021-08-27 | 2021-08-28 | 2021-08-29 | 2021-08-30 | 2021-08-31 | Total
SM-A |  | Vol. Target | Monthly Plan Vol. | Remain
| Unit | 160000 |  | 160000
| WD SM B1 (S/P AL-61) | [34 empty] | 0
| Unit | -32203.3775 |  | -32203.3775
| SM AW | [34 empty] | 0
| Unit | 0 | 100000 | 0
| SM-AW | [34 empty] | 0
| Unit | 0 |  | 0
| WD SM B2 | [34 empty] | 0
Total |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2021-09-01
Class | Pit | Volume |  |  | 2021-09-01 | 2021-09-02 | 2021-09-03 | 2021-09-04 | 2021-09-05 | 2021-09-06 | 2021-09-07 | 2021-09-08 | 2021-09-09 | 2021-09-10 | 2021-09-11 | 2021-09-12 | 2021-09-13 | 2021-09-14 | 2021-09-15 | 2021-09-16 | 2021-09-17 | 2021-09-18 | 2021-09-19 | 2021-09-20 | 2021-09-21 | 2021-09-22 | 2021-09-23 | 2021-09-24 | 2021-09-25 | 2021-09-26 | 2021-09-27 | 2021-09-28 | 2021-09-29 | 2021-09-30 | 2021-10-01 | Total
SM-A |  | Vol. Target | Monthly Plan Vol. | Remain
| Unit | 160000 |  | 160000
| WD SM B1 (S/P AL-61) | [34 empty] | 0
| Unit | -32203.3775 |  | -32203.3775
| SM AW | [34 empty] | 0
| Unit | 0 | 100000 | 0
| SM-AW | [34 empty] | 0
| Unit | 0 |  | 0
| WD SM B2 | [34 empty] | 0
Total |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2021-10-01
Class | Pit | Volume |  |  | 2021-10-01 | 2021-10-02 | 2021-10-03 | 2021-10-04 | 2021-10-05 | 2021-10-06 | 2021-10-07 | 2021-10-08 | 2021-10-09 | 2021-10-10 | 2021-10-11 | 2021-10-12 | 2021-10-13 | 2021-10-14 | 2021-10-15 | 2021-10-16 | 2021-10-17 | 2021-10-18 | 2021-10-19 | 2021-10-20 | 2021-10-21 | 2021-10-22 | 2021-10-23 | 2021-10-24 | 2021-10-25 | 2021-10-26 | 2021-10-27 | 2021-10-28 | 2021-10-29 | 2021-10-30 | 2021-10-31 | Total
SM-A |  | Vol. Target | Monthly Plan Vol. | Remain
| Unit | 160000 |  | 160000
| WD SM B1 (S/P AL-61) | [34 empty] | 0
| Unit | -32203.3775 |  | -32203.3775
| SM AW | [34 empty] | 0
| Unit | 0 | 100000 | 0
| SM-AW | [34 empty] | 0
| Unit | 0 |  | 0
| WD SM B2 | [34 empty] | 0
Total |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2021-11-01
Class | Pit | Volume |  |  | 2021-11-01 | 2021-11-02 | 2021-11-03 | 2021-11-04 | 2021-11-05 | 2021-11-06 | 2021-11-07 | 2021-11-08 | 2021-11-09 | 2021-11-10 | 2021-11-11 | 2021-11-12 | 2021-11-13 | 2021-11-14 | 2021-11-15 | 2021-11-16 | 2021-11-17 | 2021-11-18 | 2021-11-19 | 2021-11-20 | 2021-11-21 | 2021-11-22 | 2021-11-23 | 2021-11-24 | 2021-11-25 | 2021-11-26 | 2021-11-27 | 2021-11-28 | 2021-11-29 | 2021-11-30 | 2021-12-01 | Total
SM-A |  | Vol. Target | Monthly Plan Vol. | Remain
| Unit | 160000 |  | 160000
| WD SM B1 (S/P AL-61) | [34 empty] | 0
| Unit | -32203.3775 |  | -32203.3775
| SM AW | [34 empty] | 0
| Unit | 0 | 100000 | 0
| SM-AW | [34 empty] | 0
| Unit | 0 |  | 0
| WD SM B2 | [34 empty] | 0
Total |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2021-12-01
Class | Pit | Volume |  |  | 2021-12-01 | 2021-12-02 | 2021-12-03 | 2021-12-04 | 2021-12-05 | 2021-12-06 | 2021-12-07 | 2021-12-08 | 2021-12-09 | 2021-12-10 | 2021-12-11 | 2021-12-12 | 2021-12-13 | 2021-12-14 | 2021-12-15 | 2021-12-16 | 2021-12-17 | 2021-12-18 | 2021-12-19 | 2021-12-20 | 2021-12-21 | 2021-12-22 | 2021-12-23 | 2021-12-24 | 2021-12-25 | 2021-12-26 | 2021-12-27 | 2021-12-28 | 2021-12-29 | 2021-12-30 | 2021-12-31 | Total
SM-A |  | Vol. Target | Monthly Plan Vol. | Remain
| Unit | 160000 |  | 160000
| WD SM B1 (S/P AL-61) | [34 empty] | 0
| Unit | -32203.3775 |  | -32203.3775
| SM AW | [34 empty] | 0
| Unit | 0 | 100000 | 0
| SM-AW | [34 empty] | 0
| Unit | 0 |  | 0
| WD SM B2 | [34 empty] | 0
Total |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## Outpit-PAMA
■ Hasil Loading Lumpur
2021-01-01
Class | Pit | Volume |  |  | 2021-01-01 | 2021-01-02 | 2021-01-03 | 2021-01-04 | 2021-01-05 | 2021-01-06 | 2021-01-07 | 2021-01-08 | 2021-01-09 | 2021-01-10 | 2021-01-11 | 2021-01-12 | 2021-01-13 | 2021-01-14 | 2021-01-15 | 2021-01-16 | 2021-01-17 | 2021-01-18 | 2021-01-19 | 2021-01-20 | 2021-01-21 | 2021-01-22 | 2021-01-23 | 2021-01-24 | 2021-01-25 | 2021-01-26 | 2021-01-27 | 2021-01-28 | 2021-01-29 | 2021-01-30 | 2021-01-31 | Total
RTS |  | Vol. Target | Monthly Plan Vol. | Remain
| Unit | 400000 |  | 400000
| CB 7B | [34 empty] | 0
Unit
| EX S/Pond Temporary | [34 empty] | 0
Unit
| S/Pond D2 CB | [34 empty] | 0
Unit
| Sump C4 | [34 empty] | 0
Total |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2021-02-01
Class | Pit | Volume |  |  | 2021-02-01 | 2021-02-02 | 2021-02-03 | 2021-02-04 | 2021-02-05 | 2021-02-06 | 2021-02-07 | 2021-02-08 | 2021-02-09 | 2021-02-10 | 2021-02-11 | 2021-02-12 | 2021-02-13 | 2021-02-14 | 2021-02-15 | 2021-02-16 | 2021-02-17 | 2021-02-18 | 2021-02-19 | 2021-02-20 | 2021-02-21 | 2021-02-22 | 2021-02-23 | 2021-02-24 | 2021-02-25 | 2021-02-26 | 2021-02-27 | 2021-02-28 | 2021-03-01 | 2021-03-02 | 2021-03-03 | Total
RTS |  | Vol. Target | Monthly Plan Vol. | Remain
| Unit | 400000 |  | 400000
| CB 7B | [34 empty] | 0
| Unit | 0 |  | 0
| EX S/Pond Temporary | [34 empty] | 0
| Unit | 0 |  | 0
| S/Pond D2 CB | [34 empty] | 0
| Unit | 0 |  | 0
| Sump C4 | [34 empty] | 0
Total |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2021-03-01
Class | Pit | Volume |  |  | 2021-03-01 | 2021-03-02 | 2021-03-03 | 2021-03-04 | 2021-03-05 | 2021-03-06 | 2021-03-07 | 2021-03-08 | 2021-03-09 | 2021-03-10 | 2021-03-11 | 2021-03-12 | 2021-03-13 | 2021-03-14 | 2021-03-15 | 2021-03-16 | 2021-03-17 | 2021-03-18 | 2021-03-19 | 2021-03-20 | 2021-03-21 | 2021-03-22 | 2021-03-23 | 2021-03-24 | 2021-03-25 | 2021-03-26 | 2021-03-27 | 2021-03-28 | 2021-03-29 | 2021-03-30 | 2021-03-31 | Total
RTS |  | Vol. Target | Monthly Plan Vol. | Remain
| Unit | 400000 | 112934 | 329040 | 1XPC2000 | 1XPC2000 | 1XPC2000 | 1XPC2000 | 1XPC2000 | 1XPC2000 |  |  | 1XPC2000 | 1XPC2000 | 1XPC2000 | 1XPC2000 | 1XPC2000 | 1XPC2000 | 1XPC2000 | 1XPC2000 | 1XPC2000 |  |  |  | 1XPC2000 | 1XPC2000 | 1XPC2000 | 1XPC2000 | 1XPC2000 | 1XPC2000 | 1XPC2000 | 1XPC2000 | 1XPC2000 | 1XPC2000 | 1XPC2000
| CB 7B |  |  |  | 2780 | 3280 | 4920 | 940 | 3760 | 2700 | 0 | 0 | 1640 | 1840 | 3300 | 2000 | 2880 | 140 | 2020 | 4120 | 240 | 0 | 0 | 0 | 1480 | 1820 | 4120 | 2820 | 5140 | 1340 | 920 | 2940 | 5040 | 5280 | 3500 | 70960
| Unit | 0 |  | 0
| EX S/Pond Temporary | [34 empty] | 0
| Unit | 0 |  | 0
| S/Pond D2 CB | [34 empty] | 0
| Unit | 0 |  | 0
| Sump C4 | [34 empty] | 0
Total |  |  |  |  | 2780 | 3280 | 4920 | 940 | 3760 | 2700 | 0 | 0 | 1640 | 1840 | 3300 | 2000 | 2880 | 140 | 2020 | 4120 | 240 | 0 | 0 | 0 | 1480 | 1820 | 4120 | 2820 | 5140 | 1340 | 920 | 2940 | 5040 | 5280 | 3500 | 70960
2021-04-01
Class | Pit | Volume |  |  | 2021-04-01 | 2021-04-02 | 2021-04-03 | 2021-04-04 | 2021-04-05 | 2021-04-06 | 2021-04-07 | 2021-04-08 | 2021-04-09 | 2021-04-10 | 2021-04-11 | 2021-04-12 | 2021-04-13 | 2021-04-14 | 2021-04-15 | 2021-04-16 | 2021-04-17 | 2021-04-18 | 2021-04-19 | 2021-04-20 | 2021-04-21 | 2021-04-22 | 2021-04-23 | 2021-04-24 | 2021-04-25 | 2021-04-26 | 2021-04-27 | 2021-04-28 | 2021-04-29 | 2021-04-30 | 2021-05-01 | Total
RTS |  | Vol. Target | Monthly Plan Vol. | Remain
| Unit | 329040 | 105392 | 312580 | 2021-04-01: 1XPC2000; 2021-04-02: 1XPC2000; 2021-04-03: 1XPC2000; 2021-04-04: 1XPC2000; 2021-04-05: 1XPC2000; 2021-04-06: 1XPC2000; 2021-04-07: 1XPC2000
| CB 7B |  |  |  | 2021-04-01: 1280; 2021-04-02: 3560; 2021-04-03: 3160; 2021-04-04: 0; 2021-04-05: 6280; 2021-04-06: 2140; 2021-04-07: 40; 2021-04-08: 0; 2021-04-09: 0; 2021-04-10: 0; 2021-04-11: 0; 2021-04-12: 0; 2021-04-13: 0; 2021-04-14: 0; 2021-04-15: 0; 2021-04-16: 0; 2021-04-17: 0 | 16460
| Unit | 0 |  | 0
| EX S/Pond Temporary | [34 empty] | 0
| Unit | 0 |  | 0 | bar: 2021-04-01 to 2021-04-06
| S/Pond D2 CB | [34 empty] | 0
| Unit | 0 |  | 0
| Sump C4 | [34 empty] | 0
Total |  |  |  |  | 1280 | 3560 | 3160 | 0 | 6280 | 2140 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16460
2021-05-01
Class | Pit | Volume |  |  | 2021-05-01 | 2021-05-02 | 2021-05-03 | 2021-05-04 | 2021-05-05 | 2021-05-06 | 2021-05-07 | 2021-05-08 | 2021-05-09 | 2021-05-10 | 2021-05-11 | 2021-05-12 | 2021-05-13 | 2021-05-14 | 2021-05-15 | 2021-05-16 | 2021-05-17 | 2021-05-18 | 2021-05-19 | 2021-05-20 | 2021-05-21 | 2021-05-22 | 2021-05-23 | 2021-05-24 | 2021-05-25 | 2021-05-26 | 2021-05-27 | 2021-05-28 | 2021-05-29 | 2021-05-30 | 2021-05-31 | Total
RTS |  | Vol. Target | Monthly Plan Vol. | Remain
| Unit | 312580 | 148736 | 250460 | 2021-05-11: 1PC2000; 2021-05-12: 1PC2000; 2021-05-13: 1PC2000; 2021-05-14: 1PC2000; 2021-05-15: 1PC2000; 2021-05-16: 1PC2000; 2021-05-17: 1PC2000; 2021-05-18: 1PC2000; 2021-05-19: 1PC2000; 2021-05-20: 1PC2000; 2021-05-21: 1PC2000; 2021-05-22: 1PC2000; 2021-05-23: 1PC2000; 2021-05-24: 1PC2000; 2021-05-25: 1PC2000; 2021-05-26: 1PC2000; 2021-05-27: 1PC2000
| CB 7B |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2720 | 4980 | 4680 | 5860 | 5760 | 5820 | 3560 | 920 | 4400 | 2800 | 6180 | 3860 | 2720 | 1100 | 2640 | 2720 | 1400 |  |  |  |  | 62120
| Unit | 0 |  | 0
| EX S/Pond Temporary | [34 empty] | 0
| Unit | 0 | 55000 | 0
| S/Pond D2 CB | [34 empty] | 0
| Unit | 0 |  | 0
| Sump C4 | [34 empty] | 0
Total |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2720 | 4980 | 4680 | 5860 | 5760 | 5820 | 3560 | 920 | 4400 | 2800 | 6180 | 3860 | 2720 | 1100 | 2640 | 2720 | 1400 | 0 | 0 | 0 | 0 | 62120
2021-06-01
Class | Pit | Volume |  |  | 2021-06-01 | 2021-06-02 | 2021-06-03 | 2021-06-04 | 2021-06-05 | 2021-06-06 | 2021-06-07 | 2021-06-08 | 2021-06-09 | 2021-06-10 | 2021-06-11 | 2021-06-12 | 2021-06-13 | 2021-06-14 | 2021-06-15 | 2021-06-16 | 2021-06-17 | 2021-06-18 | 2021-06-19 | 2021-06-20 | 2021-06-21 | 2021-06-22 | 2021-06-23 | 2021-06-24 | 2021-06-25 | 2021-06-26 | 2021-06-27 | 2021-06-28 | 2021-06-29 | 2021-06-30 | 2021-07-01 | Total
RTS |  | Vol. Target | Monthly Plan Vol. | Remain
| Unit | 250460 | 32938 | 250460
| CB 7B | [34 empty] | 0
| Unit | 0 |  | 0
| EX S/Pond Temporary | [34 empty] | 0
| Unit | 0 |  | 0
| S/Pond D2 CB | [34 empty] | 0
| Unit | 0 |  | 0
| Sump C4 | [34 empty] | 0
Total |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2021-07-01
Class | Pit | Volume |  |  | 2021-07-01 | 2021-07-02 | 2021-07-03 | 2021-07-04 | 2021-07-05 | 2021-07-06 | 2021-07-07 | 2021-07-08 | 2021-07-09 | 2021-07-10 | 2021-07-11 | 2021-07-12 | 2021-07-13 | 2021-07-14 | 2021-07-15 | 2021-07-16 | 2021-07-17 | 2021-07-18 | 2021-07-19 | 2021-07-20 | 2021-07-21 | 2021-07-22 | 2021-07-23 | 2021-07-24 | 2021-07-25 | 2021-07-26 | 2021-07-27 | 2021-07-28 | 2021-07-29 | 2021-07-30 | 2021-07-31 | Total
RTS |  | Vol. Target | Monthly Plan Vol. | Remain
| Unit | 250460 |  | 250460
| CB 7B | [34 empty] | 0
| Unit | 0 |  | 0
| EX S/Pond Temporary | [34 empty] | 0
| Unit | 0 |  | 0
| S/Pond D2 CB | [34 empty] | 0
| Unit | 0 |  | 0
| Sump C4 | [34 empty] | 0
Total |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2021-08-01
Class | Pit | Volume |  |  | 2021-08-01 | 2021-08-02 | 2021-08-03 | 2021-08-04 | 2021-08-05 | 2021-08-06 | 2021-08-07 | 2021-08-08 | 2021-08-09 | 2021-08-10 | 2021-08-11 | 2021-08-12 | 2021-08-13 | 2021-08-14 | 2021-08-15 | 2021-08-16 | 2021-08-17 | 2021-08-18 | 2021-08-19 | 2021-08-20 | 2021-08-21 | 2021-08-22 | 2021-08-23 | 2021-08-24 | 2021-08-25 | 2021-08-26 | 2021-08-27 | 2021-08-28 | 2021-08-29 | 2021-08-30 | 2021-08-31 | Total
RTS |  | Vol. Target | Monthly Plan Vol. | Remain
| Unit | 250460 |  | 250460
| CB 7B |  |  |  | 2021-08-19: 0; 2021-08-20: 0; 2021-08-21: 0; 2021-08-22: 0; 2021-08-23: 0; 2021-08-24: 0; 2021-08-25: 0; 2021-08-26: 0; 2021-08-27: 0; 2021-08-28: 0; 2021-08-29: 0; 2021-08-30: 0; 2021-08-31: 0 | 0
| Unit | 0 |  | 0
| EX S/Pond Temporary | [34 empty] | 0
| Unit | 0 |  | 0
| S/Pond D2 CB | [34 empty] | 0
| Unit | 0 |  | 0 | bar: 2021-08-01 to 2021-08-27
| Sump C4 | [34 empty] | 0
Total |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2021-09-01
Class | Pit | Volume |  |  | 2021-09-01 | 2021-09-02 | 2021-09-03 | 2021-09-04 | 2021-09-05 | 2021-09-06 | 2021-09-07 | 2021-09-08 | 2021-09-09 | 2021-09-10 | 2021-09-11 | 2021-09-12 | 2021-09-13 | 2021-09-14 | 2021-09-15 | 2021-09-16 | 2021-09-17 | 2021-09-18 | 2021-09-19 | 2021-09-20 | 2021-09-21 | 2021-09-22 | 2021-09-23 | 2021-09-24 | 2021-09-25 | 2021-09-26 | 2021-09-27 | 2021-09-28 | 2021-09-29 | 2021-09-30 | 2021-10-01 | Total
RTS |  | Vol. Target | Monthly Plan Vol. | Remain
| Unit | 55000 |  | 55000 | bar: 2021-09-10 to 2021-09-11
| 7B Control Box | [34 empty] | 0
| Unit | 0 |  | 0
| EX S/Pond Temporary | [34 empty] | 0
| Unit | 0 |  | 0
| S/Pond D2 CB | [34 empty] | 0
| Unit | 0 |  | 0 | bar: 2021-09-01 to 2021-09-16
| Sump C4 | [34 empty] | 0
Total |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2021-10-01
Class | Pit | Volume |  |  | 2021-10-01 | 2021-10-02 | 2021-10-03 | 2021-10-04 | 2021-10-05 | 2021-10-06 | 2021-10-07 | 2021-10-08 | 2021-10-09 | 2021-10-10 | 2021-10-11 | 2021-10-12 | 2021-10-13 | 2021-10-14 | 2021-10-15 | 2021-10-16 | 2021-10-17 | 2021-10-18 | 2021-10-19 | 2021-10-20 | 2021-10-21 | 2021-10-22 | 2021-10-23 | 2021-10-24 | 2021-10-25 | 2021-10-26 | 2021-10-27 | 2021-10-28 | 2021-10-29 | 2021-10-30 | 2021-10-31 | Total
RTS |  | Vol. Target | Monthly Plan Vol. | Remain
| Unit | 55000 |  | 55000
| 7B Control Box | [34 empty] | 0
| Unit | 0 |  | 0
| EX S/Pond Temporary | [34 empty] | 0
| Unit | 0 |  | 0
| S/Pond D2 CB | [34 empty] | 0
| Unit | 0 |  | 0
| Sump C4 | [34 empty] | 0
Total |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2021-11-01
Class | Pit | Volume |  |  | 2021-11-01 | 2021-11-02 | 2021-11-03 | 2021-11-04 | 2021-11-05 | 2021-11-06 | 2021-11-07 | 2021-11-08 | 2021-11-09 | 2021-11-10 | 2021-11-11 | 2021-11-12 | 2021-11-13 | 2021-11-14 | 2021-11-15 | 2021-11-16 | 2021-11-17 | 2021-11-18 | 2021-11-19 | 2021-11-20 | 2021-11-21 | 2021-11-22 | 2021-11-23 | 2021-11-24 | 2021-11-25 | 2021-11-26 | 2021-11-27 | 2021-11-28 | 2021-11-29 | 2021-11-30 | 2021-12-01 | Total
RTS |  | Vol. Target | Monthly Plan Vol. | Remain
| Unit | 55000 |  | 55000
| 7B Control Box | [34 empty] | 0
| Unit | 0 |  | 0
| EX S/Pond Temporary | [34 empty] | 0
| Unit | 0 |  | 0
| S/Pond D2 CB | [34 empty] | 0
| Unit | 0 |  | 0
| Sump C4 | [34 empty] | 0
Total |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2021-12-01
Class | Pit | Volume |  |  | 2021-12-01 | 2021-12-02 | 2021-12-03 | 2021-12-04 | 2021-12-05 | 2021-12-06 | 2021-12-07 | 2021-12-08 | 2021-12-09 | 2021-12-10 | 2021-12-11 | 2021-12-12 | 2021-12-13 | 2021-12-14 | 2021-12-15 | 2021-12-16 | 2021-12-17 | 2021-12-18 | 2021-12-19 | 2021-12-20 | 2021-12-21 | 2021-12-22 | 2021-12-23 | 2021-12-24 | 2021-12-25 | 2021-12-26 | 2021-12-27 | 2021-12-28 | 2021-12-29 | 2021-12-30 | 2021-12-31 | Total
RTS |  | Vol. Target | Monthly Plan Vol. | Remain
| Unit | 55000 |  | 55000
| 7B Control Box | [34 empty] | 0
| Unit | 0 |  | 0
| EX S/Pond Temporary | [34 empty] | 0
| Unit | 0 |  | 0
| S/Pond D2 CB | [34 empty] | 0
| Unit | 0 |  | 0
| Sump C4 | [34 empty] | 0
Total |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## Outpit-Bima
■ Hasil Loading Lumpur
2021-01-01
Class | Pit | Volume |  |  | 2021-01-01 | 2021-01-02 | 2021-01-03 | 2021-01-04 | 2021-01-05 | 2021-01-06 | 2021-01-07 | 2021-01-08 | 2021-01-09 | 2021-01-10 | 2021-01-11 | 2021-01-12 | 2021-01-13 | 2021-01-14 | 2021-01-15 | 2021-01-16 | 2021-01-17 | 2021-01-18 | 2021-01-19 | 2021-01-20 | 2021-01-21 | 2021-01-22 | 2021-01-23 | 2021-01-24 | 2021-01-25 | 2021-01-26 | 2021-01-27 | 2021-01-28 | 2021-01-29 | 2021-01-30 | 2021-01-31 | Total
SSB |  | Vol. Target | Monthly Plan Vol. | Remain
| Unit | 25000 |  | 25000
| S/Pond AL-SSB02 | [34 empty] | 0
| Unit | 3000 |  | 3000
| S/Pond AL-SSB03 | [34 empty] | 0
| Unit | 4000 |  | 4000
| S/Pond AL-SSB04 | [34 empty] | 0
| Unit | 7000 |  | 7000
| S/Pond AL-SSB05 | [34 empty] | 0
| Unit | 15000 |  | 15000
| S/Pond AL-SSB06 | [34 empty] | 0
| Unit | 7846 |  | 7846
| Control Box AL-SSB02 | [34 empty] | 0
| Unit | 14704 |  | 14704
| Control Box AL-SSB07 | [34 empty] | 0
0
0
RTM | Unit |  |  | 0
| S/Pond AB 03 | [34 empty] | 0
RTS-F | Unit |  |  | 0
| S/Pond AL 54 | [34 empty] | 0
| Unit |  |  | 0
| S/Pond AL 59 | [34 empty] | 0
RTS-G | Unit |  |  | 0
| S/Pond AL 66 | [34 empty] | 0
SMA | Unit |  |  | 0
| S/Pond AL 28 | [34 empty] | 0
| Unit |  |  | 0
| S/Pond AL 57 | [34 empty] | 0
SMB | Unit |  |  | 0
| S/Pond AL 55 | [34 empty] | 0
| Unit |  |  | 0
| S/Pond AL 56 | [34 empty] | 0
Total |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2021-02-01
Class | Pit | Volume |  |  | 2021-02-01 | 2021-02-02 | 2021-02-03 | 2021-02-04 | 2021-02-05 | 2021-02-06 | 2021-02-07 | 2021-02-08 | 2021-02-09 | 2021-02-10 | 2021-02-11 | 2021-02-12 | 2021-02-13 | 2021-02-14 | 2021-02-15 | 2021-02-16 | 2021-02-17 | 2021-02-18 | 2021-02-19 | 2021-02-20 | 2021-02-21 | 2021-02-22 | 2021-02-23 | 2021-02-24 | 2021-02-25 | 2021-02-26 | 2021-02-27 | 2021-02-28 | 2021-03-01 | 2021-03-02 | 2021-03-03 | Total
SSB |  | Vol. Target | Monthly Plan Vol. | Remain
| Unit | 25000 |  | 25000
| S/Pond AL-SSB02 | [34 empty] | 0
| Unit | 3000 |  | 3000
| S/Pond AL-SSB03 | [34 empty] | 0
| Unit | 4000 |  | 4000
| S/Pond AL-SSB04 | [34 empty] | 0
| Unit | 7000 |  | 7000
| S/Pond AL-SSB05 | [34 empty] | 0
| Unit | 15000 |  | 15000
| S/Pond AL-SSB06 | [34 empty] | 0
| Unit | 7846 |  | 7846
| Control Box AL-SSB02 | [34 empty] | 0
| Unit | 14704 |  | 14704
| Control Box AL-SSB07 | [34 empty] | 0
| Unit | 0 |  | 0
| 0 | [34 empty] | 0
RTM | Unit | 0 |  | 0
| S/Pond AB 03 | [34 empty] | 0
RTS-F | Unit | 0 |  | 0
| S/Pond AL 54 | [34 empty] | 0
| Unit | 0 |  | 0
| S/Pond AL 59 | [34 empty] | 0
RTS-G | Unit | 0 |  | 0
| S/Pond AL 66 | [34 empty] | 0
SMA | Unit | 0 |  | 0
| S/Pond AL 28 | [34 empty] | 0
| Unit | 0 |  | 0
| S/Pond AL 57 | [34 empty] | 0
SMB | Unit | 0 |  | 0
| S/Pond AL 55 | [34 empty] | 0
| Unit | 0 |  | 0
| S/Pond AL 56 | [34 empty] | 0
Total |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2021-03-01
Class | Pit | Volume |  |  | 2021-03-01 | 2021-03-02 | 2021-03-03 | 2021-03-04 | 2021-03-05 | 2021-03-06 | 2021-03-07 | 2021-03-08 | 2021-03-09 | 2021-03-10 | 2021-03-11 | 2021-03-12 | 2021-03-13 | 2021-03-14 | 2021-03-15 | 2021-03-16 | 2021-03-17 | 2021-03-18 | 2021-03-19 | 2021-03-20 | 2021-03-21 | 2021-03-22 | 2021-03-23 | 2021-03-24 | 2021-03-25 | 2021-03-26 | 2021-03-27 | 2021-03-28 | 2021-03-29 | 2021-03-30 | 2021-03-31 | Total
SSB |  | Vol. Target | Monthly Plan Vol. | Remain
| Unit | 25000 |  | 25000
S/Pond AL-SSB02
| Unit | 3000 |  | 3000
| S/Pond AL-SSB03 | [34 empty] | 0
| Unit | 4000 |  | 4000
| S/Pond AL-SSB04 | [34 empty] | 0
| Unit | 7000 |  | 7000
| S/Pond AL-SSB05 | [34 empty] | 0
| Unit | 15000 |  | 15000
| S/Pond AL-SSB06 | [34 empty] | 0
| Unit | 7846 |  | 7846
| Control Box AL-SSB02 | [34 empty] | 0
| Unit | 14704 |  | 14704
| Control Box AL-SSB07 | [34 empty] | 0
| Unit | 0 |  | 0
| 0 | [34 empty] | 0
RTM | Unit | 0 |  | 0
| S/Pond AB 03 | [34 empty] | 0
RTS-F | Unit | 0 |  | 0
| S/Pond AL 54 | [34 empty] | 0
| Unit | 0 |  | 0
| S/Pond AL 59 | [34 empty] | 0
RTS-G | Unit | 0 |  | 0
| S/Pond AL 66 | [34 empty] | 0
SMA | Unit | 0 |  | 0
| S/Pond AL 28 | [34 empty] | 0
| Unit | 0 |  | 0
| S/Pond AL 57 | [34 empty] | 0
SMB | Unit | 0 |  | 0
| S/Pond AL 55 | [34 empty] | 0
| Unit | 0 |  | 0
| S/Pond AL 56 | [34 empty] | 0
Total |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2021-04-01
Class | Pit | Volume |  |  | 2021-04-01 | 2021-04-02 | 2021-04-03 | 2021-04-04 | 2021-04-05 | 2021-04-06 | 2021-04-07 | 2021-04-08 | 2021-04-09 | 2021-04-10 | 2021-04-11 | 2021-04-12 | 2021-04-13 | 2021-04-14 | 2021-04-15 | 2021-04-16 | 2021-04-17 | 2021-04-18 | 2021-04-19 | 2021-04-20 | 2021-04-21 | 2021-04-22 | 2021-04-23 | 2021-04-24 | 2021-04-25 | 2021-04-26 | 2021-04-27 | 2021-04-28 | 2021-04-29 | 2021-04-30 | 2021-05-01 | Total
SSB |  | Vol. Target | Monthly Plan Vol. | Remain
| Unit | 25000 |  | 25000
S/Pond AL-SSB02
| Unit | 3000 |  | 3000
| S/Pond AL-SSB03 | [34 empty] | 0
| Unit | 4000 |  | 4000
| S/Pond AL-SSB04 | [34 empty] | 0
| Unit | 7000 |  | 7000
| S/Pond AL-SSB05 | [34 empty] | 0
| Unit | 15000 |  | 15000
| S/Pond AL-SSB06 | [34 empty] | 0
| Unit | 7846 |  | 7846
| Control Box AL-SSB02 | [34 empty] | 0
| Unit | 14704 |  | 14704
| Control Box AL-SSB07 | [34 empty] | 0
| Unit | 0 |  | 0
| 0 | [34 empty] | 0
RTM | Unit | 0 |  | 0
| S/Pond AB 03 | [34 empty] | 0
RTS-F | Unit | 0 |  | 0
| S/Pond AL 54 | [34 empty] | 0
| Unit | 0 |  | 0
| S/Pond AL 59 | [34 empty] | 0
RTS-G | Unit | 0 |  | 0
| S/Pond AL 66 | [34 empty] | 0
SMA | Unit | 0 |  | 0
| S/Pond AL 28 | [34 empty] | 0
| Unit | 0 |  | 0
| S/Pond AL 57 | [34 empty] | 0
SMB | Unit | 0 |  | 0
| S/Pond AL 55 | [34 empty] | 0
| Unit | 0 |  | 0
| S/Pond AL 56 | [34 empty] | 0
Total |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2021-05-01
Class | Pit | Volume |  |  | 2021-05-01 | 2021-05-02 | 2021-05-03 | 2021-05-04 | 2021-05-05 | 2021-05-06 | 2021-05-07 | 2021-05-08 | 2021-05-09 | 2021-05-10 | 2021-05-11 | 2021-05-12 | 2021-05-13 | 2021-05-14 | 2021-05-15 | 2021-05-16 | 2021-05-17 | 2021-05-18 | 2021-05-19 | 2021-05-20 | 2021-05-21 | 2021-05-22 | 2021-05-23 | 2021-05-24 | 2021-05-25 | 2021-05-26 | 2021-05-27 | 2021-05-28 | 2021-05-29 | 2021-05-30 | 2021-05-31 | Total
SSB |  | Vol. Target | Monthly Plan Vol. | Remain
| Unit | 25000 |  | 25000
S/Pond AL-SSB02
| Unit | 3000 |  | 3000
| S/Pond AL-SSB03 | [34 empty] | 0
| Unit | 4000 |  | 4000
| S/Pond AL-SSB04 | [34 empty] | 0
| Unit | 7000 |  | 7000
| S/Pond AL-SSB05 | [34 empty] | 0
| Unit | 15000 |  | 15000
| S/Pond AL-SSB06 | [34 empty] | 0
| Unit | 7846 |  | 7846
| Control Box AL-SSB02 | [34 empty] | 0
| Unit | 14704 |  | 14704
| Control Box AL-SSB07 | [34 empty] | 0
| Unit | 0 |  | 0
| 0 | [34 empty] | 0
RTS-F | Unit | 0 |  | 0
| S/Pond AL 54 | [34 empty] | 0
| Unit | 0 |  | 0
| S/Pond AL 59 | [34 empty] | 0
RTS-G | Unit | 0 |  | 0
| S/Pond AL 66 | [34 empty] | 0
SMA | Unit | 0 |  | 0
| S/Pond AL 28 | [34 empty] | 0
| Unit | 0 |  | 0
| S/Pond AL 57 | [34 empty] | 0
SMB | Unit | 0 |  | 0
| S/Pond AL 55 | [34 empty] | 0
| Unit | 0 |  | 0
| S/Pond AL 56 | [34 empty] | 0
Total |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2021-06-01
Class | Pit | Volume |  |  | 2021-06-01 | 2021-06-02 | 2021-06-03 | 2021-06-04 | 2021-06-05 | 2021-06-06 | 2021-06-07 | 2021-06-08 | 2021-06-09 | 2021-06-10 | 2021-06-11 | 2021-06-12 | 2021-06-13 | 2021-06-14 | 2021-06-15 | 2021-06-16 | 2021-06-17 | 2021-06-18 | 2021-06-19 | 2021-06-20 | 2021-06-21 | 2021-06-22 | 2021-06-23 | 2021-06-24 | 2021-06-25 | 2021-06-26 | 2021-06-27 | 2021-06-28 | 2021-06-29 | 2021-06-30 | 2021-07-01 | Total
SSB |  | Vol. Target | Monthly Plan Vol. | Remain
| Unit | 25000 |  | 25000
S/Pond AL-SSB02
| Unit | 3000 |  | 3000
| S/Pond AL-SSB03 | [34 empty] | 0
| Unit | 4000 |  | 4000
| S/Pond AL-SSB04 | [34 empty] | 0
| Unit | 7000 |  | 7000
| S/Pond AL-SSB05 | [34 empty] | 0
| Unit | 15000 |  | 15000
| S/Pond AL-SSB06 | [34 empty] | 0
| Unit | 7846 |  | 7846
| Control Box AL-SSB02 | [34 empty] | 0
| Unit | 14704 |  | 14704
| Control Box AL-SSB07 | [34 empty] | 0
| Unit | 0 |  | 0
| 0 | [34 empty] | 0
RTS-F | Unit | 0 |  | 0
| S/Pond AL 54 | [34 empty] | 0
| Unit | 0 |  | 0
| S/Pond AL 59 | [34 empty] | 0
RTS-G | Unit | 0 |  | 0
| S/Pond AL 66 | [34 empty] | 0
SMA | Unit | 0 |  | 0
| S/Pond AL 28 | [34 empty] | 0
| Unit | 0 |  | 0
| S/Pond AL 57 | [34 empty] | 0
SMB | Unit | 0 |  | 0
| S/Pond AL 55 | [34 empty] | 0
| Unit | 0 |  | 0
| S/Pond AL 56 | [34 empty] | 0
Total |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2021-07-01
Class | Pit | Volume |  |  | 2021-07-01 | 2021-07-02 | 2021-07-03 | 2021-07-04 | 2021-07-05 | 2021-07-06 | 2021-07-07 | 2021-07-08 | 2021-07-09 | 2021-07-10 | 2021-07-11 | 2021-07-12 | 2021-07-13 | 2021-07-14 | 2021-07-15 | 2021-07-16 | 2021-07-17 | 2021-07-18 | 2021-07-19 | 2021-07-20 | 2021-07-21 | 2021-07-22 | 2021-07-23 | 2021-07-24 | 2021-07-25 | 2021-07-26 | 2021-07-27 | 2021-07-28 | 2021-07-29 | 2021-07-30 | 2021-07-31 | Total
SSB |  | Vol. Target | Monthly Plan Vol. | Remain
| Unit | 25000 |  | 25000
S/Pond AL-SSB02
| Unit | 3000 |  | 3000
| S/Pond AL-SSB03 | [34 empty] | 0
| Unit | 4000 |  | 4000
| S/Pond AL-SSB04 | [34 empty] | 0
| Unit | 7000 |  | 7000
| S/Pond AL-SSB05 | [34 empty] | 0
| Unit | 15000 |  | 15000
| S/Pond AL-SSB06 | [34 empty] | 0
| Unit | 7846 |  | 7846
| Control Box AL-SSB02 | [34 empty] | 0
| Unit | 14704 |  | 14704
| Control Box AL-SSB07 | [34 empty] | 0
| Unit | 0 |  | 0
| 0 | [34 empty] | 0
Unit
| C/Box AL 02 | [34 empty] | 0
RTS-F | Unit | 0 |  | 0
| S/Pond AL 54 | [34 empty] | 0
| Unit | 0 |  | 0
| S/Pond AL 59 | [34 empty] | 0
RTS-G | Unit | 0 |  | 0
| S/Pond AL 66 | [34 empty] | 0
SMA | Unit | 0 |  | 0
| S/Pond AL 28 | [34 empty] | 0
| Unit | 0 |  | 0
| S/Pond AL 57 | [34 empty] | 0
SMB | Unit | 0 |  | 0
| S/Pond AL 55 | [34 empty] | 0
| Unit | 0 |  | 0
| S/Pond AL 56 | [34 empty] | 0
Total |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2021-08-01
` | Pit | Volume |  |  | 2021-08-01 | 2021-08-02 | 2021-08-03 | 2021-08-04 | 2021-08-05 | 2021-08-06 | 2021-08-07 | 2021-08-08 | 2021-08-09 | 2021-08-10 | 2021-08-11 | 2021-08-12 | 2021-08-13 | 2021-08-14 | 2021-08-15 | 2021-08-16 | 2021-08-17 | 2021-08-18 | 2021-08-19 | 2021-08-20 | 2021-08-21 | 2021-08-22 | 2021-08-23 | 2021-08-24 | 2021-08-25 | 2021-08-26 | 2021-08-27 | 2021-08-28 | 2021-08-29 | 2021-08-30 | 2021-08-31 | Total
SSB |  | Vol. Target | Monthly Plan Vol. | Remain
| Unit | 25000 |  | 25000
| S/Pond AL-SSB02 | [34 empty] | 0
| Unit | 3000 |  | 3000
| S/Pond AL-SSB03 | [34 empty] | 0
| Unit | 4000 |  | 4000
| S/Pond AL-SSB04 | [34 empty] | 0
| Unit | 7000 |  | 7000
| S/Pond AL-SSB05 | [34 empty] | 0
| Unit | 15000 |  | 15000
| S/Pond AL-SSB06 | [34 empty] | 0
| Unit | 7846 |  | 7846
| Control Box AL-SSB02 | [34 empty] | 0
| Unit | 14704 |  | 14704
| Control Box AL-SSB07 | [34 empty] | 0
| Unit | 0 |  | 0
| 0 | [34 empty] | 0
| Unit | 0 |  | 0 | bar: 2021-08-01 to 2021-08-09; 2021-08-21 to 2021-08-31
| C/Box (SP 02) | [34 empty] | 0
| Unit | 0 |  | 0 | bar: 2021-08-01 to 2021-08-09; 2021-08-15 to 2021-08-21; 2021-08-24 to 2021-08-31
| C/Box (SP 07) | [34 empty] | 0
RTS-F | Unit | 0 |  | 0
| S/Pond AL 54 | [34 empty] | 0
| Unit | 0 |  | 0
| S/Pond AL 59 | [34 empty] | 0
RTS-G | Unit | 0 |  | 0
| S/Pond AL 66 | [34 empty] | 0
SMA | Unit | 0 |  | 0
| S/Pond AL 28 | [34 empty] | 0
| Unit | 0 |  | 0
| S/Pond AL 57 | [34 empty] | 0
SMB | Unit | 0 |  | 0
| S/Pond AL 55 | [34 empty] | 0
| Unit | 0 |  | 0
| S/Pond AL 56 | [34 empty] | 0
Total |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2021-09-01
Class | Pit | Volume |  |  | 2021-09-01 | 2021-09-02 | 2021-09-03 | 2021-09-04 | 2021-09-05 | 2021-09-06 | 2021-09-07 | 2021-09-08 | 2021-09-09 | 2021-09-10 | 2021-09-11 | 2021-09-12 | 2021-09-13 | 2021-09-14 | 2021-09-15 | 2021-09-16 | 2021-09-17 | 2021-09-18 | 2021-09-19 | 2021-09-20 | 2021-09-21 | 2021-09-22 | 2021-09-23 | 2021-09-24 | 2021-09-25 | 2021-09-26 | 2021-09-27 | 2021-09-28 | 2021-09-29 | 2021-09-30 | 2021-10-01 | Total
SSB |  | Vol. Target | Monthly Plan Vol. | Remain
| Unit | 25000 |  | 25000
S/Pond AL-SSB02
| Unit | 3000 |  | 3000
| S/Pond AL-SSB03 | [34 empty] | 0
| Unit | 4000 |  | 4000
| S/Pond AL-SSB04 | [34 empty] | 0
| Unit | 7000 |  | 7000
| S/Pond AL-SSB05 | [34 empty] | 0
| Unit | 15000 |  | 15000
| S/Pond AL-SSB06 | [34 empty] | 0
| Unit | 7846 |  | 7846
| Control Box AL-SSB02 | [34 empty] | 0
| Unit | 14704 |  | 14704
| Control Box AL-SSB07 | [34 empty] | 0
| Unit | 0 |  | 0
| S/Pond AL 07 | [34 empty] | 0
| Unit | 0 |  | 0
| SP 7 C/B 2 | [34 empty] | 0
RTS-F | Unit | 0 |  | 0
| S/Pond AL 54 | [34 empty] | 0
| Unit | 0 |  | 0
| S/Pond AL 59 | [34 empty] | 0
RTS-G | Unit | 0 |  | 0
| S/Pond AL 66 | [34 empty] | 0
RTM | Unit | 0 |  | 0
| S/Pond AL 11 | [34 empty] | 0
SMA | Unit | 0 |  | 0
| S/Pond AL 28 | [34 empty] | 0
| Unit | 0 |  | 0
| S/Pond AL 57 | [34 empty] | 0
SMB | Unit | 0 |  | 0
| S/Pond AL 55 | [34 empty] | 0
| Unit | 0 |  | 0
| S/Pond AL 56 | [34 empty] | 0
Total |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2021-10-01
Class | Pit | Volume |  |  | 2021-10-01 | 2021-10-02 | 2021-10-03 | 2021-10-04 | 2021-10-05 | 2021-10-06 | 2021-10-07 | 2021-10-08 | 2021-10-09 | 2021-10-10 | 2021-10-11 | 2021-10-12 | 2021-10-13 | 2021-10-14 | 2021-10-15 | 2021-10-16 | 2021-10-17 | 2021-10-18 | 2021-10-19 | 2021-10-20 | 2021-10-21 | 2021-10-22 | 2021-10-23 | 2021-10-24 | 2021-10-25 | 2021-10-26 | 2021-10-27 | 2021-10-28 | 2021-10-29 | 2021-10-30 | 2021-10-31 | Total
SSB |  | Vol. Target | Monthly Plan Vol. | Remain
| Unit | 25000 |  | 25000
S/Pond AL-SSB02
| Unit | 3000 |  | 3000
| S/Pond AL-SSB03 | [34 empty] | 0
| Unit | 4000 |  | 4000
| S/Pond AL-SSB04 | [34 empty] | 0
| Unit | 7000 |  | 7000
| S/Pond AL-SSB05 | [34 empty] | 0
| Unit | 15000 |  | 15000
| S/Pond AL-SSB06 | [34 empty] | 0
| Unit | 7846 |  | 7846
| Control Box AL-SSB02 | [34 empty] | 0
| Unit | 14704 |  | 14704
| Control Box AL-SSB07 | [34 empty] | 0
| Unit | 0 |  | 0
| SP 7 C/B 2 | [34 empty] | 0
RTS-F | Unit | 0 |  | 0
| S/Pond AL 54 | [34 empty] | 0
| Unit | 0 |  | 0
| S/Pond AL 59 | [34 empty] | 0
RTS-G | Unit | 0 |  | 0
| S/Pond AL 64 | [34 empty] | 0
| Unit | 0 |  | 0
| S/Pond AL 66 | [34 empty] | 0
RTM | Unit | 0 |  | 0
| S/Pond AL 11 | [34 empty] | 0
SMA | Unit | 0 |  | 0
| S/Pond AL 28 | [34 empty] | 0
| Unit | 0 |  | 0
| S/Pond AL 57 | [34 empty] | 0
SMB | Unit | 0 |  | 0
| S/Pond AL 55 | [34 empty] | 0
| Unit | 0 |  | 0
| S/Pond AL 56 | [34 empty] | 0
Total |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2021-11-01
Class | Pit | Volume |  |  | 2021-11-01 | 2021-11-02 | 2021-11-03 | 2021-11-04 | 2021-11-05 | 2021-11-06 | 2021-11-07 | 2021-11-08 | 2021-11-09 | 2021-11-10 | 2021-11-11 | 2021-11-12 | 2021-11-13 | 2021-11-14 | 2021-11-15 | 2021-11-16 | 2021-11-17 | 2021-11-18 | 2021-11-19 | 2021-11-20 | 2021-11-21 | 2021-11-22 | 2021-11-23 | 2021-11-24 | 2021-11-25 | 2021-11-26 | 2021-11-27 | 2021-11-28 | 2021-11-29 | 2021-11-30 | 2021-12-01 | Total
SSB |  | Vol. Target | Monthly Plan Vol. | Remain
| Unit | 25000 |  | 25000
S/Pond AL-SSB02
| Unit | 3000 |  | 3000
| S/Pond AL-SSB03 | [34 empty] | 0
| Unit | 4000 |  | 4000
| S/Pond AL-SSB04 | [34 empty] | 0
| Unit | 7000 |  | 7000
| S/Pond AL-SSB05 | [34 empty] | 0
| Unit | 15000 |  | 15000
| S/Pond AL-SSB06 | [34 empty] | 0
| Unit | 7846 |  | 7846
| Control Box AL-SSB02 | [34 empty] | 0
| Unit | 14704 |  | 14704
| Control Box AL-SSB07 | [34 empty] | 0
| Unit | 0 |  | 0
| SP 7 C/B 2 | [34 empty] | 0
RTS-F | Unit | 0 |  | 0
| S/Pond AL 54 | [34 empty] | 0
| Unit | 0 |  | 0
| S/Pond AL 59 | [34 empty] | 0
RTS-G | Unit | 0 |  | 0
| S/Pond AL 66 | [34 empty] | 0
RTM | Unit | 0 |  | 0
| S/Pond AL 11 | [34 empty] | 0
SMA | Unit | 0 |  | 0
| S/Pond AL 28 | [34 empty] | 0
| Unit | 0 |  | 0
| S/Pond AL 57 | [34 empty] | 0
SMB | Unit | 0 |  | 0
| S/Pond AL 55 | [34 empty] | 0
| Unit | 0 |  | 0
| S/Pond AL 56 | [34 empty] | 0
Total |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2021-12-01
Class | Pit | Volume |  |  | 2021-12-01 | 2021-12-02 | 2021-12-03 | 2021-12-04 | 2021-12-05 | 2021-12-06 | 2021-12-07 | 2021-12-08 | 2021-12-09 | 2021-12-10 | 2021-12-11 | 2021-12-12 | 2021-12-13 | 2021-12-14 | 2021-12-15 | 2021-12-16 | 2021-12-17 | 2021-12-18 | 2021-12-19 | 2021-12-20 | 2021-12-21 | 2021-12-22 | 2021-12-23 | 2021-12-24 | 2021-12-25 | 2021-12-26 | 2021-12-27 | 2021-12-28 | 2021-12-29 | 2021-12-30 | 2021-12-31 | Total
SSB |  | Vol. Target | Monthly Plan Vol. | Remain
| Unit | 25000 |  | 25000
S/Pond AL-SSB02
| Unit | 3000 |  | 3000
| S/Pond AL-SSB03 | [34 empty] | 0
| Unit | 4000 |  | 4000
| S/Pond AL-SSB04 | [34 empty] | 0
| Unit | 7000 |  | 7000
| S/Pond AL-SSB05 | [34 empty] | 0
| Unit | 15000 |  | 15000
| S/Pond AL-SSB06 | [34 empty] | 0
| Unit | 7846 |  | 7846
| Control Box AL-SSB02 | [34 empty] | 0
| Unit | 14704 |  | 14704
| Control Box AL-SSB07 | [34 empty] | 0
| Unit | 0 |  | 0
| SP 7 C/B 2 | [34 empty] | 0
RTS-F | Unit | 0 |  | 0
| S/Pond AL 54 | [34 empty] | 0
| Unit | 0 |  | 0
| S/Pond AL 59 | [34 empty] | 0
RTS-G | Unit | 0 |  | 0
| S/Pond AL 66 | [34 empty] | 0
SMA | Unit | 0 |  | 0
| S/Pond AL 28 | [34 empty] | 0
| Unit | 0 |  | 0
| S/Pond AL 57 | [34 empty] | 0
SMB | Unit | 0 |  | 0
| S/Pond AL 55 | [34 empty] | 0
| Unit | 0 |  | 0
| S/Pond AL 56 | [34 empty] | 0
Total |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## Outpit-PTP
■ Hasil Loading Lumpur
2021-01-01
Class | Pit | Volume |  |  | 2021-01-01 | 2021-01-02 | 2021-01-03 | 2021-01-04 | 2021-01-05 | 2021-01-06 | 2021-01-07 | 2021-01-08 | 2021-01-09 | 2021-01-10 | 2021-01-11 | 2021-01-12 | 2021-01-13 | 2021-01-14 | 2021-01-15 | 2021-01-16 | 2021-01-17 | 2021-01-18 | 2021-01-19 | 2021-01-20 | 2021-01-21 | 2021-01-22 | 2021-01-23 | 2021-01-24 | 2021-01-25 | 2021-01-26 | 2021-01-27 | 2021-01-28 | 2021-01-29 | 2021-01-30 | 2021-01-31 | Total
SM-D |  | Vol. Target | Monthly Plan Vol. | Remain
| Unit | 950000 |  | 950000
| EX S/Pond AL 52 | [34 empty] | 0
| Unit |  |  | 0
| Control Box AL-52 | [34 empty] | 0
| Unit |  |  | 0
| Control Box AL-68 | [34 empty] | 0
| Unit |  |  | 0
0
Total |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2021-02-01
Class | Pit | Volume |  |  | 2021-02-01 | 2021-02-02 | 2021-02-03 | 2021-02-04 | 2021-02-05 | 2021-02-06 | 2021-02-07 | 2021-02-08 | 2021-02-09 | 2021-02-10 | 2021-02-11 | 2021-02-12 | 2021-02-13 | 2021-02-14 | 2021-02-15 | 2021-02-16 | 2021-02-17 | 2021-02-18 | 2021-02-19 | 2021-02-20 | 2021-02-21 | 2021-02-22 | 2021-02-23 | 2021-02-24 | 2021-02-25 | 2021-02-26 | 2021-02-27 | 2021-02-28 | 2021-03-01 | 2021-03-02 | 2021-03-03 | Total
SM-D |  | Vol. Target | Monthly Plan Vol. | Remain
| Unit | 950000 |  | 950000
| EX S/Pond AL 52 | [34 empty] | 0
| Unit | 0 |  | 0
| Control Box AL-52 | [34 empty] | 0
| Unit | 0 |  | 0
| Control Box AL-68 | [34 empty] | 0
| Unit | 0 |  | 0
| 0 | [34 empty] | 0
Total |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2021-03-01
Class | Pit | Volume |  |  | 2021-03-01 | 2021-03-02 | 2021-03-03 | 2021-03-04 | 2021-03-05 | 2021-03-06 | 2021-03-07 | 2021-03-08 | 2021-03-09 | 2021-03-10 | 2021-03-11 | 2021-03-12 | 2021-03-13 | 2021-03-14 | 2021-03-15 | 2021-03-16 | 2021-03-17 | 2021-03-18 | 2021-03-19 | 2021-03-20 | 2021-03-21 | 2021-03-22 | 2021-03-23 | 2021-03-24 | 2021-03-25 | 2021-03-26 | 2021-03-27 | 2021-03-28 | 2021-03-29 | 2021-03-30 | 2021-03-31 | Total
SM-D |  | Vol. Target | Monthly Plan Vol. | Remain
| Unit | 950000 |  | 950000
| EX S/Pond AL 52 | [34 empty] | 0
| Unit | 0 |  | 0
| Control Box AL-52 | [34 empty] | 0
| Unit | 0 |  | 0
| Control Box AL-68 | [34 empty] | 0
| Unit | 0 |  | 0
| 0 | [34 empty] | 0
Total |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2021-04-01
Class | Pit | Volume |  |  | 2021-04-01 | 2021-04-02 | 2021-04-03 | 2021-04-04 | 2021-04-05 | 2021-04-06 | 2021-04-07 | 2021-04-08 | 2021-04-09 | 2021-04-10 | 2021-04-11 | 2021-04-12 | 2021-04-13 | 2021-04-14 | 2021-04-15 | 2021-04-16 | 2021-04-17 | 2021-04-18 | 2021-04-19 | 2021-04-20 | 2021-04-21 | 2021-04-22 | 2021-04-23 | 2021-04-24 | 2021-04-25 | 2021-04-26 | 2021-04-27 | 2021-04-28 | 2021-04-29 | 2021-04-30 | 2021-05-01 | Total
SM-D |  | Vol. Target | Monthly Plan Vol. | Remain
| Unit | 950000 | 180000 | 950000
| EX S/Pond AL 52 | [34 empty] | 0
| Unit | 0 |  | 0
| Control Box AL-52 | [34 empty] | 0
| Unit | 0 |  | 0
| Control Box AL-68 | [34 empty] | 0
| Unit | 0 |  | 0
| 0 | [34 empty] | 0
Total |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2021-05-01
Class | Pit | Volume |  |  | 2021-05-01 | 2021-05-02 | 2021-05-03 | 2021-05-04 | 2021-05-05 | 2021-05-06 | 2021-05-07 | 2021-05-08 | 2021-05-09 | 2021-05-10 | 2021-05-11 | 2021-05-12 | 2021-05-13 | 2021-05-14 | 2021-05-15 | 2021-05-16 | 2021-05-17 | 2021-05-18 | 2021-05-19 | 2021-05-20 | 2021-05-21 | 2021-05-22 | 2021-05-23 | 2021-05-24 | 2021-05-25 | 2021-05-26 | 2021-05-27 | 2021-05-28 | 2021-05-29 | 2021-05-30 | 2021-05-31 | Total
SM-D |  | Vol. Target | Monthly Plan Vol. | Remain
| Unit | 950000 | 120000 | 950000
| EX S/Pond AL 52 | [34 empty] | 0
| Unit | 0 |  | 0
| Control Box AL-52 | [34 empty] | 0
| Unit | 0 |  | 0
| Control Box AL-68 | [34 empty] | 0
| Unit | 0 |  | 0
| 0 | [34 empty] | 0
Total |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2021-06-01
Class | Pit | Volume |  |  | 2021-06-01 | 2021-06-02 | 2021-06-03 | 2021-06-04 | 2021-06-05 | 2021-06-06 | 2021-06-07 | 2021-06-08 | 2021-06-09 | 2021-06-10 | 2021-06-11 | 2021-06-12 | 2021-06-13 | 2021-06-14 | 2021-06-15 | 2021-06-16 | 2021-06-17 | 2021-06-18 | 2021-06-19 | 2021-06-20 | 2021-06-21 | 2021-06-22 | 2021-06-23 | 2021-06-24 | 2021-06-25 | 2021-06-26 | 2021-06-27 | 2021-06-28 | 2021-06-29 | 2021-06-30 | 2021-07-01 | Total
SM-D |  | Vol. Target | Monthly Plan Vol. | Remain
| Unit | 950000 |  | 950000
| EX S/Pond AL 52 | [34 empty] | 0
| Unit | 0 |  | 0
| Control Box AL-52 | [34 empty] | 0
| Unit | 0 |  | 0
| Control Box AL-68 | [34 empty] | 0
| Unit | 0 |  | 0
| 0 | [34 empty] | 0
Total |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2021-07-01
Class | Pit | Volume |  |  | 2021-07-01 | 2021-07-02 | 2021-07-03 | 2021-07-04 | 2021-07-05 | 2021-07-06 | 2021-07-07 | 2021-07-08 | 2021-07-09 | 2021-07-10 | 2021-07-11 | 2021-07-12 | 2021-07-13 | 2021-07-14 | 2021-07-15 | 2021-07-16 | 2021-07-17 | 2021-07-18 | 2021-07-19 | 2021-07-20 | 2021-07-21 | 2021-07-22 | 2021-07-23 | 2021-07-24 | 2021-07-25 | 2021-07-26 | 2021-07-27 | 2021-07-28 | 2021-07-29 | 2021-07-30 | 2021-07-31 | Total
SM-D |  | Vol. Target | Monthly Plan Vol. | Remain
| Unit | 950000 |  | 950000
| EX S/Pond AL 52 | [34 empty] | 0
| Unit | 0 |  | 0
| Control Box AL-52 | [34 empty] | 0
| Unit | 0 |  | 0
| Control Box AL-68 | [34 empty] | 0
| Unit | 0 |  | 0
| 0 | [34 empty] | 0
Total |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2021-08-01
Class | Pit | Volume |  |  | 2021-08-01 | 2021-08-02 | 2021-08-03 | 2021-08-04 | 2021-08-05 | 2021-08-06 | 2021-08-07 | 2021-08-08 | 2021-08-09 | 2021-08-10 | 2021-08-11 | 2021-08-12 | 2021-08-13 | 2021-08-14 | 2021-08-15 | 2021-08-16 | 2021-08-17 | 2021-08-18 | 2021-08-19 | 2021-08-20 | 2021-08-21 | 2021-08-22 | 2021-08-23 | 2021-08-24 | 2021-08-25 | 2021-08-26 | 2021-08-27 | 2021-08-28 | 2021-08-29 | 2021-08-30 | 2021-08-31 | Total
SM-D |  | Vol. Target | Monthly Plan Vol. | Remain
| Unit | 950000 |  | 950000
| EX S/Pond AL 52 | [34 empty] | 0
| Unit | 0 |  | 0
| Control Box AL-52 | [34 empty] | 0
| Unit | 0 |  | 0
| Control Box AL-68 | [34 empty] | 0
| Unit | 0 |  | 0
| 0 | [34 empty] | 0
Total |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2021-09-01
Class | Pit | Volume |  |  | 2021-09-01 | 2021-09-02 | 2021-09-03 | 2021-09-04 | 2021-09-05 | 2021-09-06 | 2021-09-07 | 2021-09-08 | 2021-09-09 | 2021-09-10 | 2021-09-11 | 2021-09-12 | 2021-09-13 | 2021-09-14 | 2021-09-15 | 2021-09-16 | 2021-09-17 | 2021-09-18 | 2021-09-19 | 2021-09-20 | 2021-09-21 | 2021-09-22 | 2021-09-23 | 2021-09-24 | 2021-09-25 | 2021-09-26 | 2021-09-27 | 2021-09-28 | 2021-09-29 | 2021-09-30 | 2021-10-01 | Total
SM-D |  | Vol. Target | Monthly Plan Vol. | Remain
| Unit | 950000 |  | 950000
| S/Pond 7B | [34 empty] | 0
| Unit | 0 |  | 0
| Control Box AL-52 | [34 empty] | 0
| Unit | 0 |  | 0
| Control Box AL-68 | [34 empty] | 0
| Unit | 0 |  | 0
| 0 | [34 empty] | 0
Total |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2021-10-01
Class | Pit | Volume |  |  | 2021-10-01 | 2021-10-02 | 2021-10-03 | 2021-10-04 | 2021-10-05 | 2021-10-06 | 2021-10-07 | 2021-10-08 | 2021-10-09 | 2021-10-10 | 2021-10-11 | 2021-10-12 | 2021-10-13 | 2021-10-14 | 2021-10-15 | 2021-10-16 | 2021-10-17 | 2021-10-18 | 2021-10-19 | 2021-10-20 | 2021-10-21 | 2021-10-22 | 2021-10-23 | 2021-10-24 | 2021-10-25 | 2021-10-26 | 2021-10-27 | 2021-10-28 | 2021-10-29 | 2021-10-30 | 2021-10-31 | Total
SM-D |  | Vol. Target | Monthly Plan Vol. | Remain
| Unit | 950000 |  | 950000
| S/Pond 7B | [34 empty] | 0
| Unit | 0 |  | 0
| Control Box AL-52 | [34 empty] | 0
| Unit | 0 |  | 0
| Control Box AL-68 | [34 empty] | 0
| Unit | 0 |  | 0
| 0 | [34 empty] | 0
Total |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2021-11-01
Class | Pit | Volume |  |  | 2021-11-01 | 2021-11-02 | 2021-11-03 | 2021-11-04 | 2021-11-05 | 2021-11-06 | 2021-11-07 | 2021-11-08 | 2021-11-09 | 2021-11-10 | 2021-11-11 | 2021-11-12 | 2021-11-13 | 2021-11-14 | 2021-11-15 | 2021-11-16 | 2021-11-17 | 2021-11-18 | 2021-11-19 | 2021-11-20 | 2021-11-21 | 2021-11-22 | 2021-11-23 | 2021-11-24 | 2021-11-25 | 2021-11-26 | 2021-11-27 | 2021-11-28 | 2021-11-29 | 2021-11-30 | 2021-12-01 | Total
SM-D |  | Vol. Target | Monthly Plan Vol. | Remain
| Unit | 950000 |  | 950000
| S/Pond 7B | [34 empty] | 0
| Unit | 0 |  | 0
| Control Box AL-52 | [34 empty] | 0
| Unit | 0 |  | 0
| Control Box AL-68 | [34 empty] | 0
| Unit | 0 |  | 0
| 0 | [34 empty] | 0
Total |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2021-12-01
Class | Pit | Volume |  |  | 2021-12-01 | 2021-12-02 | 2021-12-03 | 2021-12-04 | 2021-12-05 | 2021-12-06 | 2021-12-07 | 2021-12-08 | 2021-12-09 | 2021-12-10 | 2021-12-11 | 2021-12-12 | 2021-12-13 | 2021-12-14 | 2021-12-15 | 2021-12-16 | 2021-12-17 | 2021-12-18 | 2021-12-19 | 2021-12-20 | 2021-12-21 | 2021-12-22 | 2021-12-23 | 2021-12-24 | 2021-12-25 | 2021-12-26 | 2021-12-27 | 2021-12-28 | 2021-12-29 | 2021-12-30 | 2021-12-31 | Total
SM-D |  | Vol. Target | Monthly Plan Vol. | Remain
| Unit | 950000 |  | 950000
| S/Pond 7B | [34 empty] | 0
| Unit | 0 |  | 0
| Control Box AL-52 | [34 empty] | 0
| Unit | 0 |  | 0
| Control Box AL-68 | [34 empty] | 0
| Unit | 0 |  | 0
| 0 | [34 empty] | 0
Total |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## Map
RTS A-F
RTS G
SM A
>> SM A
SM B
>> SM B
SM D
>> SM D
RTN - SM 6
>> RTN - SM 6
RTM
SSB
>> Settling Pond AL 59 Pit Roto South F
>> Settling Pond AL 54 Pit Roto South F
>> Settling Pond AL 66 Pit Roto South G
>> Settling Pond AL 28 & AL 57 Pit SM A
>> Settling Pond AL 55 & AL 56 Pit SM B
>> Settling Pond AL 64 Pit RTS G