## Weekly report
[Production Team]
May 31th , 2023
| This Week | [8 empty] | Next Week
Main | - Continue Construct Lowest Point Sump Optimazation for Expose Coal (RTM) | [8 empty] | - Continue Loading Mud & Coal Sump Optimazation for Expose Coal (RTM)
Issues | - Continue Expose Seam 12 group for coal inventory (RTM) | [8 empty] | - Continue Expose Seam 12 group for coal inventory (rtm)
Main | - Continue construct sump intermediate - RTM | [8 empty] | - Continue construct sump intermediate - RTM | [11 empty] | progress area pit 1 sisi utara timur
| - Continue Loading mud at Main Sump RTM (2 x Dragflow) - RTM | [8 empty] | - Continue Loading mud at Main Sump RTM (2 x Dragflow) - RTM | [11 empty] | cut back sisi timur selatan
| - Progress Area Pit 1 Sisi Utara - RTN | [8 empty] | - Progress Area Pit 1 Sisi Utara - RTN | [11 empty] | - Penurunan cut back area sisi selatan
| - Penurunan Cut Back Area Sisi Selatan RTN | [8 empty] | - Penurunan Cut Back Area Sisi Selatan RTN | [11 empty] | - Penurunan cut back area sisi selatan
| - Coal Optimization at Bottom SM 6 Area | [8 empty] | - Coal Optimization at Bottom SM 6 Area | [11 empty] | cut back sisi timur selatan
| - Expose Seam 8 to Displacement of the High Wall Ditch - SM 6 | [8 empty] | - Expose Seam 8 to Displacement of the High Wall Ditch - SM 6 | [11 empty] | - Penurunan cut back area sisi selatan
| - Construct Access Low Wall - SM 6 | [8 empty] | - Construct Access Low Wall - SM 6 | [11 empty] | - Penurunan cut back area sisi selatan
| - Continue Prepare dumping at P3 Area OPD (Crossing citizen road) - SSB | [8 empty] | - Continue Prepare dumping at P3 Area OPD (Crossing citizen road) - SSB
| - Continue Prepare Access to OPD Area (Susubang) | [8 empty] | - Continue Prepare Access to OPD Area (Susubang)
| - Continue Running Seam 5 & SM D2's Pump | [8 empty] | - Continue Running Seam 5 & SM D2's Pump
| - Continue running Geotube (SM D) | [8 empty] | - Continue running Geotube (SM D)
| - Continue Maintanance East Side of Waste Dump 9's Ditch (SM D) | [8 empty] | - Continue Maintanance East Side of Waste Dump 9's Ditch (SM D)
| - Continue Focus to Finalization Semangka Blok Plan Inpit to RL 48 (1 Fleet) - SSB | [8 empty] | - Continue Focus to Finalization Semangka Blok Plan Inpit to RL 48 (1 Fleet) - SSB
| - Continue Construct Outer Drainage Area OPD West - SSB | [8 empty] | - Continue Construct Outer Drainage Area OPD West - SSB
| - Continue Dilation Sump Seam 5 at SM D | [8 empty] | - Continue Dilation Sump Seam 5 at SM D | [11 empty] | oprimasi bb area bottom sm 6, seharusnya sudah loading lumpur
| - Continue Progress Loading Slurry Removal at Remains ex AL 52 SM D | [8 empty] | - Continue Progress Loading Slurry Removal at Remains ex AL 52 SM D | [11 empty] | expose seam 8 untuk peralihan parit high wall
| - Progress Loading Top Soil - SM B | [8 empty] | - Progress Loading Top Soil - SM B | [11 empty] | construct access low wall sm 6
| - Continue Cutback SM B2 Area (SIMS) | [8 empty] | - Continue Cutback SM B2 Area (SIMS)
| - Loading Mud at Inpit SM AW | [8 empty] | - Loading Mud at Inpit SM AW
- Loading Mud at Inpit SM AW
| - Continue Progress Cutback 7B RTS (1 X PC2000) - RTS AF | [8 empty] | - Comissioning Slurry Removal RTS G
| - Continue Construck Sump Temporary RTS G | [8 empty] | - Continue Construck Sump Temporary RTS G
| - Continue Loading Bundwall and Mud at Sump C3 West - RTS AF | [8 empty] | - Continue Loading Bundwall and Mud at Sump C3 West
Rainfall | - Rainfall | [17 empty] | (Unit : mm, hr/day)
Coal & |  | Class |  |  | Month to Date (01 ~ 31 May) | [8 empty] | Weekly (01 ~ 31 May) |  |  | Remarks
Waste |  |  |  |  | Plan (May) |  |  | Actual |  |  | Diff
|  | Rainfall |  |  | 198.7077 |  |  | 305.1818 |  |  | 106.4741 |  |  | 103.6591
|  | Standby hours |  |  | 3.19 |  |  | 5.0217 |  |  | 1.8317 |  |  | 3.8633
| - Coal Production & Waste Removal | [17 empty] | (Unit : Kton, Kbcm)
|  | Class |  | Month to Date (01 ~ 31 May) | [5 empty] | Weekly (01 ~ 31 May) | [5 empty] | A/Plan of May
|  |  |  | Plan |  | Actual |  | Diff |  | Plan |  | Actual |  | Diff
|  | Coal |  | 2863710.2 |  | 2715566.11 |  | -148144.09 |  | 637903.7 |  | 605422.3 |  | -32481.4 |  | 2875 |  | Kton
|  | Waste |  | 16983999.7 |  | 14267937 |  | -2716062.7 |  | 3835096.3 |  | 3536267 |  | -298829.3 |  | 16984 |  | KBcm
Exposed | - Exposed Coal (Target : Exposed 14 days, Ready 7 days) | [17 empty] | (Unit : Kton) |  | * Caculation for coal stock days
Coal |  | Class |  |  | Last Week (21th May ) |  |  |  | This Week (28th May) |  |  |  | Diff |  |  |  | Remarks (Main Area) |  |  |  |  | May
[5 empty] | Exposed |  | Ready |  | Exposed |  | Ready |  | Exposed |  | Ready | [5 empty] | area | Daily Plan | Exposed | Ready
|  | R S |  |  | 18.6139 |  | 17.6221 |  | 29.9837 |  | 19.5793 |  | 11.3698 | -1.1326 | 1.9572 | -1.1326 | RTN, RTM, RTS, SSB |  |  |  | RS | 25838.8 | 1.1604 | 0.75775
|  | S M |  |  | 235.2094 |  | 82.9891 |  | 223.4076 |  | 65.5109 |  | -11.8018 | -0.13258 | -17.4782 | -0.13258 | SM-A/D |  |  |  | SM | 42709.7 | 5.2308 | 1.5339
|  | TOTAL |  |  | 253.8233 |  | 100.6113 |  | 253.3913 |  | 85.0902 |  | -0.43202 | 0.86742 | -15.5211 | 0.86742 | [5 empty] | 68548.5
|  | Stock Days |  |  | RS Coal : 2 days, SM Coal : 6 days
Sump | - Sump Status (As of 31th May)
. Total Catchment Area 4,073 ha, Weekly Rainfall 103.7 mm (Max. RTM 175.0 mm, Min. SSB 3.0 mm)
|  | Volume of Water (Km³) | [8 empty] | In-flow (Km³) |  |  | Ex-flow (Km³) |  |  | Remarks
|  | Last Week (21th May ) |  |  | This Week (28th May) |  |  | Diff
|  | 11772 |  |  | 11475 |  |  | -297 |  |  | 4412.205 |  |  | 4709.205
Hauling | - Management of Hauling Distance
Distance |  | - All area are in a good performance in order to mantain hauling distance
* Apr-May Based on trucking base
Quality &
Recovery
Road | - Progress moving pipe water citizen to road replacement
Access | - Progress Plan Road SM B to SM C | [8 empty] | - Progress Plan Road SM B to SM C
| - Prepare moving access road to access entrance SM D | [8 empty] | - Prepare moving access road to access entrance SM D
| - Continue Construct Jalan Hauling SM AW | [8 empty] | - Continue Construct Jalan Hauling SM AW
| - Progress Plan Road to Bank Soil & Intersection B4 | [8 empty] | - Progress Plan Road to Bank Soil & Intersection B4
Slope Stability
Pit Maintenance
| - Sump Status (As of 31th May) | [18 empty] | (Unit : KM³, KM³/day)
| Class |  |  | Catchment Area(ha) |  | Volume of Water | [8 empty] | Pumping Capa. |  | Pump Line (Including Transfer) |  |  |  | Class |  | Weekly Rain Fall | In-flow | 전주 잔여량 +강우유입량 | 주간 펌핑량 | 예상잔여량 | diff
[6 empty] | Last Week (21th May ) |  |  | This Week (28th May) |  |  | Diff.
| Ex -Pit | RN | 7W | 426 |  | 3181 |  |  | 3078 |  |  | -103 |  |  | 54 |  | 2 line |  |  |  | RN | 7W | 170.5 | 726.33 | 3907.33 | 378 | 3529.33 | -451.33
|  |  | 4W | 87 |  | 3304 |  |  | 3298 |  |  | -6 |  |  | 22 |  | 2 line |  |  |  |  | 4W | 170.5 | 148.335 | 3452.335 | 154 | 3298.335 | -0.335
|  | RM |  | 328 |  | 0 |  |  | 0 |  |  | 0 |  |  | 46.08 |  | 3 line |  |  |  | RM |  | 175 | 574 | 574 | 322.56 | 251.44 | -251.44
|  | RS | C3 | 478 |  | 461 |  |  | 458 |  |  | -3 |  |  | 50.4 |  | 4 line |  |  |  | RTS | C3 | 110.5 | 528.19 | 989.19 | 352.8 | 636.39 | -178.39
|  |  | D1 | 52 |  | 0 |  |  | 0 |  |  | 0 |  |  | 86.4 |  | 1 line |  |  |  |  | D1 | 110.5 | 57.46 | 57.46 | 604.8 | -547.34 | 547.34
|  |  | D2 | 479 |  | 378 |  |  | 357 |  |  | -21 |  |  | 87.4 |  | 1 line |  |  |  |  | D2 | 110.5 | 529.295 | 907.295 | 611.8 | 295.495 | 61.505
|  |  | E1 | 154 |  | 273 |  |  | 256 |  |  | -17 |  |  | 43.2 |  | 1 line |  |  |  |  | E1 | 41.25 | 63.525 | 336.525 | 302.4 | 34.125 | 221.875
|  |  | 3F | 322 |  | 893 |  |  | 910 |  |  | 17 |  |  | 34.92 |  | 3 line |  |  |  |  | 3F | 41.25 | 132.825 | 1025.825 | 244.44 | 781.385 | 128.615
|  |  | C4 | 36 |  | 0 |  |  | 0 |  |  | 0 |  |  | 40 |  | 1 line |  |  |  |  | C4 | 110.5 | 39.78 | 39.78 | 280 | -240.22 | 240.22
|  |  | G1 | 114 |  | 82 |  |  | 60 |  |  | -22 |  |  | 20 |  | 1 line |  |  |  |  | G1 | 65 | 74.1 | 156.1 | 140 | 16.1 | 43.9
|  |  | Mensiwei | 43 |  | 0 |  |  | 0 |  |  | 0 |  |  | 10 |  | 1 line |  |  |  |  | Mensiwei | 65 | 27.95 | 27.95 | 70 | -42.05 | 42.05
|  | SM | Aw | 308 |  | 0 |  |  | 0 |  |  | 0 |  |  | 10 |  | 2 line |  |  |  | SM | Aw | 159.5 | 491.26 | 491.26 | 70 | 421.26 | -421.26
|  |  | A1 | 129 |  | 59 |  |  | 50 |  |  | -9 |  |  | 50 |  | 2 line |  |  |  |  | A1 | 159.5 | 205.755 | 264.755 | 350 | -85.245 | 135.245
|  |  | #6 | 132 |  | 15 |  |  | 8 |  |  | -7 |  |  | 15 |  | 2 line |  |  |  |  | #6 | 159.5 | 210.54 | 225.54 | 105 | 120.54 | -112.54
|  |  | B | 309 |  | 93 |  |  | 90 |  |  | -3 |  |  | 15 |  | 3 line |  |  |  |  | B | 162 | 500.58 | 593.58 | 105 | 488.58 | -398.58
|  |  | 3 D1 | 280 |  | 344 |  |  | 320 |  |  | -24 |  |  | 26.1 |  | 4 line |  |  |  |  | 3 D1 | 23 | 64.4 | 408.4 | 182.7 | 225.7 | 94.3
|  |  | 6L D1 | 130 |  | 92 |  |  | 75 |  |  | -17 |  |  | 26.1 |  | 1 line |  |  |  |  | 6L D1 | 23 | 29.9 | 121.9 | 182.7 | -60.8 | 135.8
|  |  | D2 | 180 |  | 2455 |  |  | 2400 |  |  | -55 |  |  | 27.6 |  | 1 line |  |  |  |  | D2 | 3 | 5.4 | 2460.4 | 193.2 | 2267.2 | 132.8
|  | SSB |  | 86 |  | 142 |  |  | 115 |  |  | -27 |  |  | 17.8 |  | 1 line |  |  |  | SSB |  | 3 | 2.58 | 144.58 | 124.6 | 19.98 | 95.02
| Total |  |  | 4073 |  | 11772 |  |  | 11475 |  |  | -297 |  |  | 682 | [8 empty] | 4412.205

## Weekly Statistics
<Production Team> | [7 empty] | Weekly Production Statistics
| [May Plan : OB 16,984 KBcm, Coal 2,875 Kton] | [12 empty] | (Weekly: 05/25~05/31, Monthly: 05/01~05/31)
|  | OB | Weekly | [5 empty] | Monthly
|  | (bcm) | Plan |  | Actual |  | Diff. |  | Plan |  | Actual |  | Diff.
|  | RN(Pama) | 191935.8 |  | 107733.5 |  | -84202.3 |  | 850000.3 |  | 588031.5 |  | -261968.8
|  | C/D | 435354.5 |  | 453871.8333 |  | 18517.3333 |  | 1927999.7 |  | 1783031.8333 |  | -144967.8667
|  | G | 211129.1 |  | 247217.8333 |  | 36088.7333 |  | 935000.1 |  | 856211.8333 |  | -78788.2667
|  | RM(Pama) | 209773.9 |  | 226031.1667 |  | 16257.2667 |  | 928999.7 |  | 905354.1667 |  | -23645.5333
|  | SM-B(Pama) | 124193.3 |  | 160770.1667 |  | 36576.8667 |  | 549999.8 |  | 715696.1667 |  | 165696.3667
|  | SM6(Pama) | 306193.3 |  | 265402.6667 |  | -40790.6333 |  | 1355999.8 |  | 1090514.6667 |  | -265485.1333
|  | SM-A (SIMS) | 711290.3 |  | 441480.6667 |  | -269809.6333 |  | 3150000 |  | 1959413.6667 |  | -1190586.3333
|  | SM-C8 (Pama) | 42903 |  | 0 |  | -42903 |  | 189999.8 |  | 0 |  | -189999.8
|  | SM-D1 (PTP) | 1354838.8 |  | 1292603.6667 |  | -62235.1333 |  | 6000000.1 |  | 5092886.6667 |  | -907113.4333
|  | SM-D2 (DUM) | 59387.3 |  | 82762.1667 |  | 23374.8667 |  | 263000.2 |  | 331076.1667 |  | 68075.9667
|  | SSB | 188097 |  | 258393.3333 |  | 70296.3333 |  | 833000.2 |  | 945720.3333 |  | 112720.1333
total
|  | Sum | 3835096.3 |  | 3536267 |  | -298829.3 |  | 16983999.7 |  | 14267937 |  | -2716062.7
|  | Coal | Weekly | [5 empty] | Monthly
| (톤) | (Ton) | Plan |  | Actual |  | Diff. |  | Plan |  | Actual |  | Diff.
|  | RTN(Petro) | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  | RTN(Pama) | 14451.5 |  | 15510.25 |  | 1058.75 |  | 63999.9 |  | 58609.65 |  | -5390.25
|  | RS_CD(Pama) | 47419.4 |  | 68724.4833 |  | 21305.0833 |  | 210000 |  | 254695.8833 |  | 44695.8833
|  | RS_G(Pama) | 11290.3 |  | 17683.1667 |  | 6392.8667 |  | 50000 |  | 97115.2667 |  | 47115.2667
|  | RM(Pama) | 39516.4 |  | 37063.0167 |  | -2453.3833 |  | 175000.3 |  | 200070.5167 |  | 25070.2167
|  | SMB (Pama) | 29806.7 |  | 28658.7 |  | -1148 |  | 142839 |  | 82039.5 |  | -60799.5
|  | SM6 (Pama) | 22580.6 |  | 25375.7 |  | 2795.1 |  | 100000 |  | 76235.9 |  | -23764.1
|  | SM-ABC(Sims) | 158064.2 |  | 97129.2 |  | -60935 |  | 717031.9 |  | 582677.7 |  | -134354.2
|  | SM-C8 (Pama) | 17161.2 |  | 0 |  | -17161.2 |  | 75999.9 |  | 0 |  | -75999.9
|  | SM-ABC(Pama) | [6 empty] | 0 |  | 0
|  | SM-D(Petro) | 281806.7 |  | 289900.2167 |  | 8093.5167 |  | 1258839 |  | 1270382.9267 |  | 11543.9267
|  | SSB(Bima) | 15806.7 |  | 25377.5667 |  | 9570.8667 |  | 70000.2 |  | 93738.7667 |  | 23738.5667
|  | Sum | 637903.7 |  | 605422.3 |  | -32481.4 |  | 2863710.2 |  | 2715566.11 |  | -148144.09
|  | Exposed | 05/21 |  |  |  | 05/28 |  |  |  | Diff.
|  | Coal(Kton) | Exposed |  | Ready |  | Exposed |  | Ready |  | Exposed |  | Ready
|  | RTN | 2.73 |  | 2.5935 |  | 4.719 |  | 3.6309 |  | 1.989 |  | 1.0374
|  | C/D | 5.018 |  | 4.8256 |  | 12.48 |  | 5.434 |  | 7.462 |  | 0.6084
|  | E/F | [8 empty] | 0 |  | 0
|  | G | 2.275 |  | 2.1612 |  | 3.64 |  | 2.5935 |  | 1.365 |  | 0.43225
|  | RTM | 6.396 |  | 6.0762 |  | 6.552 |  | 5.7798 |  | 0.156 |  | -0.2964
|  | SM-A | 85.8936 |  | 39.45 |  | 38.61 |  | 16.6725 |  | -47.2836 |  | -22.7775
|  | SM-B | 2.8743 |  | 2.745 |  | 10.0165 |  | 5.8332 |  | 7.1422 |  | 3.0882
|  | SM-6 | 4.095 |  | 6.9869 |  | 3.9 |  | 2.4209 |  | -0.195 |  | -4.5659
|  | SM-D1 | 142.3465 |  | 33.8073 |  | 170.8811 |  | 40.5843 |  | 28.5346 |  | 6.777
|  | SM-D2 | [8 empty] | 0 |  | 0
|  | SSB | 2.1949 |  | 1.9656 |  | 2.5927 |  | 2.1411 |  | 0.3978 |  | 0.1755
|  | Sum | 253.8233 |  | 100.6113 |  | 253.3913 |  | 85.0902 |  | -0.43202 |  | -15.5211
| ROM Temporary (Kton) |  | PTP |  |  | SIMS |  |  | SSB |  |  | TOTAL
|  |  | (ROM A) |  |  | (ROM_SMA)
|  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0
| Rain |  | Weekly (05/25~05/31) | [5 empty] | Monthly (05/01~05/31) | [5 empty] | 6 | weekly
| (mm,hr) |  | Rain fall | Rain hour | Road Maintenance | Fog hour | Disturb Hour(mm/hr) |  | Rain fall | Rain hour | Road Maintenance | Fog hour | Disturb Hour(mm/hr) |  | 30 | monthly
[7 empty] | Sum | Avg. Daily |  |  |  |  | Sum | Avg. Daily
|  | RTN | 170.5 | 20.3167 | 7.5 | 0 | 27.8167 | 4.6361 | 374.5 | 104.2833 | 38.6 | 0 | 142.8833 | 4.7628
|  | A/B | 123 | 20.2167 | 5.8 | 0 | 26.0167 | 4.3361 | 344.5 | 106.3833 | 33.9333 | 0 | 140.3167 | 4.6772
|  | C/D | 110.5 | 20.2167 | 7.5333 | 0 | 27.75 | 4.625 | 288 | 106.8 | 37.3167 | 0 | 144.1167 | 4.8039
|  | E/F | 41.25 | 11.3458 | 6.8833 | 0 | 18.2292 | 3.0382 | 179.5 | 104.6042 | 88.5583 | 2.6333 | 195.7958 | 6.5265
|  | G | 65 | 7.6167 | 5.8667 | 0 | 13.4833 | 2.2472 | 210 | 106.0833 | 39.6833 | 3.5 | 149.2667 | 4.9756
|  | RTM | 175 | 20.75 | 6.0167 | 0 | 26.7667 | 4.4611 | 363.5 | 108.7333 | 38.5833 | 1.25 | 148.5667 | 4.9522
|  | SM-A | 159.5 | 18.8333 | 16.5333 | 1.9333 | 37.3 | 6.2167 | 357 | 108.5667 | 72.85 | 4.9833 | 186.4 | 6.2133
|  | SM-B | 162 | 20.3 | 19.6167 | 1.85 | 41.7667 | 6.9611 | 380 | 120.8667 | 85.8333 | 25.1 | 231.8 | 7.7267
|  | SM-D1 | 23 | 4.25 | 2.0833 | 0 | 6.3333 | 1.0556 | 303.5 | 60.3 | 21 | 0 | 81.3 | 2.71
|  | SM 6 | 107.5 | 20.45 | 6.3167 | 0 | 26.7667 | 4.4611 | 355 | 116.4667 | 50.1333 | 1.6833 | 168.2833 | 5.6094
|  | SSB | 3 | 1.9 | 0.85 | 0 | 2.75 | 0.45833 | 201.5 | 49.7333 | 18.6833 | 0 | 68.4167 | 2.2806
|  | Avg. | 103.6591 | 15.1087 | 7.7273 | 0.34394 | 23.1799 | 3.8633 | 305.1818 | 99.3473 | 47.7432 | 3.5591 | 150.6496 | 5.0217
※ Plan Slippery (Rain+Clean Up) Disturb hour May : 3.19 hr/day

## Weekly Raw Data
[10 empty] | Weekly sum |  |  | Weekly Daily Plan |  |  | Monthly cum |  |  |  | 2022-04-30 | 389
Class | Pit/Area | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Sun | Weekly |  |  | May |  |  | 2023-05-24 |  | 2022-04-30 |  | --> data end of month bulan sebelumnya
|  | 2023-05-25 | 2023-05-26 | 2023-05-27 | 2023-05-28 | 2023-05-29 | 2023-05-30 | 2023-05-31 | 2023-06-01 | Actual | Plan | w/days | daily plan | daily plan | w/days | plan | actual | Plan | Actual
Waste | RN(Pama) | 22576 | 22931 | 16481 | 3246 | 9568 | 17541 | 15390.5 |  | 107733.5 | 191935.8 | 7 | 27419.4 |  |  | 658064.5 | 480298 | 748000 | 593829
| C/D | 78567 | 72483 | 45610 | 81764 | 50801 | 59808 | 64838.8333 |  | 453871.8333 | 435354.5 |  | 62193.5 |  |  | 1492645.2 | 1329160 | 1758000 | 1420111
| G | 33981 | 39327 | 27557 | 39547 | 31807 | 39682 | 35316.8333 |  | 247217.8333 | 211129.1 |  | 30161.3 |  |  | 723871 | 608994 | 776000 | 591230
| RM(Pama) | 30478 | 28141 | 19503 | 41677 | 31015 | 42927 | 32290.1667 |  | 226031.1667 | 209773.9 |  | 29967.7 |  |  | 719225.8 | 679323 | 920000 | 653695
| SM-B(Pama) | 33273 | 25706 | 16933 | 24718 | 12690 | 24483 | 22967.1667 |  | 160770.1667 | 124193.3 |  | 17741.9 |  |  | 425806.5 | 554926 | 450000 | 409141
| SM6(Pama) | 36325 | 48746 | 27764 | 53815 | 22076 | 38762 | 37914.6667 |  | 265402.6667 | 306193.3 |  | 43741.9 |  |  | 1049806.5 | 825112 | 1229000 | 817837
| SM-A (SIMS) | 79759 | 68754 | 57274 | 67719 | 32211 | 72695 | 63068.6667 |  | 441480.6667 | 711290.3 |  | 101612.9 |  |  | 2438709.7 | 1517933 | 3198000 | 681585
| SM-C8 (Pama) | [8 empty] | 0 | 42903 |  | 6129 |  |  | 147096.8 | 0
| SM-D1 (PTP) | 201716 | 183287 | 146484 | 215837 | 160094 | 200528 | 184657.6667 |  | 1292603.6667 | 1354838.8 |  | 193548.4 |  |  | 4645161.3 | 3800283 | 4800000 | 3750436
| SM-D2 (DUM) | 12903 | 10670 | 9361 | 13761 | 12144 | 12100 | 11823.1667 |  | 82762.1667 | 59387.3 |  | 8483.9 |  |  | 203612.9 | 248314 | 241000 | 222750
| SSB | 29271 | 28010 | 32930 | 32398 | 28038 | 70833 | 36913.3333 |  | 258393.3333 | 188097 |  | 26871 |  |  | 644903.2 | 687327 | 831000 | 798360
| total | 558849 | 528055 | 399897 | 574482 | 390444 | 579359 | 505181 | 0 | 3536267 | 3835096.3 |  | 547870.9 | 0 |  | 13148903.4 | 10731670 | 14951000 | 9938974
Coal | RTN(Petro) | [9 empty] | 0 | 7 | 0 |  |  | 0 | 0 | 0 | 0
(ton) | RTN(Pama) | 2070.2 | 2119.2 | 1192.6 | 2579.9 | 2207.6 | 3125 | 2215.75 |  | 15510.25 | 14451.5 |  | 2064.5 |  |  | 49548.4 | 43099.4 | 70000 | 61080
| RS_CD(Pama) | 9517.4 | 9362.3 | 7640.3 | 14620.2 | 10387.7 | 7378.8 | 9817.7833 |  | 68724.4833 | 47419.4 |  | 6774.2 |  |  | 162580.6 | 185971.4 | 200000 | 236526
| RS_G(Pama) | 1943.7 | 3588.2 | 2735.7 | 3429.2 | 1778.6 | 1681.6 | 2526.1667 |  | 17683.1667 | 11290.3 |  | 1612.9 |  |  | 38709.7 | 79432.1 | 70000 | 34315
| RM(Pama) | 9066.4 | 4652.8 | 5011 | 6402.5 | 2281.5 | 4354.1 | 5294.7167 |  | 37063.0167 | 39516.4 |  | 5645.2 |  |  | 135483.9 | 163007.5 | 170000 | 159993
| SMB (Pama) | 3574 | 3206 | 5047.8 | 5353.2 | 2972 | 4411.6 | 4094.1 |  | 28658.7 | 29806.7 |  | 4258.1 |  |  | 113032.3 | 53380.8 | 60000 | 42314
| SM6 (Pama) | 5505.9 | 3761.7 | 1690.9 | 4164.2 | 2075.4 | 4552.5 | 3625.1 |  | 25375.7 | 22580.6 |  | 3225.8 |  |  | 77419.4 | 50860.2 | 100000 | 39467
| SM-ABC(Sims) | 25907.4 | 22140.4 | 12914.3 | 5892.8 | 2461.4 | 13937.3 | 13875.6 |  | 97129.2 | 158064.2 |  | 22580.6 |  |  | 558967.7 | 485548.5 | 700000 | 194137
| SM-C8 (Pama) | [8 empty] | 0 | 17161.2 |  | 2451.6 |  |  | 58838.7 | 0 | 0 | 0
SM-ABC(Pama)
| SM-D(Petro) | 46069.4 | 42745.9 | 37917.2 | 46659 | 29416 | 45678.4 | 41414.3167 |  | 289900.2167 | 281806.7 |  | 40258.1 |  |  | 977032.3 | 980482.71 | 1124000 | 915683
| SM-D(DUM) | [9 empty] | 0 |  | 0 |  |  |  | 0 | 0 | 0
| SSB(Bima) | 3135.4 | 2909.7 | 2899.1 | 5273.7 | 4524.9 | 3009.4 | 3625.3667 |  | 25377.5667 | 15806.7 |  | 2258.1 |  |  | 54193.5 | 68361.2 | 70000 | 64974
| total | 106789.8 | 94486.2 | 77048.9 | 94374.7 | 58105.1 | 88128.7 | 86488.9 | 0 | 605422.3 | 637903.7 |  | 91129.1 | 0 |  | 2225806.5 | 2110143.81 | 2564000 | 1748489
Rainfall | RN | [8 empty] | 0 |  |  | 0
(mm) | B | [8 empty] | 0 |  |  | 0
| C | [8 empty] | 0 |  |  | 0
| E | [8 empty] | 0 |  |  | 0
| F | [8 empty] | 0 |  |  | 0
| G | [8 empty] | 0 |  |  | 0
| M | [8 empty] | 0 |  |  | 0
| SM-A | [8 empty] | 0 |  |  | 0
| SM-B | [8 empty] | 0 |  |  | 0
| SM-D1 | [8 empty] | 0 |  |  | 0
| SM-D2 | [8 empty] | 0 |  |  | 0
| SSB | [8 empty] | 0 |  |  | 0
| TCMT | [8 empty] | 0 |  |  | 0
| A-Bay | [8 empty] | 0 |  |  | 0
Rain+Cleanup | RN | [8 empty] | 0 | 0 | 0 | 0 | 0
(hr) | B | [8 empty] | 0 | 0 | 0 | 0 | 0
*actual | C | [8 empty] | 0 | 0 | 0 | 0 | 0
| E | [8 empty] | 0 | 0 | 0 | 0 | 0
| F | [8 empty] | 0 | 0 | 0 | 0 | 0
| G | [8 empty] | 0 | 0 | 0 | 0 | 0
| M | [8 empty] | 0 | 0 | 0 | 0 | 0
| SM-A | [8 empty] | 0 | 0 | 0 | 0 | 0
| SM-B | [8 empty] | 0 | 0 | 0 | 0 | 0
| SM-D1 | [8 empty] | 0 | 0 | 0 | 0 | 0
| SM-D2 | [8 empty] | 0 | 0 | 0 | 0 | 0
| SSB | [8 empty] | 0 | 0 | 0 | 0 | 0
| TCMT | [8 empty] | 0 | 0 | 0 | 0 | 0
| A-Bay | [8 empty] | 0 | 0 | 0 | 0 | 0
Fog | RN | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
(hr) | B | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
| C | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
| E | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
| F | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
| G | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
| M | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
| SM-A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
| SM-B | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
| SM-D1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
| SM-D2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
| SSB | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
| TMCT | [8 empty] | 0 |  |  | 0 |  |  |  |  | 0
| A-Bay | [8 empty] | 0 |  |  | 0

## Weekly Raw Data (2) (hidden)
[9 empty] | Weekly sum |  |  | Weekly Daily Plan |  |  | Monthly cum |  |  |  | 2022-12-31 | -2
Class | Pit/Area | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Weekly |  |  | Jan |  |  | 2022-12-29 |  | 2022-12-31 |  | --> data end of month bulan sebelumnya
|  | 2022-12-30 | 2022-12-31 | 2023-01-01 | 2023-01-02 | 2023-01-03 | 2023-01-04 | 2023-01-05 | Actual | Plan | w/days | daily plan | daily plan | w/days | plan | actual | Plan | Actual
Waste | RN(Pama) | 55588 | 49283 |  |  |  |  | 52435.5 | 157306.5 | 143228 | 4 | 35807 |  |  | 1110000 | 1324458 | 1110000 | 1324458
(BCM) | RN(KMI) | [6 empty] | #DIV/0! | #DIV/0! | 8388 |  | 2097 |  |  | 65000 | 51880 | 65000 | 51880
| C/D | 64401 | 69662 |  |  |  |  | 67031.5 | 201094.5 | 338064 |  | 84516 |  |  | 2620000 | 2330018 | 2620000 | 2330018
| E/F | [6 empty] | #DIV/0! | #DIV/0! | 0
| G | 44652 | 34927 |  |  |  |  | 39789.5 | 119368.5 | 114840 |  | 28710 |  |  | 890000 | 943534 | 890000 | 943534
| RM(Pama) | 51863 | 33818 |  |  |  |  | 42840.5 | 128521.5 | 154840 |  | 38710 |  |  | 1200000 | 1188969 | 1200000 | 1188969
| RM(PTP) | [8 empty] | 0
| SM-A (SIMS) | 115265 | 58738 |  |  |  |  | 87001.5 | 261004.5 | 438840 |  | 109710 |  |  | 3401000 | 2587514 | 3401000 | 2587514
| SM-B(PTP) | 37560 | 29400 |  |  |  |  | 33480 | 100440 | 201292 |  | 50323 |  |  | 1560000 | 1067160 | 1560000 | 1067160
| SM-B(KMI) | [7 empty] | 0 | 0
| SM-D1 (PTP) | 213370 | 144080 |  |  |  |  | 178725 | 536175 | 638708 |  | 159677 |  |  | 4950000 | 4675675 | 4950000 | 4675675
| SM-D2 (DUM) | 11495 | [5 empty] | 11495 | 22990 | 36128 |  | 9032 |  |  | 280000 | 268169 | 280000 | 268169
| SSB | 35820 | 25577 |  |  |  |  | 30698.5 | 92095.5 | 127744 |  | 31936 |  |  | 990000 | 872146 | 990000 | 872146
| total | 630014 | 445485 | 0 | 0 | 0 | 0 | #DIV/0! | #DIV/0! | 2202072 |  | 550518 | 0 |  | 17066000 | 15309523 | 17066000 | 15309523
Coal | RTN(Petro) | [7 empty] | 0 | 0 | 4
(ton) | RTN(Pama) | 2726 | 1985 |  |  |  |  | 2355.5 | 7066.5 | 10324 |  | 2581 |  |  | 80000 | 73706 | 80000 | 73706
| RS_CD(Pama) | 10954 | 11715 |  |  |  |  | 11334.5 | 34003.5 | 38708 |  | 9677 |  |  | 300000 | 314377 | 300000 | 314377
| RS_EF(Pama) | [6 empty] | #DIV/0! | #DIV/0! | 0
| RS_G(Pama) | 1642 | 86 |  |  |  |  | 864 | 2592 | 12904 |  | 3226 |  |  | 100000 | 95512 | 100000 | 95512
| RM(Pama) | 9281 | 8656 |  |  |  |  | 8968.5 | 26905.5 | 37420 |  | 9355 |  |  | 290000 | 258783 | 290000 | 258783
| RM(Petro) | [7 empty] | 0 | 0
| SM-ABC(Sims) | 30206 | 21423 |  |  |  |  | 25814.5 | 77443.5 | 104516 |  | 26129 |  |  | 810000 | 705733 | 810000 | 705733
| SM-ABC(PTP) | 3929 | 4143 |  |  |  |  | 4036 | 12108 | 20644 |  | 5161 |  |  | 160000 | 117005 | 160000 | 117005
| SM-D(Petro) | 48995 | 32284 |  |  |  |  | 40639.5 | 121918.5 | 180644 |  | 45161 |  |  | 1400000 | 1214026 | 1400000 | 1214026
| SM-D(DUM) | [7 empty] | 0 | 0 |  |  |  |  | 0 |  | 0
| SSB(Bima) | 2652 | 2331 |  |  |  |  | 2491.5 | 7474.5 | 11612 |  | 2903 |  |  | 90000 | 82857 | 90000 | 82857
| total | 110385 | 82623 | 0 | 0 | 0 | 0 | #DIV/0! | #DIV/0! | 416772 |  | 104193 | 0 |  | 3230000 | 2861999 | 3230000 | 2861999
Rainfall | RN | [7 empty] | 0 |  |  | 0
(mm) | B | [7 empty] | 0 |  |  | 0
| C | [7 empty] | 0 |  |  | 0
| E | [7 empty] | 0 |  |  | 0
| F | [7 empty] | 0 |  |  | 0
| G | [7 empty] | 0 |  |  | 0
| M | [7 empty] | 0 |  |  | 0
| SM-A | [7 empty] | 0 |  |  | 0
| SM-B | [7 empty] | 0 |  |  | 0
| SM-D1 | [7 empty] | 0 |  |  | 0
| SM-D2 | [7 empty] | 0 |  |  | 0
| SSB | [7 empty] | 0 |  |  | 0
| TCMT | [7 empty] | 0 |  |  | 0
| A-Bay | [7 empty] | 0 |  |  | 0
Rain+Cleanup | RN | [7 empty] | 0 | 0 | 0 | 0 | 0
(hr) | B | [7 empty] | 0 | 0 | 0 | 0 | 0
*actual | C | [7 empty] | 0 | 0 | 0 | 0 | 0
| E | [7 empty] | 0 | 0 | 0 | 0 | 0
| F | [7 empty] | 0 | 0 | 0 | 0 | 0
| G | [7 empty] | 0 | 0 | 0 | 0 | 0
| M | [7 empty] | 0 | 0 | 0 | 0 | 0
| SM-A | [7 empty] | 0 | 0 | 0 | 0 | 0
| SM-B | [7 empty] | 0 | 0 | 0 | 0 | 0
| SM-D1 | [7 empty] | 0 | 0 | 0 | 0 | 0
| SM-D2 | [7 empty] | 0 | 0 | 0 | 0 | 0
| SSB | [7 empty] | 0 | 0 | 0 | 0 | 0
| TCMT | [7 empty] | 0 | 0 | 0 | 0 | 0
| A-Bay | [7 empty] | 0 | 0 | 0 | 0 | 0
Fog | RN | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
(hr) | B | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
| C | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
| E | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
| F | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
| G | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
| M | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
| SM-A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
| SM-B | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
| SM-D1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
| SM-D2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
| SSB | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
| TMCT | [7 empty] | 0 |  |  | 0 |  |  |  |  | 0
| A-Bay | [7 empty] | 0 |  |  | 0

## Slurry Removal Plan 2021 (hidden)
Plan Slurry Removal 2021
|  | 15200 |  | 5960 |  | 17800 |  | 12000 |  | 10080 |  | 17560 |  | 13100 |  |  |  |  | [Unit : Km3] |  | PAMA | Petrosea
Description |  | Y2020 Balance (Remainder) ⒜ | Y2021 |  |  |  |  | Jan | Feb | Mar | Apr | May | Jun |  | Aug | Sep | Oct | Nov | Dec |  | 39776 | 0
|  |  | New Slurry ⒝ | Total Slurry ⒜+⒝ | Plan Slurry Removal | Balance | [14 empty] | 42945 | 139800
SIMS | SM A1 | 87336 |  | 90480 |  | 116188 |  | Jan: 91695; Mar: 58028; May: 108233 | 91993.3333 | [5 empty] | -349949.3333 | 38511 | 117080
| SM A6 | 15700 |  | 15398 |  | 22117 |  | Jan: 25826; Mar: 3499; May: 22715 | 17542.5 | 100 | 100 | 100 |  |  | -69882.5 | 54835 | 154880
| SM A3 | 55198 |  | 40553 |  | 59063 |  | Jan: 41099; Mar: 28491; May: 44839 | 44873.8333 | [5 empty] | -159302.8333 | 41146 | 91680
| SMB | 32400 |  | 20400 |  | 35600 |  | Jan: 31120; Mar: 34240; May: 43360 | 32853.3333 | 100 | 100 | 100 | 100 | 100 | -142073.3333 | 34367 | 121040
|  | 190634 | 0 | 166831 | 0 | 232968 |  | 189740 | 0 | 124258 | 0 | 219147 | 0 |  | 200 | 200 | 200 | 100 | 100 | -533945 | 33293 | 85760
PAMA | RTS-C3 | 87843 |  | 79108 |  | 101034 |  | Jan: 89835; Mar: 41911; May: 92729 | 82076.6667 | 90 | 90 | 150 |  |  | -306881.6667 | 43276 | 129560
| RTS-D2 | 2861 |  | 620 |  | 2158 |  | Jan: 2042; Mar: 820; May: 1980 | 1746.8333 | 45 | 45 | 45 | 45 | 45 | -6813.8333 | 50221 | 155200
| RTS-G | 101760 |  | 62400 |  | 118040 |  | Jan: 100160; Mar: 72400; May: 134920 | 98280 | [5 empty] | -405760 | 32742 | 80960
| RTS-Gm | 20 | 20 | 40 | 20 | 20 | [12 empty] | 20 | 0 | 23671 | 60800
|  | 7203 |  | 23909 |  | 25998 |  | Jan: 20087; Mar: 27531; May: 31007 | 22622.5 | 135 | 135 | 195 | 45 | 65 | -101822.5 | 11004 | 57960
PTP | RTM | 1500 | 300 | 1800 | 1500 | 300 |  |  |  | 50 | 100 | 150 | 200 | 250 | 250 | 250 | 250 |  |  | 0
| SM-D1 | 2240 |  | 1261 |  | 1198 |  | Jan: 820; Mar: 756; May: 662 | 1156.1667 | [5 empty] | -3394.1667 | 0 | 0
| SM-D2 | 1000 | 200 | 1200 | 600 | 600 | [8 empty] | 100 | 150 | 150 | 100 | 100 | 0 | 0 | 0
|  | 4740 | 500 | 4261 | 2100 | 2098 |  | 820 | 0 | 806 | 100 | 812 | 200 |  | 350 | 400 | 400 | 100 | 100 | -1988 | 0 | 0
BIMA | SSB | 8849 |  | 9036 |  | 8844 |  | Jan: 7630; Mar: 7449; May: 12057 | 8977.5 | [5 empty] | -36113.5 | 0 | 0
TOTAL |  | 848 |  | 0 |  | 0 |  | Jan: 0; Mar: 0; May: 0 | 141.3333 | 685 | 735 | 795 | 245 | 265 | -2866.3333 | 0 | 0
|  | 4265 |  | 3948 |  | 6121 |  | Jan: 7345; Mar: 1648; May: 5412 | 4789.8333 | [6 empty] | 0 | 0
|  | 7906 |  | 5366 |  | 10650 |  | Jan: 10224; Mar: 6910; May: 9545 | 8433.5 | [6 empty] | 0 | 0
|  | 24034 |  | 20177 |  | 0 |  | Jan: 22847; Mar: 10383; May: 23735 | 16862.6667 | [6 empty] | 0 | 0
[21 empty] | 0 | 0
[21 empty] | 0 | 0
|  | 15671 |  | 9496 |  | 0 |  | Jan: 12095; Mar: 8305; May: 14393 | 9993.3333 | [6 empty] | 0 | 0
|  | 2128 |  | 1999 |  | 2719 |  | Jan: 961; Mar: 1804; May: 1894 | 1917.5 | [6 empty] | 0 | 0
|  | 0 |  | 1.5 |  | 1 |  | Jan: 0; Mar: 8.5; May: 1
|  | 1.5 |  | 23 |  | 3 |  | Jan: 0; Mar: 21.5; May: 6.5
|  | 3 |  | 44 |  | 2 |  | Jan: 0; Mar: 24; May: 5.5
|  | 4 |  | 33 |  | 2.5 |  | Jan: 0; Mar: 32; May: 5
|  | 0 |  | 32.5 |  | 2.5 |  | Jan: 0; Mar: 16.5; May: 6
|  | 0 |  | 52 |  | 2.5 |  | Jan: 0; Mar: 22.5; May: 7
|  | 0.5 |  | 1.5 |  | 1 |  | Jan: 0; Mar: 7; May: 1.5
|  | 0 |  | 2.5 |  | 2.5 |  | Jan: 3; Mar: 18; May: 7
|  | 0 |  | 1 |  | 4 |  | Jan: 4; Mar: 8; May: 7
|  | 13.5 |  | 19.5 |  | 1 |  | Jan: 0; Mar: 9; May: 0.5
|  | 0 |  | 0 |  | 0 |  | Jan: 0; Mar: 0; May: 0
|  | 9.5 |  | 0.5 |  | 0.5 |  | Jan: 8; Mar: 0; May: 1
|  | 6 | 0 | 11.3833 | 1.55 | 2.75 | 1.25 | 7.6667 | 0 | 7.55 | 3.9833 | 1.5 | 1.0167
|  | 7.2333 | 0 | 28.5 | 0.33333 | 1.9167 | 0.26667 | 7.5 | 0 | 8.0333 | 1.4167 | 0.81667 | 0.41667
|  | 7.3833 | 0 | 29.3 | 0.56667 | 1.35 | 0.38333 | 7.4167 | 0 | 7.9833 | 1.4333 | 0.5 | 0.63333
|  | 6.5167 | 0 | 4.8667 | 1.3167 | 2.05 | 0.63333 | 7.4667 | 0 | 17.25 | 0.96667 | 2.3833 | 0.31667
|  | 6.0667 | 0 | 5.6333 | 0.53333 | 1.4833 | 0.86667 | 7.95 | 0 | 6.0667 | 3 | 2.55 | 0.45
|  | 6.0667 | 0 | 5.6333 | 0.53333 | 1.4833 | 0.86667 | 7.95 | 0 | 6.0667 | 3 | 2.55 | 0.45
|  | 6.35 | 0.3 | 9.9167 | 1.5 | 2.6667 | 1.0833 | 7.5 | 0 | 7.2 | 2.7 | 1.5 | 1.1667
|  | 6 | 0 | 7.8167 | 1.1667 | 1.1667 | 0.45 | 7.8333 | 0 | 8.9333 | 1.6667 | 1 | 1.9333
|  | 6 | 0 | 7.5 | 4.2833 | 1 | 1.4167 | 7.0833 | 0 | 8.3333 | 4.7 | 0.75 | 1.5
|  | 6.2833 | 0.26667 | 10.1667 | 0.66667 | 1.4167 | 0.83333 | 7.3667 | 0 | 6.8333 | 2 | 0.91667 | 0.71667
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 4.4167 | 2.45 | 1.5 | 1.5 | 0.33333 | 0.66667 | 3.4333 | 3.5 | 3.9833 | 2.0167 | 1.4167 | 0.36667

## Sheet3 (hidden)
Month | PAMA | [6 empty] | SIMS | KMI |  | PTP |  |  |  | BIMA | DUM | AVG
| RTS-AD | RTS-EF | RTS-AF | RTS-G | RTN | RTM | SAMU/BIU | SM A | SM B | RTN | RTN | RTM | SM D | SM B | SSB | SM D
B/Plan | 3.504 | 3.504 | 3.504 | 3.113 | 2.699 | 5.168 | 1.371 | 4.057 | 3.958 | 2.699 | 2.699 | 5.168 | 3.765 | 4.585 | 1.895 | 2.502 | 3.663
Jan | 3.395 | 3.2984 | 3.3697 | 1.76 | 0 | 0 | 0 | 3.619 | 2.1454 | 0 | 2.4838 | 4.3242 | 3.3055 | 0 | 1.2274 | 0 | 3.1384
Feb | 3.4445 | 3.2929 | 3.3431 | 2.0059 | 0 | 0 | 0 | 4.0106 | 1.5103 | 0 | 2.6035 | 4.5341 | 3.4534 | 0 | 0.9561 | 0 | 3.2436
Mar | 3.3556 | 3.1393 | 3.2992 | 2.0237 | 0 | 0 | 0 | 4.2299 | 1.7414 | 0 | 2.4602 | 4.8234 | 3.0767 | 1.0567 | 0.96065 | 0 | 3.1405
Apr | 3.3153 | 3.0233 | 3.261 | 2.9238 | 1.5832 | 4.0903 | 0 | 3.8671 | 0 | 0.99785 | 0 | 0 | 3.0451 | 4.3013 | 1.0762 | 1.34 | 3.1733
May | 3.3567 | 3.3566 | 3.3567 | 3.857 | 1.731 | 4.037 | 0 | 3.5699 | 0 | 0.94219 | 0 | 0 | 2.8186 | 5.4742 | 1.082 | 1.4478 | 3.1832
Jun | 4.06 | 2.55 | 3.72 | 3.46 | 2.37 | 4.25 | 0 | 3.23 | 0 | 0.9 | 0 | 0 | 3.1 | 5.17 | 1.26 | 1.53 | 3.33
Jul
Aug
Sep
Oct
Nov
Dec
AVG | 3.3847 | 3.19 | 3.32 | 2.36 | 1.76 | 4.16 | 0 | 3.884 | 1.794 | 0.96838 | 2.5154 | 4.5732 | 3.13 | 4.89 | 1.08 | 0 | 3.21
DIFF | -0.11934 | -0.32 | -0.18 | -0.75 | -0.94 | -1.01 | -1.37 | -0.18 | -2.16 | -1.73 | -0.18 | -0.59 | -0.64 | 0.3 | -0.82 | -2.502 | -0.46