## Cover
Mine Site Batu Kajang, Kalimantan Timur
WEEKLY REPORT
21-27 May 2023
CONTENTS:
1. Planning Section
- Production Achievement
- Weather Condition
- Stock Exposed
- Hauling Distance
3. Safety Section
4. Administration Section
Production Department

## Planning Section
|  | PRODUCTION DEPARTMENT | [9 empty] | Departemen |  | Produksi
[12 empty] | No. Form |  | FM/PROD-027
[12 empty] | Tgl. Pembuatan |  | 2015-01-05
|  | ( SHORT REPORT ) | [9 empty] | No/Tgl. Revisi |  | 02/23-Sep-2018
TYPE | Occasional |  |  | Daily |  |  | Weekly |  |  | Monthly |  |  | Yearly
PIT | RTN | RTM | RTS-AF | RTS-G |  | SM A |  | SM B |  | SM D1 |  | SM D2 |  | SSB
CONTRACTOR | PAMA |  |  | SIMS | [5 empty] | PETROSEA |  |  | BIMA
SECTION | PLANNING |  |  | PIT CONTROL |  |  | PIT SERVICE |  |  | SAFETY |  |  | ADMIN
1. Periode |  | 21-27 May 2023
2. Week |  | 21.4286
* Production Achievement
>> Forecast (Based on Remain Day)
Class |  | Volume |  | Yearly (%) | Actual Day |  | Remain Day |  | Target/Day |  | Target/Week |  | Target/Month
Total Wa 2022 YTD |  | 60064145 |  | 32.37% | 143 |  | 214 |  | 586289.0421 |  | 4104023.2944 |  | 21692694.5561
Remain Target Wa 2022 |  | -125465855
Total Co 2022 YTD |  | 11696402.42 |  | 37.73% | 143 |  | 214 |  | 90203.727 |  | 631426.0891 |  | 3337537.8993
Remain Target Co 2022 |  | -19303597.58
>> Waste Removal (Source data : Daily Report Planning Department, Waste volume Jan-Apr based on Survey, Waste Volume May-Sept based on Trucking) | [14 empty] | Unit : Bcm
Pit | Contractor | Plan Y2023 | Weekly (A/Plan) |  |  | MTD (A/Plan) |  |  | YTD (B/Plan) |  |  | Remain Y2023 | Stripping Ratio (May 2022) |  |  |  |  | Y2022_Waste | Cal/Day | Act/Day |  |  |  | Y2021_Coal | Cal/Day | Act/Day |  | Work Schedule Coal Production (OFF SCHEDULE)
|  |  | Plan | Actual | ΔDiff | Plan | Actual | ΔDiff | Plan | Actual | ΔDiff |  | Plan | Actual | ΔDiff |  |  | Jan | 28 | 28 |  |  |  | Jan | 28 | 28 |  | Pit | Jan | [5 empty] | Feb |  |  |  | Mar |  |  |  | Apr |  |  |  | May | [5 empty] | Jun |  |  |  | Jul |  |  |  |  | Aug | [21 empty] | Sep | [11 empty] | Oct |  |  |  | Nov |  |  |  |  | Dec |  |  |  |  | TOTAL
RTN | PTP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | Feb | 28 | 28 |  |  |  | Feb | 28 | 28 |  |  | 1 | 2 | 9 | 16 | 23 | 30 | 7 | 14 | 21 | 28 | 7 | 14 | 21 | 28 | 4 | 11 | 18 | 25 | 2 | 9 | 13 | 16 | 23 | 30 | 6 | 13 | 20 | 27 | 4 | 11 | 18 | 20 | 25 | 1 | 2 | 3 | 7 | 8 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 6 | 11 | 12 | 13 | 14 | 20 | 26 | 27 | 4 | 11 | 18 | 25 | 1 | 8 | 15 | 22 | 29 | 6 | 13 | 20 | 25 | 27 |  |  | 31 | 31
RTN | PAMA | 8940000 | 191935.4839 | 104124 | -87811.4839 | 740322.6 | 542286 | -198036.6 | 3506774.1935 | 3352745 | -154029.1935 | -5587255 | 13.2813 | 11.1854 | -2.0958 |  |  | Mar | 31 | 31 |  |  |  | Mar | 31 | 31 |  | RTN | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [53 empty] | 3.5 | RTN | 27.5 | 29
RTN | KMI | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | Apr | 29 | 29 |  |  |  | Apr | 29 | 29 |  | RTM | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [53 empty] | 3.5 | RTM | 27.5 | 29
RS-CF | PAMA | 21680000 | 435354.8387 | 367538 | -67816.8387 | 1679225.8 | 1525820 | -153405.8 | 8490967.7419 | 7820407 | -670560.7419 | -13859593 | 9.181 | 7.1806 | -2.0003 |  |  | Mei | 31 | 27 |  |  |  | Mei | 31 | 27 |  | SM AB | 1 | 1 | 1 | 1 | 0.5 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [53 empty] | 6.5 | SM AB | 24.5 | 26
RS-G | PAMA | 9190000 | 211129.0323 | 215226 | 4096.9677 | 814354.8 | 709859 | -104495.8 | 3604193.5484 | 3330633 | -273560.5484 | -5859367 | 18.7 | 8.0942 | -10.6058 |  |  | Jun | 29 |  |  |  |  | Jun | 29 |  |  | RTS CF | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [53 empty] | 3.5 | RTS CF | 27.5 | 29
RTM | PTP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | Jul | 30 |  |  |  |  | Jul | 30 |  |  | RTS G | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [53 empty] | 3.5 | RTS G | 27.5 | 29
RTM | PAMA | 11310000 | 209774.1935 | 174224 | -35550.1935 | 809129 | 757445 | -51684 | 4429677.4194 | 3534090 | -895587.4194 | -7775910 | 5.3086 | 4.1678 | -1.1408 |  |  | Aug | 30 |  |  |  |  | Aug | 30 |  |  | SAMUBIU | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [53 empty] | 1.5 | SAMUBIU | 29.5 | 31
SSB | BIMA | 10180000 | 188096.7742 | 194630 | 6533.2258 | 725516.1 | 777538 | 52021.9 | 3992580.6452 | 3860546 | -132034.6452 | -6319454 | 11.9 | 10.058 | -1.842 |  |  | Sep | 30 |  |  |  |  | Sep | 30 |  |  | SM D | 1 | 1 | 1 | 1 | 0.5 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [53 empty] | 6.5 | SM D | 24.5 | 26
SAMUBIU | PAMA | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | Oct | 31 |  |  |  |  | Oct | 31 |  |  | SSB | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [53 empty] | 3.5 | SSB | 27.5 | 29
RS | S-Total | 61300000 | 1236290.3226 | 1055742 | -180548.3226 | 4768548.3 | 4312948 | -455600.3 | 24024193.5484 | 21898421 | -2125772.5484 | -39401579 | 9.6221 | 7.097 | -2.5252 |  |  | Nov | 30 |  |  |  |  | Nov | 30
SM AB | SIMS | 35350000 | 711290.3226 | 386757 | -324533.3226 | 2743548.4 | 1723720 | -1019828.4 | 13863548.3871 | 9607571 | -4255977.3871 | -25742429 | 4.3629 | 3.154 | -1.2088 |  |  | Dec | 30 |  |  |  |  | Dec | 30
SM 6 | PAMA | 13880000 | 306193.5484 | 247257 | -58936.5484 | 1181032.3 | 937947 | -243085.3 | 5440000 | 4883515 | -556485 | -8996485 | 1.8781 | 1.7162 | -0.16187 |  |  | Tot | 357 | 143 |  |  |  | Tot | 357 | 143
SM AB | PTP | 3120000 | 0 | 0 | 0 | 0 | 0 | 0 | 3120000 | 681129 | -2438871 | -2438871 | 0 | 0 | 0 |  |  | Tot | 357 | 143 |  |  |  | Tot | 357 | 143
SM AB | PAMA | 10250000 | 124193.5484 | 164804 | 40610.4516 | 479032.3 | 630838 | 151805.7 | 2126451.6129 | 1039979 | -1086472.6129 | -9210021 | 3.7671 | 9.6742 | 5.907 |  |  | Week | 51 | 20.4286 |  |  |  | Week | 51 | 20.4286
SM C | PAMA | 3000000 | 42903.2258 | 0 | -42903.2258 | 165483.9 | 0 | -165483.9 | 1165161.2903 | 0 | -1165161.2903 | -3000000 | 2.5 | 0 | -2.5
SM D | PTP | 55630000 | 1354838.7097 | 1154139 | -200699.7097 | 5225806.5 | 4331770 | -894036.5 | 21810000 | 19823321 | -1986679 | -35806679 | 4.7544 | 3.9123 | -0.84205
SM D | DUM | 3000000 | 59387.0968 | 74855 | 15467.9032 | 229064.5 | 281248 | 52183.5 | 1165161.2903 | 1195963 | 30801.7097 | -1804037 | 0 | 0 | 0
SM | S-Total | 124230000 | 2598806.4516 | 2027812 | -570994.4516 | 10023967.9 | 7905523 | -2118444.9 | 48690322.5806 | 37231478 | -11458844.5806 | -85194485 | 4.9909 | 4.4394 | -0.55147 | [11 empty] | 30.5714
Total |  | 185530000 | 3835096.7742 | 3083554 | -751542.7742 | 14792516.2 | 12218471 | -2574045.2 | 72714516.129 | 59129899 | -13584617.129 | -124596064 | 5.9075 | 5.1156 | -0.79187 | [5 empty] | 30.5714 | [5 empty] | Remain Week
Note : Prod plan (weekly, MTD, YTD) based on actual working day, production volume based on daily report planning dept.
Contractor |  | Plan Y2023 | Weekly (A/Plan) |  |  | MTD (A/Plan) |  |  | YTD (B/Plan) |  |  | Remain Y2023 | Stripping Ratio (May 2022)
|  |  | Plan | Actual | ΔDiff | Plan | Actual | ΔDiff | Plan | Actual | ΔDiff |  | Plan | Actual | ΔDiff
PAMA |  | 78250000 | 1521483.871 | 1273173 | -248310.871 | 5868580.7 | 5104195 | -764385.7 | 28763225.8065 | 23961369 | -4801856.8065 | -54288631 | 8.2071 | 7.7638 | -0.44329
PTP |  | 58750000 | 1354838.7097 | 1154139 | -200699.7097 | 5225806.5 | 4331770 | -894036.5 | 24930000 | 20504450 | -4425550 | -38245550 | 4.7544 | 3.9123 | -0.84205
SIMS |  | 35350000 | 711290.3226 | 386757 | -324533.3226 | 2743548.4 | 1723720 | -1019828.4 | 13863548.3871 | 9607571 | -4255977.3871 | -25742429 | 4.3629 | 3.154 | -1.2088
BIMA |  | 10180000 | 188096.7742 | 194630 | 6533.2258 | 725516.1 | 777538 | 52021.9 | 3992580.6452 | 3860546 | -132034.6452 | -6319454 | 11.9 | 10.058 | -1.842
DUM |  | 3000000 | 59387.0968 | 74855 | 15467.9032 | 229064.5 | 281248 | 52183.5 | 1165161.2903 | 1195963 | 30801.7097 | -1804037 | 0 | 0 | 0
KMI |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TBA |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total |  | 185530000 | 3835096.7742 | 3083554 | -751542.7742 | 14792516.2 | 12218471 | -2574045.2 | 72714516.129 | 59129899 | -13584617.129 | -126400101 | 5.9075 | 5.1156 | -0.79187
>> Coal Production (Source data : Daily Report Planning Department) | [14 empty] | Unit : Ton
Pit | Contractor | Plan Y2023 | Weekly (A/Plan) |  |  | MTD (A/Plan) |  |  | YTD (B/Plan) |  |  | Remain Y2023 | Stripping Ratio (YTD)
|  |  | Plan | Actual | ΔDiff | Plan | Actual | ΔDiff | Plan | Actual | ΔDiff |  | Plan | Actual | ΔDiff
RTN | PTP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
RTN | PAMA | 1110000 | 14451.6129 | 11068.2 | -3383.4129 | 55741.9 | 48481.4 | -7260.5 | 437096.7742 | 0 | -437096.7742 | -1110000 | 8.0229 | 0 | -8.0229
RTN | KMI | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
RS-CF | PAMA | 2320000 | 47419.3548 | 52950.8 | 5531.4452 | 182903.2 | 212491.4 | 29588.2 | 912903.2258 | 1416671.4 | 503768.1742 | -903328.6 | 9.3011 | 5.5203 | -3.7808
RS-G | PAMA | 1320000 | 11290.3226 | 17980.7 | 6690.3774 | 43548.4 | 87699.7 | 44151.3 | 524516.129 | 261929.7 | -262586.429 | -1058070.3 | 6.8715 | 12.7158 | 5.8443
RTM | PTP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
RTM | PAMA | 1950000 | 39516.129 | 39240.8 | -275.329 | 152419.4 | 181737.7 | 29318.3 | 758064.5161 | 895394.7 | 137330.1839 | -1054605.3 | 5.8434 | 3.947 | -1.8964
SSB | BIMA | 840000 | 15806.4516 | 21171.3 | 5364.8484 | 60967.7 | 77305.4 | 16337.7 | 330967.7419 | 388411.4 | 57443.6581 | -451588.6 | 12.0634 | 9.9393 | -2.124
SAMUBIU | PAMA | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
RS | S-Total | 7540000 | 128483.871 | 142411.8 | 13927.929 | 495580.6 | 607715.6 | 112135 | 2963548.3871 | 2962407.2 | -1141.1871 | -4577592.8 | 8.1066 | 7.3921 | -0.71446
SM AB | SIMS | 6440000 | 163032.2581 | 115160.3 | -47871.9581 | 628838.7 | 546510.6 | -82328.1 | 2516451.6129 | 2656478.6 | 140026.9871 | -3783521.4 | 5.5092 | 3.6167 | -1.8925
SM 6 | PAMA | 2630000 | 22580.6452 | 26818.1 | 4237.4548 | 87096.8 | 61818.7 | -25278.1 | 1010322.5806 | 115800.7 | -894521.8806 | -2514199.3 | 5.3844 | 42.1717 | 36.7873
SM AB | PTP | 570000 | 0 | 0 | 0 | 0 | 0 | 0 | 570000 | 117688 | -452312 | -452312 | 5.4737 | 5.7876 | 0.3139
SM AB | PAMA | 1830000 | 32967.7419 | 18171.5 | -14796.2419 | 127161.3 | 65208.6 | -61952.7 | 382903.2258 | 106783.6 | -276119.6258 | -1723216.4 | 5.5535 | 9.7391 | 4.1856
SM C | PAMA | 670000 | 17161.2903 | 0 | -17161.2903 | 66193.5 | 0 | -66193.5 | 252258.0645 | 0 | -252258.0645
SM D | PTP | 11320000 | 284967.7419 | 275758.9 | -9208.8419 | 1099161.3 | 1107215.21 | 8053.91 | 4962258.0645 | 4863286.21 | -98971.8545 | -6456713.79 | 4.3952 | 4.0761 | -0.31906
SM D | DUM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SM | S-Total | 23460000 | 520709.6774 | 435908.8 | -84800.8774 | 2008451.6 | 1780753.11 | -227698.49 | 9694193.5484 | 7860037.11 | -1834156.4384 | -14929962.89 | 5.0226 | 4.7368 | -0.28582
Total |  | 31000000 | 649193.5484 | 578320.6 | -70872.9484 | 2504032.2 | 2388468.71 | -115563.49 | 12657741.9355 | 10822444.31 | -1835297.6255 | -19507555.69 | 5.7447 | 5.4636 | -0.28103
Note : Prod plan (weekly, MTD, YTD) based on actual working day, production volume based on daily report planning dept.
Contractor |  | Plan Y2023 | Weekly (A/Plan) |  |  | MTD (A/Plan) |  |  | YTD (B/Plan) |  |  | Remain Y2023 | Stripping Ratio (YTD)
|  |  | Plan | Actual | ΔDiff | Plan | Actual | ΔDiff | Plan | Actual | ΔDiff |  | Plan | Actual | ΔDiff
PAMA |  | 11830000 | 185387.0968 | 166230.1 | -19156.9968 | 715064.5 | 657437.5 | -57627 | 4278064.5161 | 2796580.1 | -1481484.4161 | -9033419.9 | 6.7234 | 8.5681 | 1.8447
PTP |  | 11890000 | 284967.7419 | 275758.9 | -9208.8419 | 1099161.3 | 1107215.21 | 8053.91 | 5532258.0645 | 4980974.21 | -551283.8545 | -6909025.79 | 4.5063 | 4.1166 | -0.38974
SIMS |  | 6440000 | 163032.2581 | 115160.3 | -47871.9581 | 628838.7 | 546510.6 | -82328.1 | 2516451.6129 | 2656478.6 | 140026.9871 | -3783521.4 | 5.5092 | 3.6167 | -1.8925
BIMA |  | 840000 | 15806.4516 | 21171.3 | 5364.8484 | 60967.7 | 77305.4 | 16337.7 | 330967.7419 | 388411.4 | 57443.6581 | -451588.6 | 12.0634 | 9.9393 | -2.124
DUM |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | #DIV/0!
TBA |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total |  | 31000000 | 649193.5484 | 578320.6 | -70872.9484 | 2504032.2 | 2388468.71 | -115563.49 | 12657741.9355 | 10822444.31 | -1835297.6255 | -20177555.69 | 5.7447 | 5.4636 | -0.28103
>> Coal Hauling (Source data : Daily Report Planning Department) | [11 empty] | Unit : Ton
Contractor |  | Plan Y2023 | Daily |  |  | MTD |  |  | YTD |  |  | Remain Y2023
|  |  | Plan | Actual | ΔDiff | Plan | Actual | ΔDiff | Plan | Actual | ΔDiff
SUK |  |  | 41379.3 | 40143 | -1236.3 | 1055172.4 | 982853 | -72319.4 | 4808103.4483 | 4722499 | -85604.4483 | 4722499
TMP |  |  | 36206.9 | 37445 | 1238.1 | 923275.9 | 937119 | 13843.1 | 4808103.4483 | 4462084 | -346019.4483 | 4462084
MHA |  |  | 21551.7 | 23875 | 2323.3 | 549569 | 511582 | -37987 | 2798793.1034 | 2494499 | -304294.1034 | 2494499
Total |  | 0 | 99137.9 | 101463 | 2325.1 | 2528017.3 | 2431554 | -96463.3 | 12415000 | 11679082 | -735918 | 11679082
Note : Prod plan (weekly, MTD, YTD) based on actual working day, production volume based on daily report planning dept.
* Weather Condition | [14 empty] | Unit : mm ; x ; Hrs
Pit | Contractor | Weekly |  |  |  |  | MTD |  |  |  |  | YTD
|  | Quantity | Freq | Rain | Clean Up | Fog | Qty | Freq | Rain | Clean Up | Fog | Qty | Rain | Clean Up | Fog
RTN | PAMA | 185.5 | 7 | 32.65 | 9.3833 | 0 | 311 | 26 | 90.4667 | 34.1 | 0 | 1111.6401 | 439.75 | 169.4667 | 22.75
RTS-AB | PAMA | 159.5 | 5 | 30.4 | 6.1 | 0 | 276.5 | 25 | 92.9333 | 29.3667 | 0 | 1066.0301 | 474.3333 | 190.5167 | 32
RTS-CD | PAMA | 134 | 5 | 30.3 | 7.8333 | 0 | 222.5 | 26 | 93.35 | 32.75 | 0 | 1144.5101 | 473.05 | 176.9833 | 34.2833
RTS-EF | PAMA | 121 | 4 | 26.6 | 9.3667 | 0 | 203.5 | 26 | 104.0333 | 39.2833 | 3.5 | 1219.8851 | 599.45 | 155.8417 | 5.5667
RTS-G | PAMA | 120.5 | 4 | 26.6 | 9.3667 | 0 | 207 | 26 | 103.8667 | 39.3333 | 3.5 | 1230.5101 | 669.5167 | 170.35 | 11.8833
RTM | PAMA | 168.5 | 6 | 29 | 19.45 | 0 | 285.5 | 26 | 94.6667 | 35.4 | 1.25 | 1081.2101 | 577.6167 | 91.9333 | 0.98333
SSB | BIMA | 5.5 | 3 | 8.1833 | 2.8833 | 0 | 198.5 | 22 | 47.8333 | 17.8333 | 0 | 1079.9201 | 337.3 | 124.4 | 0
SM 6 | PAMA | 135 | 7 | 33.4333 | 13.1 | 0 | 293.5 | 28 | 102.6167 | 46.4667 | 1.6833 | 1079.9201 | 337.3 | 124.4 | 0
SM A | SIMS | 102 | 6 | 23.95 | 14.5833 | 1.9333 | 254.5 | 37 | 94.6667 | 65.25 | 4.9833 | 742 | 439.2167 | 166.3667 | 7.0167
SM B | PAMA | 110 | 9 | 31.6333 | 20.9 | 20.9333 | 281 | 42 | 106.5 | 75.6333 | 25.1 | 797.14 | 460.6667 | 227.7167 | 7.8167
SM D | PTP | 29 | 3 | 13 | 3.5 | 0 | 300.5 | 20 | 59.05 | 20.0833 | 0 | 1210.8101 | 390.2333 | 110.0333 | 0
Average |  | 115.5 | 5.3636 | 25.9773 | 10.5879 | 11.4333 | 257.6364 | 27.6364 | 89.9985 | 39.5909 | 6.6694 | 1069.416 | 472.5848 | 155.2735 | 15.2875
Note :
* Stock Exposed | [12 empty] | Unit : Ton
Class | PAMA | [6 empty] | SIMS |  |  | PTP |  | SSB | Total
| RTN | RTM | CD | EF | G | #6 | B | A | #6,8 | B | D1 | D2
Exposed | 4719 | 6552 | 12480 | 0 | 3640 | 3900 | 10016.5 | 0 | 38610 | 0 | 170881.1 |  | 2592.72 | 253391.32
Ready | 3630.9 | 5779.8 | 5434 | 0 | 2593.5 | 2420.925 | 5833.1877 | 0 | 16672.5 | 0 | 40584.2612 |  | 2141.1 | 85090.174
* Hauling Distance | [13 empty] | Unit : m
Item | PAMA | [5 empty] | SIMS |  | PTP |  | PTP |  | DUM | BIMA
| RTS-CD | RTS-G | RTN | RTM | SM 6 | SM B | SM AB | SM B | RTN | RTM | SM D | SM B | SM D | SSB
Waste | 3304.011 | 6727.3328 | 2053.3424 | 3961.1892 | 4453.3211 | 5736.8348 | 4561.7935 |  |  |  | 3606.3253 | 6354.5818 | 2099.0034 | 1338.3702
* Coal Committee Activity
Issues
2022-01-01
>> Waste | [10 empty] | Unit : Bcm |  | >> Coal | [10 empty] | Unit : Ton
Area | Cont. | B/Plan | A/Plan | W/Day | Plan/Day | Act. Day | Remain Day | Plan (MTD) B/Plan | Plan (MTD) A/Plan | Act. (MTD) | Diff (MTD) |  | Contractor | Area | B/Plan | A/Plan | W/Day | Plan/Day | Act. Day | Remain Day | Plan (MTD) B/Plan | Plan (MTD) | Act. (MTD) | Diff (MTD)
RTN | PTP |  |  | 28 | 0 | 28 | 0 | 0 | 0 | 0 | 0 |  | RTN | PTP |  |  | 28 | 0 | 28 | 0 | 0 | 0 | 0 | 0
RTN | PAMA | 690000 | 800000 | 28 | 28571.4286 | 28 | 0 | 690000 | 800000 | 793633 | -6367 |  | RTN | PAMA | 90000 | 70000 | 28 | 2500 | 28 | 0 | 90000 | 70000 | 54950 | -15050
RTN | KMI |  |  | 28 | 0 | 28 | 0 | 0 | 0 | 0 | 0 |  | RTN | KMI |  |  | 28 | 0 | 28 | 0 | 0 | 0 | 0 | 0
RS-CF | PAMA | 1680000 | 1490000 | 28 | 53214.2857 | 28 | 0 | 1680000 | 1490000 | 1782699 | 292699 |  | RS-CF | PAMA | 180000 | 240000 | 28 | 8571.4286 | 28 | 0 | 180000 | 240000 | 272378 | 32378
RS-G | PAMA | 710000 | 870000 | 28 | 31071.4286 | 28 | 0 | 710000 | 870000 | 789952 | -80048 |  | RS-G | PAMA | 100000 | 50000 | 28 | 1785.7143 | 28 | 0 | 100000 | 50000 | 36986 | -13014
RTM | PTP |  |  | 28 | 0 | 28 | 0 | 0 | 0 |  | 789952 |  | RTM | PTP |  |  | 28 | 0 | 28 | 0 | 0 | 0 | 0 | 0
RTM | PAMA | 880000 | 1100000 | 28 | 39285.7143 | 28 | 0 | 880000 | 1100000 | 979884 | -120116 |  | RTM | PAMA | 150000 | 150000 | 28 | 5357.1429 | 28 | 0 | 150000 | 150000 | 202480 | 52480
SSB | BIMA | 790000 | 810000 | 28 | 28928.5714 | 28 | 0 | 790000 | 810000 | 832509 | 22509 |  | SSB | BIMA | 70000 | 80000 | 28 | 2857.1429 | 28 | 0 | 70000 | 80000 | 73819 | -6181
SAMUBIU | PAMA |  |  | 28 | 0 | 28 | 0 | 0 | 0 | 0 | 0 |  | SAMUBIU | PAMA |  |  | 28 | 0 | 28 | 0 | 0 | 0 | 0 | 0
RS | S-Total | 4750000 | 5070000 |  | 181071.4286 |  |  | 4750000 | 5070000 | 5178677 | 898629 |  | Roto | S-Tot | 590000 | 590000 |  | 21071.4286 |  |  | 590000 | 590000 | 640613 | 50613
SM AB | SIMS | 2740000 | 2740000 | 28 | 97857.1429 | 28 | 0 | 2740000 | 2740000 | 2717779 | -22221 |  | SM AB | SIMS | 500000 | 600000 | 28 | 21428.5714 | 28 | 0 | 500000 | 600000 | 647737 | 47737
SM 6 | PAMA | 1080000 | 780000 | 28 | 27857.1429 | 28 | 0 | 1080000 | 780000 | 1001958 | 221958 |  | SM 6 | PAMA | 200000 | 30000 | 28 | 1071.4286 | 28 | 0 | 200000 | 30000 | 7127 | -22873
SM AB | PTP | 1040000 | 290000 | 28 | 10357.1429 | 28 | 0 | 1040000 | 290000 | 264000 | -26000 |  | SM AB | PTP | 190000 | 50000 | 28 | 1785.7143 | 28 | 0 | 190000 | 50000 | 82506 | 32506
SM AB | KMI |  |  | 28 | 0 | 28 | 0 | 0 | 0 |  | 0 |  | SM AB | KMI |  |  | 28 | 0 | 28 | 0 | 0 | 0 |  | 0
SM C | PTP | 230000 |  | 28 | 0 | 28 | 0 | 230000 | 0 |  | 0 |  | SM C | PTP | 50000 |  | 28 | 0 | 28 | 0 | 50000 | 0 | 0 | 0
SM D | PTP | 4320000 | 4400000 | 28 | 157142.8571 | 28 | 0 | 4320000 | 4400000 | 4637234 | 237234 |  | SM D | PTP | 1050000 | 1100000 | 28 | 39285.7143 | 28 | 0 | 1050000 | 1100000 | 1025342 | -74658
SM D | DUM | 230000 | 230000 | 28 | 8214.2857 | 28 | 0 | 230000 | 230000 | 287364 | 57364 |  | SM D | DUM |  |  | 28 | 0 | 28 | 0 | 0 | 0 |  | 0
SM | S-Total | 9640000 | 8440000 |  | 301428.5714 |  |  | 9410000 | 8210000 | 8908335 | 410971 |  | SM | S-Tot | 1990000 | 1780000 |  | 63571.4286 |  |  | 1990000 | 1780000 | 1762712 | -17288
Total |  | 14390000 | 13510000 |  | 482500 |  |  | 14160000 | 13280000 | 14087012 | 1309600 |  | Grand Total |  | 2580000 | 2370000 |  | 84642.8571 |  |  | 2580000 | 2370000 | 2403325 | 33325
2022-02-01
>> Waste | [10 empty] | Unit : KBcm |  | >> Coal | [10 empty] | Unit : Ton
Area | Cont. | B/Plan | A/Plan | W/Day | Plan/Day | Act. Day | Remain Day | Plan (MTD) B/Plan | Plan (MTD) A/Plan | Act. (MTD) | Diff (MTD) |  | Contractor | Area | B/Plan | A/Plan | W/Day | Plan/Day | Act. Day | Remain Day | Plan (MTD) B/Plan | Plan (MTD) A/Plan | Act. (MTD) | Diff (MTD)
RTN | PTP |  |  | 28 | 0 | 28 | 0 | 0 | 0 | 0 | 0 |  | RTN | PTP | 0 | 0 | 28 | 0 | 28 | 0 | 0 | 0 | 0 | 0
RTN | PAMA | 660000 | 710000 | 28 | 25357.1429 | 28 | 0 | 660000 | 710000 | 791123 | 81123 |  | RTN | PAMA | 80000 | 50000 | 28 | 1785.7143 | 28 | 0 | 80000 | 50000 | 50779 | 779
RTN | KMI |  |  | 28 | 0 | 28 | 0 | 0 | 0 | 0 | 0 |  | RTN | KMI | 0 | 0 | 28 | 0 | 28 | 0 | 0 | 0 | 0 | 0
RS-CD | PAMA | 1600000 | 1700000 | 28 | 60714.2857 | 28 | 0 | 1600000 | 1700000 | 1677719 | -22281 |  | RS-CD | PAMA | 170000 | 200000 | 28 | 7142.8571 | 28 | 0 | 170000 | 200000 | 322351 | 122351
RS-G | PAMA | 680000 | 870000 | 28 | 31071.4286 | 28 | 0 | 680000 | 870000 | 681486 | -188514 |  | RS-G | PAMA | 100000 | 70000 | 28 | 2500 | 28 | 0 | 100000 | 70000 | 67565 | -2435
RTM | PTP |  |  | 28 | 0 | 28 | 0 | 0 | 0 | 0 | 0 |  | RTM | PTP | 0 | 0 | 28 | 0 | 28 | 0 | 0 | 0 | 0 | 0
RTM | PAMA | 830000 | 710000 | 28 | 25357.1429 | 28 | 0 | 830000 | 710000 | 661856 | -48144 |  | RTM | PAMA | 140000 | 160000 | 28 | 5714.2857 | 28 | 0 | 140000 | 160000 | 181076 | 21076
SSB | BIMA | 750000 | 750000 | 28 | 26785.7143 | 28 | 0 | 750000 | 750000 | 732746 | -17254 |  | SSB | BIMA | 60000 | 70000 | 28 | 2500 | 28 | 0 | 60000 | 70000 | 87084 | 17084
SAMUBIU | PAMA |  |  | 28 | 0 | 28 | 0 | 0 | 0 | 0 | 0 |  | SAMUBIU | PAMA | 0 |  | 28 | 0 | 28 | 0 | 0 | 0 | 0 | 0
Roto | S-Tot | 4520000 | 4740000 |  | 169285.7143 |  |  | 4520000 | 4740000 | 4544930 | -195070 |  | Roto | S-Tot | 550000 | 550000 |  | 19642.8571 |  |  | 550000 | 550000 | 708855 | 158855
SM AB | SIMS | 2610000 | 2610000 | 28 | 93214.2857 | 28 | 0 | 2610000 | 2610000 | 2297729 | -312271 |  | SM AB | SIMS | 470000 | 580000 | 28 | 20714.2857 | 28 | 0 | 470000 | 580000 | 613388 | 33388
SM 6 | PAMA | 1020000 | 900000 | 28 | 32142.8571 | 28 | 0 | 1020000 | 900000 | 977822 | 77822 |  | SM 6 | PAMA | 190000 | 60000 | 28 | 2142.8571 | 28 | 0 | 190000 | 60000 | 0 | -60000
SM AB | PTP | 990000 | 270000 | 28 | 9642.8571 | 28 | 0 | 990000 | 270000 | 235440 | -34560 |  | SM AB | PTP | 180000 | 50000 | 28 | 1785.7143 | 28 | 0 | 180000 | 50000 | 35182 | -14818
SM AB | KMI |  |  | 28 | 0 | 28 | 0 | 0 | 0 | 0 | 0 |  | SM AB | KMI | 0 | 0 | 28 | 0 | 28 | 0 | 0 | 0 | 0 | 0
SM C | PTP | 220000 | [7 empty] | 0 |  |  | SM C | PTP | 50000 |  | 28 | 0 | 28 | 0 | 50000 | 0 | 0 | 0
SM D | PTP | 4100000 | 4280000 | 28 | 152857.1429 | 28 | 0 | 4100000 | 4280000 | 3854173 | -425827 |  | SM D | PTP | 980000 | 990000 | 28 | 35357.1429 | 28 | 0 | 980000 | 990000 | 931872 | -58128
SM D | DUM | 220000 | 240000 | 28 | 8571.4286 | 28 | 0 | 220000 | 240000 | 234982 | -5018 |  | SM D | DUM | 0 |  | 28 | 0 | 28 | 0 | 0 | 0 |  | 0
SM | S-Tot | 9160000 | 8300000 |  | 296428.5714 |  |  | 8940000 | 8300000 | 7600146 | -699854 |  | SM | S-Tot | 1870000 | 1680000 |  | 60000 |  |  | 1870000 | 1680000 | 1580442 | -99558
Grand Total |  | 13680000 | 13040000 |  | 465714.2857 |  |  | 13460000 | 13040000 | 12145076 | -894924 |  | Grand Total |  | 2420000 | 2230000 |  | 79642.8571 |  |  | 2420000 | 2230000 | 2289297 | 59297
2022-03-04
>> Waste | [10 empty] | Unit : KBcm |  | >> Coal | [10 empty] | Unit : Ton
Cont. | Area | B/Plan | A/Plan | W/Day | Plan/Day | Act. Day | Remain Day | Plan (MTD) B/Plan | Plan (MTD) A/Plan | Act. (MTD) | Diff (MTD) |  | Contractor | Area | B/Plan | A/Plan | W/Day | Plan/Day | Act. Day | Remain Day | Plan (MTD) B/Plan | Plan (MTD) A/Plan | Act. (MTD) | Diff (MTD)
RTN | PTP | 0 | 0 | 31 | 0 | 31 | 0 | 0 | 0 | 0 | 0 |  | RTN | PTP | 0 | 0 | 31 | 0 | 31 | 0 | 0 | 0 | 0 | 0
RTN | PAMA | 730000 | 850000 | 31 | 27419.3548 | 31 | 0 | 730000 | 850000 | 740367 | -109633 |  | RTN | PAMA | 90000 | 50000 | 31 | 1612.9032 | 31 | 0 | 90000 | 50000 | 73383 | 23383
RTN | KMI | 0 | 0 | 31 | 0 | 31 | 0 | 0 | 0 | 0 | 0 |  | RTN | KMI | 0 | 0 | 31 | 0 | 31 | 0 | 0 | 0 | 0 | 0
RS-CF | PAMA | 1760000 | 1760000 | 31 | 56774.1935 | 31 | 0 | 1760000 | 1760000 | 1613054 | -146946 |  | RS-CF | PAMA | 190000 | 250000 | 31 | 8064.5161 | 31 | 0 | 190000 | 250000 | 319948 | 69948
RS-G | PAMA | 750000 | 750000 | 31 | 24193.5484 | 31 | 0 | 750000 | 750000 | 590559 | -159441 |  | RS-G | PAMA | 110000 | 70000 | 31 | 2258.0645 | 31 | 0 | 110000 | 70000 | 34543 | -35457
RTM | PTP | 0 |  | 31 | 0 | 31 | 0 | 0 | 0 | 0 | 0 |  | RTM | PTP | 0 | 0 | 31 | 0 | 31 | 0 | 0 | 0 | 0 | 0
RTM | PAMA | 920000 | 800000 | 31 | 25806.4516 | 31 | 0 | 920000 | 800000 | 706215 | -93785 |  | RTM | PAMA | 160000 | 160000 | 31 | 5161.2903 | 31 | 0 | 160000 | 160000 | 167084 | 7084
SSB | BIMA | 830000 | 830000 | 31 | 26774.1935 | 31 | 0 | 830000 | 830000 | 805070 | -24930 |  | SSB | BIMA | 70000 | 70000 | 31 | 2258.0645 | 31 | 0 | 70000 | 70000 | 73279 | 3279
SAMUBIU | PAMA | 0 | 0 | 31 | 0 | 31 | 0 | 0 | 0 | 0 | 0 |  | SAMUBIU | PAMA | 0 | 0 | 31 | 0 | 31 | 0 | 0 | 0 | 0 | 0
Roto | S-Tot | 4990000 | 4990000 |  | 160967.7419 |  |  | 4990000 | 4990000 | 4455265 | -534735 |  | Roto | S-Tot | 620000 | 600000 |  | 19354.8387 |  |  | 620000 | 600000 | 668237 | 68237
SM AB | SIMS | 2880000 | 2880000 | 31 | 92903.2258 | 31 | 0 | 2880000 | 2880000 | 2245542 | -634458 |  | SM AB | SIMS | 520000 | 660000 | 31 | 21290.3226 | 31 | 0 | 520000 | 660000 | 657249 | -2751
SM 6 | PAMA | 1130000 | 1130000 | 31 | 36451.6129 | 31 | 0 | 1130000 | 1130000 | 954411 | -175589 |  | SM 6 | PAMA | 210000 | 75000 | 31 | 2419.3548 | 31 | 0 | 210000 | 75000 | 7388 | -67612
SM AB | PTP | 1090000 | 1000000 | 31 | 32258.0645 | 31 | 0 | 1090000 | 1000000 | 182680 | -817320 |  | SM AB | PTP | 200000 | 120000 | 31 | 3870.9677 | 31 | 0 | 200000 | 120000 | 0 | -120000
SM AB | KMI | 0 | 0 | 31 | 0 | 31 | 0 | 0 | 0 | 0 | 0 |  | SM AB | KMI | 0 | 0 | 31 | 0 | 31 | 0 | 0 | 0 | 0 | 0
SM C | PTP | 240000 | 0 | [6 empty] | 0 |  |  | SM C | PTP | 50000 | 0 | 31 | 0 | 31 | 0 | 50000 | 0 | 0 | 0
SM D | PTP | 4530000 | 4530000 | 31 | 146129.0323 | 31 | 0 | 4530000 | 4530000 | 3656424 | -873576 |  | SM D | PTP | 1060000 | 1080000 | 31 | 34838.7097 | 31 | 0 | 1060000 | 1080000 | 893969 | -186031
SM D | DUM | 240000 | 240000 | 31 | 7741.9355 | 31 | 0 | 240000 | 240000 | 180290 | -59710 |  | SM D | DUM | 0 | 0 | 31 | 0 | 31 | 0 | 0 | 0 | 0 | 0
SM | S-Tot | 10110000 | 9780000 |  | 315483.871 |  |  | 9870000 | 9780000 | 7219347 | -2560653 |  | SM | S-Tot | 2040000 | 1935000 |  | 62419.3548 |  |  | 2040000 | 1935000 | 1558606 | -376394
Grand Total |  | 15100000 | 14770000 |  | 476451.6129 |  |  | 14860000 | 14770000 | 11674612 | -3095388 |  | Grand Total |  | 2660000 | 2535000 |  | 81774.1935 |  |  | 2660000 | 2535000 | 2226843 | -308157
2022-04-03
>> Waste | [10 empty] | Unit : KBcm |  | >> Coal | [10 empty] | Unit : Kton
Cont. | Area | B/Plan | A/Plan | W/Day | Plan/Day | Act. Day | Remain Day | Plan (MTD) B/Plan | Plan (MTD) A/Plan | Act. (MTD) | Diff (MTD) |  | Contractor | Area | B/Plan | A/Plan | W/Day | Plan/Day | Act. Day | Remain Day | Plan (MTD) B/Plan | Plan (MTD) A/Plan | Act. (MTD) | Diff (MTD)
RTN | PTP | 0 | 0 | 29 | 0 | 29 | 0 | 0 | 0 | 0 | 0 |  | RTN | PTP | 0 | 0 | 29 | 0 | 29 | 0 | 0 | 0 | 0 | 0
RTN | PAMA | 730000 | 748000 | 29 | 25793.1034 | 29 | 0 | 730000 | 748000 | 593829 | -154171 |  | RTN | PAMA | 90000 | 70000 | 29 | 2413.7931 | 29 | 0 | 90000 | 70000 | 48481.4 | -21518.6
RTN | KMI | 0 |  | 29 | 0 | 29 | 0 | 0 | 0 | 0 | 0 |  | RTN | KMI | 0 | 0 | 29 | 0 | 29 | 0 | 0 | 0 | 0 | 0
RS-CF | PAMA | 1760000 | 1758000 | 29 | 60620.6897 | 29 | 0 | 1760000 | 1758000 | 1420111 | -337889 |  | RS-CF | PAMA | 190000 | 200000 | 29 | 6896.5517 | 29 | 0 | 190000 | 200000 | 212491.4 | 12491.4
RS-G | PAMA | 750000 | 776000 | 29 | 26758.6207 | 29 | 0 | 750000 | 776000 | 591230 | -184770 |  | RS-G | PAMA | 110000 | 70000 | 29 | 2413.7931 | 29 | 0 | 110000 | 70000 | 87699.7 | 17699.7
RTM | PTP | 0 |  | 29 | 0 | 29 | 0 | 0 | 0 | 0 | 0 |  | RTM | PTP |  |  | 29 | 0 | 29 | 0 | 0 | 0 | 0 | 0
RTM | PAMA | 920000 | 920000 | 29 | 31724.1379 | 29 | 0 | 920000 | 920000 | 653695 | -266305 |  | RTM | PAMA | 160000 | 170000 | 29 | 5862.069 | 29 | 0 | 160000 | 170000 | 181737.7 | 11737.7
SSB | BIMA | 830000 | 831000 | 29 | 28655.1724 | 29 | 0 | 830000 | 831000 | 798360 | -32640 |  | SSB | BIMA | 70000 | 70000 | 29 | 2413.7931 | 29 | 0 | 70000 | 70000 | 77305.4 | 7305.4
SAMUBIU | PAMA | 0 |  | 29 | 0 | 29 | 0 | 0 | 0 | 0 | 0 |  | SAMUBIU | PAMA | 0 | 0 | 29 | 0 | 29 | 0 | 0 | 0 | 0 | 0
Roto | S-Tot | 4990000 | 5033000 |  | 173551.7241 |  |  | 4990000 | 5033000 | 4057225 | -975775 |  | Roto | S-Tot | 620000 | 580000 |  | 20000 |  |  | 620000 | 580000 | 607715.6 | 27715.6
SM AB | SIMS | 2890000 | 3198000 | 29 | 110275.8621 | 29 | 0 | 2890000 | 3198000 | 681585 | -2516415 |  | SM AB | SIMS | 530000 | 700000 | 29 | 24137.931 | 29 | 0 | 530000 | 700000 | 546510.6 | -153489.4
SM 6 | PAMA | 1130000 | 1229000 | 29 | 42379.3103 | 29 | 0 | 1130000 | 1229000 | 817837 | -411163 |  | SM 6 | PAMA | 210000 | 100000 | 29 | 3448.2759 | 29 | 0 | 210000 | 100000 | 61818.7 | -38181.3
SM AB | PTP | 0 | 0 | 29 | 0 | 29 | 0 | 0 | 0 | 0 | 0 |  | SM AB | PTP |  |  | 29 | 0 | 29 | 0 | 0 | 0 | 0 | 0
SM AB | PAMA | 1090000 | 450000 | 29 | 15517.2414 | 29 | 0 | 1090000 | 450000 | 409141 | -40859 |  | SM AB | PAMA | 200000 | 60000 | 29 | 2068.9655 | 29 | 0 | 200000 | 60000 | 65208.6 | 5208.6
SM C | PAMA | 240000 | 0 | [6 empty] | 0 | 0 |  | SM C | PAMA | 50000 | 0 | 29 | 0 | 29 | 0 | 50000 | 0 | 0 | 0
SM D | PTP | 4540000 | 4800000 | 29 | 165517.2414 | 29 | 0 | 4540000 | 4800000 | 3750436 | -1049564 |  | SM D | PTP | 1010000 | 1124000 | 29 | 38758.6207 | 29 | 0 | 1010000 | 1124000 | 1107215.21 | -16784.79
SM D | DUM | 240000 | 241000 | 29 | 8310.3448 | 29 | 0 | 240000 | 241000 | 222750 | -18250 |  | SM D | DUM | 0 | 0 | 29 | 0 | 29 | 0 | 0 | 0 | 0 | 0
SM | S-Tot | 10130000 | 9918000 |  | 342000 |  |  | 9890000 | 9918000 | 5881749 | -4036251 |  | SM | S-Tot | 2000000 | 1984000 |  | 68413.7931 |  |  | 2000000 | 1984000 | 1780753.11 | -203246.89
Grand Total |  | 15120000 | 14951000 |  | 515551.7241 |  |  | 14880000 | 14951000 | 9938974 | -5012026 |  | Grand Total |  | 2620000 | 2564000 |  | 88413.7931 |  |  | 2620000 | 2564000 | 2388468.71 | -175531.29
2022-05-04
>> Waste | [10 empty] | Unit : KBcm |  | >> Coal | [10 empty] | Unit : KTon
Cont. | Area | B/Plan | A/Plan | W/Day | Plan/Day | Act. Day | Remain Day | Plan (MTD) B/Plan | Plan (MTD) A/Plan | Act. (MTD) | Diff (MTD) |  | Contractor | Area | B/Plan | A/Plan | W/Day | Plan/Day | Act. Day | Remain Day | Plan (MTD) B/Plan | Plan (MTD) A/Plan | Act. (MTD) | Diff (MTD)
RTN | PTP | 0 | 0 | 31 | 0 | 27 | 4 | 0 | 0 | 0 | 0 |  | RTN | PTP | 0 | 0 | 31 | 0 | 27 | 4 | 0 | 0 | 0 | 0
RTN | PAMA | 800000 | 850000 | 31 | 27419.3548 | 27 | 4 | 696774.1935 | 740322.5806 | 542286 | -198036.5806 |  | RTN | PAMA | 100000 | 64000 | 31 | 2064.5161 | 27 | 4 | 87096.7742 | 55741.9355 | 48481.4 | -7260.5355
RTN | KMI | 0 | 0 | 31 | 0 | 27 | 4 | 0 | 0 | 0 | 0 |  | RTN | KMI | 0 | 0 | 31 | 0 | 27 | 4 | 0 | 0 | 0 | 0
RS-CF | PAMA | 1930000 | 1928000 | 31 | 62193.5484 | 27 | 4 | 1680967.7419 | 1679225.8065 | 1525820 | -153405.8065 |  | RS-CF | PAMA | 210000 | 210000 | 31 | 6774.1935 | 27 | 4 | 182903.2258 | 182903.2258 | 212491.4 | 29588.1742
RS-G | PAMA | 820000 | 935000 | 31 | 30161.2903 | 27 | 4 | 714193.5484 | 814354.8387 | 709859 | -104495.8387 |  | RS-G | PAMA | 120000 | 50000 | 31 | 1612.9032 | 27 | 4 | 104516.129 | 43548.3871 | 87699.7 | 44151.3129
RTM | PTP | 0 | 0 | 31 | 0 | 27 | 4 | 0 | 0 | 0 | 0 |  | RTM | PTP | 0 | 0 | 31 | 0 | 27 | 4 | 0 | 0 | 0 | 0
RTM | PAMA | 1010000 | 929000 | 31 | 29967.7419 | 27 | 4 | 879677.4194 | 809129.0323 | 757445 | -51684.0323 |  | RTM | PAMA | 170000 | 175000 | 31 | 5645.1613 | 27 | 4 | 148064.5161 | 152419.3548 | 181737.7 | 29318.3452
SSB | BIMA | 910000 | 833000 | 31 | 26870.9677 | 27 | 4 | 792580.6452 | 725516.129 | 777538 | 52021.871 |  | SSB | BIMA | 70000 | 70000 | 31 | 2258.0645 | 27 | 4 | 60967.7419 | 60967.7419 | 77305.4 | 16337.6581
SAMUBIU | PAMA | 0 | 0 | 31 | 0 | 27 | 4 | 0 | 0 | 0 | 0 |  | SAMUBIU | PAMA | 0 | 0 | 31 | 0 | 27 | 4 | 0 | 0 | 0 | 0
Roto | S-Tot | 5470000 | 5475000 |  | 176612.9032 |  |  | 4764193.5484 | 4768548.3871 | 4312948 | -455600.3871 |  | Roto | S-Tot | 670000 | 569000 |  | 18354.8387 |  |  | 583548.3871 | 495580.6452 | 607715.6 | 112134.9548
SM AB | SIMS | 3150000 | 3150000 | 31 | 101612.9032 | 27 | 4 | 2743548.3871 | 2743548.3871 | 1723720 | -1019828.3871 |  | SM AB | SIMS | 570000 | 722000 | 31 | 23290.3226 | 27 | 4 | 496451.6129 | 628838.7097 | 546510.6 | -82328.1097
SM 6 | PAMA | 1240000 | 1356000 | 31 | 43741.9355 | 27 | 4 | 1080000 | 1181032.2581 | 937947 | -243085.2581 |  | SM 6 | PAMA | 230000 | 100000 | 31 | 3225.8065 | 27 | 4 | 200322.5806 | 87096.7742 | 61818.7 | -25278.0742
SM AB | PTP | 0 | 0 | 31 | 0 | 27 | 4 | 0 | 0 | 0 | 0 |  | SM AB | PTP | 0 | 0 | 31 | 0 | 27 | 4 | 0 | 0 | 0 | 0
SM AB | PAMA | 1190000 | 550000 | 31 | 17741.9355 | 27 | 4 | 1036451.6129 | 479032.2581 | 630838 | 151805.7419 |  | SM AB | PAMA | 210000 | 146000 | 31 | 4709.6774 | 27 | 4 | 182903.2258 | 127161.2903 | 65208.6 | -61952.6903
SM C | PAMA | 270000 | 190000 | 31 | 6129.0323 | 27 | 4 | 235161.2903 | 165483.871 | 0 | -165483.871 |  | SM C | PAMA | 60000 | 76000 | 31 | 2451.6129 | 27 | 4 | 52258.0645 | 66193.5484 | 0 | -66193.5484
SM D | PTP | 4960000 | 6000000 | 31 | 193548.3871 | 27 | 4 | 4320000 | 5225806.4516 | 4331770 | -894036.4516 |  | SM D | PTP | 990000 | 1262000 | 31 | 40709.6774 | 27 | 4 | 862258.0645 | 1099161.2903 | 1107215.21 | 8053.9197
SM D | DUM | 270000 | 263000 | 31 | 8483.871 | 27 | 4 | 235161.2903 | 229064.5161 | 281248 | 52183.4839 |  | SM D | DUM | 0 | 0 | 31 | 0 | 27 | 4 | 0 | 0 | 0 | 0
SM | S-Tot | 11080000 | 11509000 |  | 371258.0645 |  |  | 9650322.5806 | 10023967.7419 | 7905523 | -2118444.7419 |  | SM | S-Tot | 2060000 | 2306000 |  | 74387.0968 |  |  | 1794193.5484 | 2008451.6129 | 1780753.11 | -227698.5029
Grand Total |  | 16550000 | 16984000 |  | 547870.9677 |  |  | 14414516.129 | 14792516.129 | 12218471 | -2574045.129 |  | Grand Total |  | 2730000 | 2875000 |  | 92741.9355 |  |  | 2377741.9355 | 2504032.2581 | 2388468.71 | -115563.5481
2022-06-03
>> Waste | [10 empty] | Unit : KBcm |  | >> Coal | [10 empty] | Unit : Kton
Cont. | Area | B/Plan | A/Plan | W/Day | Plan/Day | Act. Day | Remain Day | Plan (MTD) B/Plan | Plan (MTD) A/Plan | Act. (MTD) | Diff (MTD) |  | Contractor | Area | B/Plan | A/Plan | W/Day | Plan/Day | Act. Day | Remain Day | Plan (MTD) B/Plan | Plan (MTD) A/Plan | Act. (MTD) | Diff (MTD)
RTN | PTP |  |  | 29 | 0 | 0 | 29 | 0 | 0 |  | 0 |  | RTN | PTP |  |  | 29 | 0 | 0 | 29 | 0 | 0 |  | 0
RTN | PAMA |  |  | 29 | 0 | 0 | 29 | 0 | 0 |  | 0 |  | RTN | PAMA |  |  | 29 | 0 | 0 | 29 | 0 | 0 |  | 0
RTN | KMI |  |  | 29 | 0 | 0 | 29 | 0 | 0 |  | 0 |  | RTN | KMI |  |  | 29 | 0 | 0 | 29 | 0 | 0 |  | 0
RS-CF | PAMA |  |  | 29 | 0 | 0 | 29 | 0 | 0 |  | 0 |  | RS-CF | PAMA |  |  | 29 | 0 | 0 | 29 | 0 | 0 |  | 0
RS-G | PAMA |  |  | 29 | 0 | 0 | 29 | 0 | 0 |  | 0 |  | RS-G | PAMA |  |  | 29 | 0 | 0 | 29 | 0 | 0 |  | 0
RTM | PTP |  |  | 29 | 0 | 0 | 29 | 0 | 0 |  | 0 |  | RTM | PTP |  |  | 29 | 0 | 0 | 29 | 0 | 0 |  | 0
RTM | PAMA |  |  | 29 | 0 | 0 | 29 | 0 | 0 |  | 0 |  | RTM | PAMA |  |  | 29 | 0 | 0 | 29 | 0 | 0 |  | 0
SSB | BIMA |  |  | 29 | 0 | 0 | 29 | 0 | 0 |  | 0 |  | SSB | BIMA |  |  | 29 | 0 | 0 | 29 | 0 | 0 |  | 0
SAMUBIU | PAMA |  |  | 29 | 0 | 0 | 29 | 0 | 0 |  | 0 |  | SAMUBIU | PAMA |  |  | 29 | 0 | 0 | 29 | 0 | 0 |  | 0
Roto | S-Tot | 0 | 0 |  | 0 |  |  | 0 | 0 | 0 | 0 |  | Roto | S-Tot | 0 | 0 |  | 0 |  |  | 0 | 0 | 0 | 0
SM AB | SIMS |  |  | 29 | 0 | 0 | 29 | 0 | 0 |  | 0 |  | SM AB | SIMS |  |  | 29 | 0 | 0 | 29 | 0 | 0 |  | 0
SM AB | PTP |  |  | 29 | 0 | 0 | 29 | 0 | 0 |  | 0 |  | SM AB | PTP |  |  | 29 | 0 | 0 | 29 | 0 | 0 |  | 0
SM AB | KMI |  |  | 29 | 0 | 0 | 29 | 0 | 0 |  | 0 |  | SM AB | KMI |  |  | 29 | 0 | 0 | 29 | 0 | 0 |  | 0
SM C | PTP | [11 empty] | SM C | PTP |  |  | 29 | 0 | 0 | 29 | 0 | 0 |  | 0
SM D | PTP |  |  | 29 | 0 | 0 | 29 | 0 | 0 |  | 0 |  | SM D | PTP |  |  | 29 | 0 | 0 | 29 | 0 | 0 |  | 0
SM D | DUM |  |  | 29 | 0 | 0 | 29 | 0 | 0 |  | 0 |  | SM D | DUM |  |  | 29 | 0 | 0 | 29 | 0 | 0 |  | 0
SM | S-Tot | 0 | 0 |  | 0 |  |  | 0 | 0 | 0 | 0 |  | SM | S-Tot | 0 | 0 |  | 0 |  |  | 0 | 0 | 0 | 0
Grand Total |  | 0 | 0 |  | 0 |  |  | 0 | 0 | 0 | 0 |  | Grand Total |  | 0 | 0 |  | 0 |  |  | 0 | 0 | 0 | 0
2022-07-04
>> Waste | [10 empty] | Unit : KBcm |  | >> Coal | [10 empty] | Unit : Ton
Cont. | Area | B/Plan | A/Plan | W/Day | Plan/Day | Act. Day | Remain Day | Plan (MTD) B/Plan | Plan (MTD) A/Plan | Act. (MTD) | Diff (MTD) |  | Contractor | Area | B/Plan | A/Plan | W/Day | Plan/Day | Act. Day | Remain Day | Plan (MTD) B/Plan | Plan (MTD) A/Plan | Act. (MTD) | Diff (MTD)
RTN | PTP |  |  | 30 | 0 | 0 | 30 | 0 | 0 |  | 0 |  | RTN | PTP |  |  | 30 | 0 | 0 | 30 | 0 | 0 |  | 0
RTN | PAMA |  |  | 30 | 0 | 0 | 30 | 0 | 0 |  | 0 |  | RTN | PAMA |  |  | 30 | 0 | 0 | 30 | 0 | 0 |  | 0
RTN | KMI |  |  | 30 | 0 | 0 | 30 | 0 | 0 |  | 0 |  | RTN | KMI |  |  | 30 | 0 | 0 | 30 | 0 | 0 |  | 0
RS-CF | PAMA |  |  | 30 | 0 | 0 | 30 | 0 | 0 |  | 0 |  | RS-CF | PAMA |  |  | 30 | 0 | 0 | 30 | 0 | 0 |  | 0
RS-G | PAMA |  |  | 30 | 0 | 0 | 30 | 0 | 0 |  | 0 |  | RS-G | PAMA |  |  | 30 | 0 | 0 | 30 | 0 | 0 |  | 0
RTM | PTP |  |  | 30 | 0 | 0 | 30 | 0 | 0 |  | 0 |  | RTM | PTP |  |  | 30 | 0 | 0 | 30 | 0 | 0 |  | 0
RTM | PAMA |  |  | 30 | 0 | 0 | 30 | 0 | 0 |  | 0 |  | RTM | PAMA |  |  | 30 | 0 | 0 | 30 | 0 | 0 |  | 0
SSB | BIMA |  |  | 30 | 0 | 0 | 30 | 0 | 0 |  | 0 |  | SSB | BIMA |  |  | 30 | 0 | 0 | 30 | 0 | 0 |  | 0
SAMUBIU | PAMA |  |  | 30 | 0 | 0 | 30 | 0 | 0 |  | 0 |  | SAMUBIU | PAMA |  |  | 30 | 0 | 0 | 30 | 0 | 0 | 0 | 0
Roto | S-Tot | 0 | 0 |  | 0 |  |  | 0 | 0 | 0 | 0 |  | Roto | S-Tot | 0 | 0 |  | 0 |  |  | 0 | 0 | 0 | 0
SM AB | SIMS |  |  | 30 | 0 | 0 | 30 | 0 | 0 |  | 0 |  | SM AB | SIMS |  |  | 30 | 0 | 0 | 30 | 0 | 0 |  | 0
SM AB | PTP |  |  | 30 | 0 | 0 | 30 | 0 | 0 |  | 0 |  | SM AB | PTP |  |  | 30 | 0 | 0 | 30 | 0 | 0 |  | 0
SM AB | KMI |  |  | 30 | 0 | 0 | 30 | 0 | 0 |  | 0 |  | SM AB | KMI |  |  | 30 | 0 | 0 | 30 | 0 | 0 |  | 0
SM C | PTP |  |  | 30 | 0 | 0 | 30 | 0 | 0 |  | 0 |  | SM C | PTP |  |  | 30 | 0 | 0 | 30 | 0 | 0 |  | 0
SM D | PTP |  |  | 30 | 0 | 0 | 30 | 0 | 0 |  | 0 |  | SM D | PTP |  |  | 30 | 0 | 0 | 30 | 0 | 0 |  | 0
SM D | DUM |  |  | 30 | 0 | 0 | 30 | 0 | 0 |  | 0 |  | SM D | DUM |  |  | 30 | 0 | 0 | 30 | 0 | 0 |  | 0
SM | S-Tot | 0 | 0 |  | 0 |  |  | 0 | 0 | 0 | 0 |  | SM | S-Tot | 0 | 0 |  | 0 |  |  | 0 | 0 | 0 | 0
Grand Total |  | 0 | 0 |  | 0 |  |  | 0 | 0 | 0 | 0 |  | Grand Total |  | 0 | 0 |  | 0 |  |  | 0 | 0 | 0 | 0
2022-08-04
>> Waste | [10 empty] | Unit : KBcm |  | >> Coal | [10 empty] | Unit : Ton
Cont. | Area | B/Plan | A/Plan | W/Day | Plan/Day | Act. Day | Remain Day | Plan (MTD) B/Plan | Plan (MTD) A/Plan | Act. (MTD) | Diff (MTD) |  | Contractor | Area | B/Plan | A/Plan | W/Day | Plan/Day | Act. Day | Remain Day | Plan (MTD) B/Plan | Plan (MTD) A/Plan | Act. (MTD) | Diff (MTD)
RTN | PTP |  |  | 30 | 0 | 0 | 30 | 0 | 0 |  | 0 |  | RTN | PTP |  |  | 30 | 0 | 0 | 30 | 0 | 0 |  | 0
RTN | PAMA |  |  | 30 | 0 | 0 | 30 | 0 | 0 |  | 0 |  | RTN | PAMA |  |  | 30 | 0 | 0 | 30 | 0 | 0 |  | 0
RTN | KMI |  |  | 30 | 0 | 0 | 30 | 0 | 0 |  | 0 |  | RTN | KMI |  |  | 30 | 0 | 0 | 30 | 0 | 0 |  | 0
RS-CF | PAMA |  |  | 30 | 0 | 0 | 30 | 0 | 0 |  | 0 |  | RS-CF | PAMA |  |  | 30 | 0 | 0 | 30 | 0 | 0 |  | 0
RS-G | PAMA |  |  | 30 | 0 | 0 | 30 | 0 | 0 |  | 0 |  | RS-G | PAMA |  |  | 30 | 0 | 0 | 30 | 0 | 0 |  | 0
RTM | PTP |  |  | 30 | 0 | 0 | 30 | 0 | 0 |  | 0 |  | RTM | PTP |  |  | 30 | 0 | 0 | 30 | 0 | 0 |  | 0
RTM | PAMA |  |  | 30 | 0 | 0 | 30 | 0 | 0 |  | 0 |  | RTM | PAMA |  |  | 30 | 0 | 0 | 30 | 0 | 0 |  | 0
SSB | BIMA |  |  | 30 | 0 | 0 | 30 | 0 | 0 |  | 0 |  | SSB | BIMA |  |  | 30 | 0 | 0 | 30 | 0 | 0 |  | 0
SAMUBIU | PAMA |  |  | 30 | 0 | 0 | 30 | 0 | 0 |  | 0 |  | SAMUBIU | PAMA |  |  | 30 | 0 | 0 | 30 | 0 | 0 |  | 0
Roto | S-Tot | 0 | 0 |  | 0 |  |  | 0 | 0 | 0 | 0 |  | Roto | S-Tot | 0 | 0 |  | 0 |  |  | 0 | 0 | 0 | 0
SM AB | SIMS |  |  | 30 | 0 | 0 | 30 | 0 | 0 |  | 0 |  | SM AB | SIMS |  |  | 30 | 0 | 0 | 30 | 0 | 0 |  | 0
SM AB | PTP |  |  | 30 | 0 | 0 | 30 | 0 | 0 |  | 0 |  | SM AB | PTP |  |  | 30 | 0 | 0 | 30 | 0 | 0 |  | 0
SM AB | KMI |  |  | 30 | 0 | 0 | 30 | 0 | 0 |  | 0 |  | SM AB | KMI |  |  | 30 | 0 | 0 | 30 | 0 | 0 |  | 0
SM C | PTP |  |  | 30 | 0 | 0 | 30 | 0 | 0 |  | 0 |  | SM C | PTP |  |  | 30 | 0 | 0 | 30 | 0 | 0 |  | 0
SM D | PTP |  |  | 30 | 0 | 0 | 30 | 0 | 0 |  | 0 |  | SM D | PTP |  |  | 30 | 0 | 0 | 30 | 0 | 0 |  | 0
SM D | DUM |  |  | 30 | 0 | 0 | 30 | 0 | 0 |  | 0 |  | SM D | DUM |  |  | 30 | 0 | 0 | 30 | 0 | 0 |  | 0
SM | S-Tot | 0 | 0 |  | 0 |  |  | 0 | 0 | 0 | 0 |  | SM | S-Tot | 0 | 0 |  | 0 |  |  | 0 | 0 | 0 | 0
Grand Total |  | 0 | 0 |  | 0 |  |  | 0 | 0 | 0 | 0 |  | Grand Total |  | 0 | 0 |  | 0 |  |  | 0 | 0 | 0 | 0
2022-09-03
>> Waste | [10 empty] | Unit : KBcm |  | >> Coal | [10 empty] | Unit : Kton
Cont. | Area | B/Plan | A/Plan | W/Day | Plan/Day | Act. Day | Remain Day | Plan (MTD) B/Plan | Plan (MTD) A/Plan | Act. (MTD) | Diff (MTD) |  | Contractor | Area | B/Plan | A/Plan | W/Day | Plan/Day | Act. Day | Remain Day | Plan (MTD) B/Plan | Plan (MTD) A/Plan | Act. (MTD) | Diff (MTD)
RTN | PTP |  |  | 30 | 0 | 0 | 30 | 0 | 0 |  | 0 |  | RTN | PTP |  |  | 30 | 0 | 0 | 30 | 0 | 0 |  | 0
RTN | PAMA |  |  | 30 | 0 | 0 | 30 | 0 | 0 |  | 0 |  | RTN | PAMA |  |  | 30 | 0 | 0 | 30 | 0 | 0 |  | 0
RTN | KMI |  |  | 30 | 0 | 0 | 30 | 0 | 0 |  | 0 |  | RTN | KMI |  |  | 30 | 0 | 0 | 30 | 0 | 0 |  | 0
RS-CF | PAMA |  |  | 30 | 0 | 0 | 30 | 0 | 0 |  | 0 |  | RS-CF | PAMA |  |  | 30 | 0 | 0 | 30 | 0 | 0 |  | 0
RS-G | PAMA |  |  | 30 | 0 | 0 | 30 | 0 | 0 |  | 0 |  | RS-G | PAMA |  |  | 30 | 0 | 0 | 30 | 0 | 0 |  | 0
RTM | PTP |  |  | 30 | 0 | 0 | 30 | 0 | 0 |  | 0 |  | RTM | PTP |  |  | 30 | 0 | 0 | 30 | 0 | 0 |  | 0
RTM | PAMA |  |  | 30 | 0 | 0 | 30 | 0 | 0 |  | 0 |  | RTM | PAMA |  |  | 30 | 0 | 0 | 30 | 0 | 0 |  | 0
SSB | BIMA |  |  | 30 | 0 | 0 | 30 | 0 | 0 |  | 0 |  | SSB | BIMA |  |  | 30 | 0 | 0 | 30 | 0 | 0 |  | 0
SAMUBIU | PAMA |  |  | 30 | 0 | 0 | 30 | 0 | 0 |  | 0 |  | SAMUBIU | PAMA |  |  | 30 | 0 | 0 | 30 | 0 | 0 |  | 0
Roto | S-Tot | 0 | 0 |  | 0 |  |  | 0 | 0 | 0 | 0 |  | Roto | S-Tot | 0 | 0 |  | 0 |  |  | 0 | 0 | 0 | 0
SM AB | SIMS |  |  | 30 | 0 | 0 | 30 | 0 | 0 |  | 0 |  | SM AB | SIMS |  |  | 30 | 0 | 0 | 30 | 0 | 0 |  | 0
SM AB | PTP |  |  | 30 | 0 | 0 | 30 | 0 | 0 |  | 0 |  | SM AB | PTP |  |  | 30 | 0 | 0 | 30 | 0 | 0 |  | 0
SM AB | KMI |  |  | 30 | 0 | 0 | 30 | 0 | 0 |  | 0 |  | SM AB | KMI |  |  | 30 | 0 | 0 | 30 | 0 | 0 |  | 0
SM C | PTP |  |  | 30 | 0 | 0 | 30 | 0 | 0 |  | 0 |  | SM C | PTP |  |  | 30 | 0 | 0 | 30 | 0 | 0 |  | 0
SM D | PTP |  |  | 30 | 0 | 0 | 30 | 0 | 0 |  | 0 |  | SM D | PTP |  |  | 30 | 0 | 0 | 30 | 0 | 0 |  | 0
SM D | DUM |  |  | 30 | 0 | 0 | 30 | 0 | 0 |  | 0 |  | SM D | DUM |  |  | 30 | 0 | 0 | 30 | 0 | 0 |  | 0
SM | S-Tot | 0 | 0 |  | 0 |  |  | 0 | 0 | 0 | 0 |  | SM | S-Tot | 0 | 0 |  | 0 |  |  | 0 | 0 | 0 | 0
Grand Total |  | 0 | 0 |  | 0 |  |  | 0 | 0 | 0 | 0 |  | Grand Total |  | 0 | 0 |  | 0 |  |  | 0 | 0 | 0 | 0
2022-10-04
>> Waste | [10 empty] | Unit : KBcm |  | >> Coal | [10 empty] | Unit : Kton
Cont. | Area | B/Plan | A/Plan | W/Day | Plan/Day | Act. Day | Remain Day | Plan (MTD) B/Plan | Plan (MTD) A/Plan | Act. (MTD) | Diff (MTD) |  | Contractor | Area | B/Plan | A/Plan | W/Day | Plan/Day | Act. Day | Remain Day | Plan (MTD) B/Plan | Plan (MTD) A/Plan | Act. (MTD) | Diff (MTD)
RTN | PTP |  |  | 31 | 0 | 0 | 31 | 0 | 0 |  | 0 |  | RTN | PTP |  |  | 31 | 0 | 0 | 31 | 0 | 0 |  | 0
RTN | PAMA |  |  | 31 | 0 | 0 | 31 | 0 | 0 |  | 0 |  | RTN | PAMA |  |  | 31 | 0 | 0 | 31 | 0 | 0 |  | 0
RTN | KMI |  |  | 31 | 0 | 0 | 31 | 0 | 0 |  | 0 |  | RTN | KMI |  |  | 31 | 0 | 0 | 31 | 0 | 0 |  | 0
RS-CF | PAMA |  |  | 31 | 0 | 0 | 31 | 0 | 0 |  | 0 |  | RS-CF | PAMA |  |  | 31 | 0 | 0 | 31 | 0 | 0 |  | 0
RS-G | PAMA |  |  | 31 | 0 | 0 | 31 | 0 | 0 |  | 0 |  | RS-G | PAMA |  |  | 31 | 0 | 0 | 31 | 0 | 0 |  | 0
RTM | PTP |  |  | 31 | 0 | 0 | 31 | 0 | 0 |  | 0 |  | RTM | PTP |  |  | 31 | 0 | 0 | 31 | 0 | 0 |  | 0
RTM | PAMA |  |  | 31 | 0 | 0 | 31 | 0 | 0 |  | 0 |  | RTM | PAMA |  |  | 31 | 0 | 0 | 31 | 0 | 0 |  | 0
SSB | BIMA |  |  | 31 | 0 | 0 | 31 | 0 | 0 |  | 0 |  | SSB | BIMA |  |  | 31 | 0 | 0 | 31 | 0 | 0 |  | 0
SAMUBIU | PAMA |  |  | 31 | 0 | 0 | 31 | 0 | 0 |  | 0 |  | SAMUBIU | PAMA |  |  | 31 | 0 | 0 | 31 | 0 | 0 |  | 0
Roto | S-Tot | 0 | 0 |  | 0 |  |  | 0 | 0 | 0 | 0 |  | Roto | S-Tot | 0 | 0 |  | 0 |  |  | 0 | 0 | 0 | 0
SM AB | SIMS |  |  | 31 | 0 | 0 | 31 | 0 | 0 |  | 0 |  | SM AB | SIMS |  |  | 31 | 0 | 0 | 31 | 0 | 0 |  | 0
SM AB | PTP |  |  | 31 | 0 | 0 | 31 | 0 | 0 |  | 0 |  | SM AB | PTP |  |  | 31 | 0 | 0 | 31 | 0 | 0 |  | 0
SM AB | KMI |  |  | 31 | 0 | 0 | 31 | 0 | 0 |  | 0 |  | SM AB | KMI |  |  | 31 | 0 | 0 | 31 | 0 | 0 |  | 0
SM C | PTP |  |  | 31 | 0 | 0 | 31 | 0 | 0 |  | 0 |  | SM C | PTP |  |  | 31 | 0 | 0 | 31 | 0 | 0 |  | 0
SM D | PTP |  |  | 31 | 0 | 0 | 31 | 0 | 0 |  | 0 |  | SM D | PTP |  |  | 31 | 0 | 0 | 31 | 0 | 0 |  | 0
SM D | DUM |  |  | 31 | 0 | 0 | 31 | 0 | 0 |  | 0 |  | SM D | DUM |  |  | 31 | 0 | 0 | 31 | 0 | 0 |  | 0
SM | S-Tot | 0 | 0 |  | 0 |  |  | 0 | 0 | 0 | 0 |  | SM | S-Tot | 0 | 0 |  | 0 |  |  | 0 | 0 | 0 | 0
Grand Total |  | 0 | 0 |  | 0 |  |  | 0 | 0 | 0 | 0 |  | Grand Total |  | 0 | 0 |  | 0 |  |  | 0 | 0 | 0 | 0
2022-11-03
>> Waste | [10 empty] | Unit : KBcm |  | >> Coal | [10 empty] | Unit : Kton
Cont. | Area | B/Plan | A/Plan | W/Day | Plan/Day | Act. Day | Remain Day | Plan (MTD) B/Plan | Plan (MTD) A/Plan | Act. (MTD) | Diff (MTD) |  | Contractor | Area | B/Plan | A/Plan | W/Day | Plan/Day | Act. Day | Remain Day | Plan (MTD) B/Plan | Plan (MTD) A/Plan | Act. (MTD) | Diff (MTD)
RTN | PTP |  |  | 30 | 0 | 0 | 30 | 0 | 0 |  | 0 |  | RTN | PTP |  |  | 30 | 0 | 0 | 30 | 0 | 0 |  | 0
RTN | PAMA |  |  | 30 | 0 | 0 | 30 | 0 | 0 |  | 0 |  | RTN | PAMA |  |  | 30 | 0 | 0 | 30 | 0 | 0 |  | 0
RTN | KMI |  |  | 30 | 0 | 0 | 30 | 0 | 0 |  | 0 |  | RTN | KMI |  |  | 30 | 0 | 0 | 30 | 0 | 0 |  | 0
RS-CF | PAMA |  |  | 30 | 0 | 0 | 30 | 0 | 0 |  | 0 |  | RS-CF | PAMA |  |  | 30 | 0 | 0 | 30 | 0 | 0 |  | 0
RS-G | PAMA |  |  | 30 | 0 | 0 | 30 | 0 | 0 |  | 0 |  | RS-G | PAMA |  |  | 30 | 0 | 0 | 30 | 0 | 0 |  | 0
RTM | PTP |  |  | 30 | 0 | 0 | 30 | 0 | 0 |  | 0 |  | RTM | PTP |  |  | 30 | 0 | 0 | 30 | 0 | 0 |  | 0
RTM | PAMA |  |  | 30 | 0 | 0 | 30 | 0 | 0 |  | 0 |  | RTM | PAMA |  |  | 30 | 0 | 0 | 30 | 0 | 0 |  | 0
SSB | BIMA |  |  | 30 | 0 | 0 | 30 | 0 | 0 |  | 0 |  | SSB | BIMA |  |  | 30 | 0 | 0 | 30 | 0 | 0 |  | 0
SAMUBIU | PAMA |  |  | 30 | 0 | 0 | 30 | 0 | 0 |  | 0 |  | SAMUBIU | PAMA |  |  | 30 | 0 | 0 | 30 | 0 | 0 | 0 | 0
Roto | S-Tot | 0 | 0 |  | 0 |  |  | 0 | 0 | 0 | 0 |  | Roto | S-Tot | 0 | 0 |  | 0 |  |  | 0 | 0 | 0 | 0
SM AB | SIMS |  |  | 30 | 0 | 0 | 30 | 0 | 0 |  | 0 |  | SM AB | SIMS |  |  | 30 | 0 | 0 | 30 | 0 | 0 |  | 0
SM AB | PTP |  |  | 30 | 0 | 0 | 30 | 0 | 0 |  | 0 |  | SM AB | PTP |  |  | 30 | 0 | 0 | 30 | 0 | 0 |  | 0
SM AB | KMI |  |  | 30 | 0 | 0 | 30 | 0 | 0 |  | 0 |  | SM AB | KMI |  |  | 30 | 0 | 0 | 30 | 0 | 0 |  | 0
SM C | PTP |  |  | 30 | 0 | 0 | 30 | 0 | 0 |  | 0 |  | SM C | PTP |  |  | 30 | 0 | 0 | 30 | 0 | 0 |  | 0
SM D | PTP |  |  | 30 | 0 | 0 | 30 | 0 | 0 |  | 0 |  | SM D | PTP |  |  | 30 | 0 | 0 | 30 | 0 | 0 |  | 0
SM D | DUM |  |  | 30 | 0 | 0 | 30 | 0 | 0 |  | 0 |  | SM D | DUM |  |  | 30 | 0 | 0 | 30 | 0 | 0 | 0 | 0
SM | S-Tot | 0 | 0 |  | 0 |  |  | 0 | 0 | 0 | 0 |  | SM | S-Tot | 0 | 0 |  | 0 |  |  | 0 | 0 | 0 | 0
Grand Total |  | 0 | 0 |  | 0 |  |  | 0 | 0 | 0 | 0 |  | Grand Total |  | 0 | 0 |  | 0 |  |  | 0 | 0 | 0 | 0
2022-12-04
>> Waste | [10 empty] | Unit : KBcm |  | >> Coal | [10 empty] | Unit : Ton
Cont. | Area | B/Plan | A/Plan | W/Day | Plan/Day | Act. Day | Remain Day | Plan (MTD) B/Plan | Plan (MTD) A/Plan | Act. (MTD) | Diff (MTD) |  | Contractor | Area | B/Plan | A/Plan | W/Day | Plan/Day | Act. Day | Remain Day | Plan (MTD) B/Plan | Plan (MTD) A/Plan | Act. (MTD) | Diff (MTD)
RTN | PTP |  |  | 30 | 0 | 0 | 30 | 0 | 0 |  | 0 |  | RTN | PTP |  |  | 30 | 0 | 0 | 30 | 0 | 0 |  | 0
RTN | PAMA |  |  | 30 | 0 | 0 | 30 | 0 | 0 |  | 0 |  | RTN | PAMA |  |  | 30 | 0 | 0 | 30 | 0 | 0 |  | 0
RTN | KMI |  |  | 30 | 0 | 0 | 30 | 0 | 0 |  | 0 |  | RTN | KMI |  |  | 30 | 0 | 0 | 30 | 0 | 0 |  | 0
RS-CF | PAMA |  |  | 30 | 0 | 0 | 30 | 0 | 0 |  | 0 |  | RS-CF | PAMA |  |  | 30 | 0 | 0 | 30 | 0 | 0 |  | 0
RS-G | PAMA |  |  | 30 | 0 | 0 | 30 | 0 | 0 |  | 0 |  | RS-G | PAMA |  |  | 30 | 0 | 0 | 30 | 0 | 0 |  | 0
RTM | PTP |  |  | 30 | 0 | 0 | 30 | 0 | 0 |  | 0 |  | RTM | PTP |  |  | 30 | 0 | 0 | 30 | 0 | 0 |  | 0
RTM | PAMA |  |  | 30 | 0 | 0 | 30 | 0 | 0 |  | 0 |  | RTM | PAMA |  |  | 30 | 0 | 0 | 30 | 0 | 0 |  | 0
SSB | BIMA |  |  | 30 | 0 | 0 | 30 | 0 | 0 |  | 0 |  | SSB | BIMA |  |  | 30 | 0 | 0 | 30 | 0 | 0 |  | 0
SAMUBIU | PAMA |  |  | 30 | 0 | 0 | 30 | 0 | 0 | 0 | 0 |  | SAMUBIU | PAMA |  |  | 30 | 0 | 0 | 30 | 0 | 0 |  | 0
Roto | S-Tot | 0 | 0 |  | 0 |  |  | 0 | 0 | 0 | 0 |  | Roto | S-Tot | 0 | 0 |  | 0 |  |  | 0 | 0 | 0 | 0
SM AB | SIMS |  |  | 30 | 0 | 0 | 30 | 0 | 0 |  | 0 |  | SM AB | SIMS |  |  | 30 | 0 | 0 | 30 | 0 | 0 |  | 0
SM AB | PTP |  |  | 30 | 0 | 0 | 30 | 0 | 0 |  | 0 |  | SM AB | PTP |  |  | 30 | 0 | 0 | 30 | 0 | 0 |  | 0
SM AB | KMI |  |  | 30 | 0 | 0 | 30 | 0 | 0 |  | 0 |  | SM AB | KMI |  |  | 30 | 0 | 0 | 30 | 0 | 0 |  | 0
SM C | PTP |  |  | 30 | 0 | 0 | 30 | 0 | 0 |  | 0 |  | SM C | PTP |  |  | 30 | 0 | 0 | 30 | 0 | 0 |  | 0
SM D | PTP |  |  | 30 | 0 | 0 | 30 | 0 | 0 |  | 0 |  | SM D | PTP |  |  | 30 | 0 | 0 | 30 | 0 | 0 |  | 0
SM D | DUM |  |  | 30 | 0 | 0 | 30 | 0 | 0 |  | 0 |  | SM D | DUM |  |  | 30 | 0 | 0 | 30 | 0 | 0 |  | 0
SM | S-Tot | 0 | 0 |  | 0 |  |  | 0 | 0 | 0 | 0 |  | SM | S-Tot | 0 | 0 |  | 0 |  |  | 0 | 0 | 0 | 0
Grand Total |  | 0 | 0 |  | 0 |  |  | 0 | 0 | 0 | 0 |  | Grand Total |  | 0 | 0 |  | 0 |  |  | 0 | 0 | 0 | 0
Summary Of Production
>> By Contractor / Area |  |  |  |  | >> By Month
Cont. | Area | Volume |  |  | Month | Volume
|  | Waste | Coal |  |  | Waste | Coal
RTN | PTP | 0 | 0 |  | Jan | 14087012 | 2403325
RTN | PAMA | 3461238 | 276074.8 |  | Feb | 12145076 | 2289297
RTN | KMI | 0 | 0 |  | Mar | 11674612 | 2226843
RS-CF | PAMA | 8019403 | 1339659.8 |  | Apr | 9938974 | 2388468.71
RS-G | PAMA | #REF! | 314493.4 |  | May | 12218471 | 2388468.71
RTM | PTP | 789952 | 0 |  | Jun | 0 | 0
RTM | PAMA | 3759095 | 914115.4 |  | Jul | 0 | 0
SSB | BIMA | 3946223 | 388792.8 |  | Aug | 0 | 0
SAMUBIU | PAMA | 0 | 0 |  | Sep | 0 | 0
Roto | S-Tot | 22549045 | 3233136.2 |  | Oct | 0 | 0
SM AB | SIMS | 9666355 | 3011395.2 |  | Nov | 0 | 0
SM 6 | PAMA | 1001958 | 7127 |  | Dec | 0 | 0
SM AB | PTP | 682120 | 117688 |  | G-Tot | 60064145 | 11696402.42
SM AB | KMI | 1039979 | 130417.2
SM C | PTP | 0 | 0
SM D | PTP | 20230037 | 5065613.42
SM D | DUM | 1206634 | 0
SM | S-Tot | 37515100 | 8463266.22
Grand Total |  | 60064145 | 11696402.42
Rainfall
Contractor | Area | Jan |  |  |  | Feb |  |  |  | Mar |  |  |  | Apr |  |  |  | May |  |  |  | Jun
|  | Qty | Rain | Clean Up | Fog | Qty | Rain | Clean Up | Fog | Qty | Rain | Clean Up | Fog | Qty | Rain | Clean Up | Fog | Qty | Rain | Clean Up | Fog | Qty | Rain | Clean Up | Fog
PTP | RTN | 136.1 | 91.35 | 8.5667 | 0 | 329.5 | 152.2167 | 10.1167 | 0 | 364.54 | 171.1833 | 28.0667 | 0 | 281.5 | 25 | 122.7167 | 22.75
PAMA | RS-AB | 179 | 99.9167 | 12.05 | 0 | 259.5 | 160.65 | 14.8833 | 0 | 373.03 | 190.7667 | 53.15 | 0 | 254.5 | 23 | 110.4333 | 32
PAMA | RS-CD | 184 | 106.55 | 13.2667 | 0 | 286 | 157.4 | 13.15 | 0 | 380.01 | 186.1 | 41.0833 | 0 | 294.5 | 23 | 109.4833 | 34.2833
PAMA | RS-EF | 185.125 | 120.8333 | 19.1875 | 0 | 339.5 | 177.9875 | 23.0458 | 0 | 491.385 | 197.775 | 76.6375 | 3.15 | 203.875 | 102.8542 | 36.9708 | 2.4167
PAMA | RS-G | 153 | 127.6167 | 16.6167 | 0 | 394.5 | 180.4833 | 27.5833 | 0 | 512.01 | 225.75 | 85.0833 | 7.05 | 171 | 135.6667 | 41.0667 | 4.8333
PTP | RM | 167.2 | 95.4667 | 12.95 | 0 | 256 | 166 | 15.2833 | 0 | 385.01 | 185.7833 | 37.6167 | 0 | 273 | 130.3667 | 26.0833 | 0.98333
PAMA | SM 6 | [12 empty] | 293 | 130.4833 | 36.5833 | 0
BIMA | SSB | 112.5 | 53.2 | 19.5833 | 0 | 377.7 | 96.5333 | 36.5 | 0 | 263.52 | 139.8 | 40.05 | 0 | 326.2 | 47.7667 | 28.2667 | 0
SIMS | SM A | 77 | 80.2833 | 23.3667 | 0 | 208 | 119.15 | 44.4667 | 0 | 320 | 144.65 | 64.0333 | 4.3 | 137 | 95.1333 | 34.5 | 2.7167
KMI | SM B | 74.5 | 80.9333 | 33.1167 | 0 | 234.1 | 136.0667 | 59.6167 | 0 | 352.04 | 152 | 84.85 | 3.0333 | 136.5 | 91.6667 | 50.1333 | 4.7833
PTP | SM D1 | 183.5 | 58.8833 | 25.4167 | 0 | 325.2 | 135.3167 | 23.15 | 0 | 475.51 | 126.1167 | 40.1833 | 0 | 226.6 | 69.9167 | 21.2833 | 0
Average |  | 145.1925 | 91.5033 | 18.4121 | #DIV/0! | 301 | 148.1804 | 26.7796 | #DIV/0! | 391.7055 | 171.9925 | 55.0754 | 4.3833 | 236.1523 | 79.5322 | 56.1383 | 13.0958 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
Contractor | Area | Jul |  |  |  | Aug |  |  |  | Sep |  |  |  | Oct |  |  |  | Nov |  |  |  | Dec
|  | Qty | Rain | Clean Up | Fog | Qty | Rain | Clean Up | Fog | Qty | Rain | Clean Up | Fog | Qty | Rain | Clean Up | Fog | Qty | Rain | Clean Up | Fog | Qty | Rain | Clean Up | Fog
PTP | RTN
PAMA | RS-AB
PAMA | RS-CD
PAMA | RS-EF
PAMA | RS-G
PTP | RM
BIMA | SSB
SIMS | SM A
KMI | SM B
PTP | SM D1
Average |  | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
Contractor | Area | Total
|  | Qty | Rain | Clean Up | Fog
PTP | RTN | 1111.6401 | 439.75 | 169.4667 | 22.75
PAMA | RS-AB | 1066.0301 | 474.3333 | 190.5167 | 32
PAMA | RS-CD | 1144.5101 | 473.05 | 176.9833 | 34.2833
PAMA | RS-EF | 1219.8851 | 599.45 | 155.8417 | 5.5667
PAMA | RS-G | 1230.5101 | 669.5167 | 170.35 | 11.8833
PTP | RM | 1081.2101 | 577.6167 | 91.9333 | 0.98333
BIMA | SSB | 1079.9201 | 337.3 | 124.4 | 0
SIMS | SM A | 742 | 439.2167 | 166.3667 | 7.0167
KMI | SM B | 797.14 | 460.6667 | 227.7167 | 7.8167
PTP | SM D1 | 1210.8101 | 390.2333 | 110.0333 | 0
Average |  | 1068.3656 | 486.1133 | 158.3608 | 15.2875
Note on T23: New Year 1 Jan 2023 off Stop Prod due to RKAB : 2-3 Jan '23
Note on Z23: New Year 1 Jan 2023 off Stop Prod due to RKAB : 2-3 Jan '23
Note on T26: Gusti Elissa Damayanti: Hari Raya Idul Fitri
Note on Z26: Gusti Elissa Damayanti: Hari Raya Idul Fitri
Note on T28: Idul adha 7 juni 2022
Note on Z28: Idul Adha
Note on T29: Idul Adha 7 juli 2022
Note on Z29: Idul Adha 7 juli 2022
Note on T30: Yanti : HUT RI 17 Aug 2021
Note on Z30: Yanti : HUT RI 17 Aug 2021
Note on S34: Gusti Elissa Damayanti: 3-5 dec STOP Operation
Note on T34: Lissa: 3-5 dec STOP Operation
Note on Z34: Yanti : Christmas 25 Dec 2021
Note on B36: Gusti Elissa Damayanti: Since April '23, PAMA's responsibility
Note on B70: Gusti Elissa Damayanti: Since April '23, PAMA's responsibility

## Volume (Bcm;Ton)
|  |  | PRODUCTION DEPARTMENT | [16 empty] | Departemen |  | Produksi
[20 empty] | No. Form |  | FM/PROD-027
[20 empty] | Tgl. Pembuatan |  | 2015-01-05
|  |  | ( SHORT REPORT ) | [16 empty] | No/Tgl. Revisi |  | 02/23-Sep-2018
TYPE |  | Occasional |  |  |  |  | Daily |  |  |  |  | Weekly |  |  |  | Monthly |  |  |  | Yearly
PIT |  | RTN |  | RTM |  | RTS-AF |  |  |  | RTS-G |  | SM A |  | SM 6 |  | SM B |  | SM D1 |  | SM D2 |  | SSB
CONTRACTOR |  | PAMA |  |  |  |  | SIMS | [8 empty] | PETROSEA |  |  |  | BIMA
SECTION |  | PLANNING |  |  |  |  | PIT CONTROL |  |  |  |  | PIT SERVICE |  |  |  | SAFETY |  |  |  | ADMIN
1. Periode |  | 21-27 May 2023
2. Reported by |  | Gusti Elissa D.
* Production Achievement (Based on B/Plan)
>> Waste Removal | [22 empty] | Unit : Bcm
Pit | Contractor | Plan Y2023 | Jan |  |  | Feb |  |  | Mar |  |  | Apr |  |  | May |  |  | Jun |  |  | 1st Semester
|  |  | Plan | Actual | ΔDiff | Plan | Actual | ΔDiff | Plan | Actual | ΔDiff | Plan | Actual | ΔDiff | Plan | Actual | ΔDiff | Plan | Actual | ΔDiff | Plan | Actual | ΔDiff
RTN | PTP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
RTN | PAMA | 8940000 | 690000 | 793633 | 103633 | 660000 | 791123 | 131123 | 730000 | 740367 | 10367 | 730000 | 593829 | -136171 | 696774.1935 | 542286 | -154488.1935 | 0 | 0 | 0 | 3506774.1935 | 3461238 | -45536.1935
RTN | KMI | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
RS-CF | PAMA | 21680000 | 1680000 | 1782699 | 102699 | 1600000 | 1677719 | 77719 | 1760000 | 1613054 | -146946 | 1760000 | 1420111 | -339889 | 1680967.7419 | 1525820 | -155147.7419 | 0 | 0 | 0 | 8480967.7419 | 8019403 | -461564.7419
RS-G | PAMA | 9190000 | 710000 | 789952 | 79952 | 680000 | 681486 | 1486 | 750000 | 590559 | -159441 | 750000 | 591230 | -158770 | 714193.5484 | 709859 | -4334.5484 | 0 | 0 | 0 | 3604193.5484 | 3363086 | -241107.5484
RTM | PTP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
RTM | PAMA | 11310000 | 880000 | 979884 | 99884 | 830000 | 661856 | -168144 | 920000 | 706215 | -213785 | 920000 | 653695 | -266305 | 879677.4194 | 757445 | -122232.4194 | 0 | 0 | 0 | 4429677.4194 | 3759095 | -670582.4194
SSB | BIMA | 10180000 | 790000 | 832509 | 42509 | 750000 | 732746 | -17254 | 830000 | 805070 | -24930 | 830000 | 798360 | -31640 | 792580.6452 | 777538 | -15042.6452 | 0 | 0 | 0 | 3992580.6452 | 3946223 | -46357.6452
SAMUBIU | PAMA | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Roto | S-Total | 61300000 | 4750000 | 5178677 | 428677 | 4520000 | 4544930 | 24930 | 4990000 | 4455265 | -534735 | 4990000 | 4057225 | -932775 | 4764193.5484 | 4312948 | -451245.5484 | 0 | 0 | 0 | 24014193.5484 | 22549045 | -1465148.5484
SM AB | SIMS | 35350000 | 2740000 | 2717779 | -22221 | 2610000 | 2297729 | -312271 | 2880000 | 2245542 | -634458 | 2890000 | 681585 | -2208415 | 2743548.3871 | 1723720 | -1019828.3871 | 0 | 0 | 0 | 13863548.3871 | 9666355 | -4197193.3871
SM 6 | PAMA | 13880000 | 1080000 | 1001958 | -78042 | 1020000 | 977822 | -42178 | 1130000 | 954411 | -175589 | 1130000 | 817837 | -312163 | 1080000 | 937947 | -142053 | 0 | 0 | 0 | 5440000 | 4689975 | -750025
SM AB | PTP | 3120000 | 1040000 | 264000 | -776000 | 990000 | 235440 | -754560 | 1090000 | 182680 | -907320 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3120000 | 682120 | -2437880
SM AB | PAMA | 10250000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1090000 | 409141 | -680859 | 1036451.6129 | 630838 | -405613.6129 | 0 | 0 | 0 | 2126451.6129 | 1039979 | -1086472.6129
SM C | PAMA | 3000000 | 230000 | 0
SM D | PTP | 55630000 | 4320000 | 4637234 | 317234 | 4100000 | 3854173 | -245827 | 4530000 | 3656424 | -873576 | 4540000 | 3750436 | -789564 | 4320000 | 4331770 | 11770 | 0 | 0 | 0 | 21810000 | 20230037 | -1579963
SM D | DUM | 3000000 | 230000 | 287364 | 57364 | 220000 | 234982 | 14982 | 240000 | 180290 | -59710 | 240000 | 222750 | -17250 | 235161.2903 | 281248 | 46086.7097 | 0 | 0 | 0 | 1165161.2903 | 1206634 | 41472.7097
SM | S-Total | 124230000 | 9640000 | 8908335 | -731665 | 8940000 | 7600146 | -1339854 | 9870000 | 7219347 | -2650653 | 9890000 | 5881749 | -4008251 | 9415161.2903 | 7905523 | -1509638.2903 | 0 | 0 | 0 | 47525161.2903 | 37515100 | -10010061.2903
Total |  | 185530000 | 14390000 | 14087012 | -302988 | 13460000 | 12145076 | -1314924 | 14860000 | 11674612 | -3185388 | 14880000 | 9938974 | -4941026 | 14179354.8387 | 12218471 | -1960883.8387 | 0 | 0 | 0 | 71539354.8387 | 60064145 | -11475209.8387
Pit | Contractor | Plan Y2023 | Jul |  |  | Aug |  |  | Sep |  |  | Oct |  |  | Nov |  |  | Dec |  |  | YTD 2022
|  |  | Plan | Actual | ΔDiff | Plan | Actual | ΔDiff | Plan | Actual | ΔDiff | Plan | Actual | ΔDiff | Plan | Actual | ΔDiff | Plan | Actual | ΔDiff | Plan | Actual | ΔDiff
RTN | PTP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
RTN | PAMA | 8940000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3506774.1935 | 3461238 | -45536.1935
RTN | KMI | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
RS-CF | PAMA | 21680000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8480967.7419 | 8019403 | -461564.7419
RS-G | PAMA | 9190000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3604193.5484 | 3363086 | -241107.5484
RTM | PTP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
RTM | PAMA | 11310000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4429677.4194 | 3759095 | -670582.4194
SSB | BIMA | 10180000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3992580.6452 | 3946223 | -46357.6452
SAMUBIU | PAMA | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Roto | S-Total | 61300000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24014193.5484 | 22549045 | -1465148.5484
SM AB | SIMS | 35350000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13863548.3871 | 9666355 | -4197193.3871
SM 6 | PAMA | 13880000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5440000 | 4689975 | -750025
SM AB | PTP | 3120000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3120000 | 682120 | -2437880
SM AB | PAMA | 10250000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2126451.6129 | 1039979 | -1086472.6129
SM C | PAMA | 3000000 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SM D | PTP | 55630000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21810000 | 20230037 | -1579963
SM D | DUM | 3000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1165161.2903 | 1206634 | 41472.7097
SM | S-Total | 124230000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 47525161.2903 | 37515100 | -10010061.2903
Total |  | 185530000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 71539354.8387 | 60064145 | -11475209.8387
* Production Achievement (Based on A/Plan) | [16 empty] | Unit : Bcm |  | * Remarks :
Pit | Contractor | Plan May | Week I |  |  | Week II |  |  | Week III |  |  | Week IV |  |  | Week V |  |  |  | - Source data : Daily Report Planning Department
|  |  | Plan | Actual | ΔDiff | Plan | Actual | ΔDiff | Plan | Actual | ΔDiff | Plan | Actual | ΔDiff | Plan | Actual | ΔDiff |  | - Waste volume Jan-Apr based on trucking
RTN | PTP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | >> Sims 100% of trucking data ; HD 42 bcm
RTN | PAMA | 850000 | 164516.129 | 126367 | -38149.129 | 191935.4839 | 151575 | -40360.4839 | 191935.4839 | 99628 | -92307.4839 | 191935.4839 | 104124 | -87811.4839 | 109677.4194 |  | -109677.4194 |  | >> Pama 100% of trucking data ; HD 42 bcm
RTN | KMI | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | >> Petrosea 100% of trucking data ; HD 40 bcm
RS-CF | PAMA | 1928000 | 373161.2903 | 335293 | -37868.2903 | 435354.8387 | 405612 | -29742.8387 | 435354.8387 | 428538 | -6816.8387 | 435354.8387 | 367538 | -67816.8387 | 248774.1935 |  | -248774.1935 |  | >> Bima 100% of trucking data ; DT 8 bcm
RS-G | PAMA | 935000 | 180967.7419 | 146564 | -34403.7419 | 211129.0323 | 169986 | -41143.0323 | 211129.0323 | 202636 | -8493.0323 | 211129.0323 | 215226 | 4096.9677 | 120645.1613 |  | -120645.1613
RTM | PTP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
RTM | PAMA | 929000 | 179806.4516 | 161316 | -18490.4516 | 209774.1935 | 195575 | -14199.1935 | 209774.1935 | 216824 | 7049.8065 | 209774.1935 | 174224 | -35550.1935 | 119870.9677 |  | -119870.9677
SSB | BIMA | 833000 | 161225.8065 | 156864 | -4361.8065 | 188096.7742 | 191386 | 3289.2258 | 188096.7742 | 205336 | 17239.2258 | 188096.7742 | 194630 | 6533.2258 | 107483.871 |  | -107483.871
SAMUBIU | PAMA | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
Roto | S-Total | 5475000 | 1059677.4194 | 926404 | -133273.4194 | 1236290.3226 | 1114134 | -122156.3226 | 1236290.3226 | 1152962 | -83328.3226 | 1236290.3226 | 1055742 | -180548.3226 | 706451.6129 | 0 | -706451.6129
SM AB | SIMS | 3150000 | 609677.4194 | 338809 | -270868.4194 | 711290.3226 | 438579 | -272711.3226 | 711290.3226 | 511962 | -199328.3226 | 711290.3226 | 386757 | -324533.3226 | 406451.6129 |  | -406451.6129
SM 6 | PAMA | 1356000 | 262451.6129 | 178196 | -84255.6129 | 306193.5484 | 232260 | -73933.5484 | 306193.5484 | 311601 | 5407.4516 | 306193.5484 | 247257 | -58936.5484 | 174967.7419 |  | -174967.7419
SM AB | PTP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
SM AB | PAMA | 550000 | 106451.6129 | 109960 | 3508.3871 | 124193.5484 | 169986 | 45792.4516 | 124193.5484 | 196454 | 72260.4516 | 124193.5484 | 215226 | 91032.4516 | 70967.7419 |  | -70967.7419
SM C | PAMA | 190000 | 36774.1935 | 0 | -36774.1935 | 42903.2258 | 0 | -42903.2258 | 42903.2258 | 0 | -42903.2258 | 42903.2258 | 0 | -42903.2258 | 24516.129 |  | -24516.129
SM D | PTP | 6000000 | 1161290.3226 | 860832 | -300458.3226 | 1354838.7097 | 1049636 | -305202.7097 | 1354838.7097 | 1203101 | -151737.7097 | 1354838.7097 | 1154139 | -200699.7097 | 774193.5484 |  | -774193.5484
SM D | DUM | 263000 | 50903.2258 | 54197 | 3293.7742 | 59387.0968 | 66451 | 7063.9032 | 59387.0968 | 79541 | 20153.9032 | 59387.0968 | 74855 | 15467.9032 | 33935.4839 |  | -33935.4839
SM | S-Total | 11509000 | 2227548.3871 | 1541994 | -685554.3871 | 2598806.4516 | 1956912 | -641894.4516 | 2598806.4516 | 2302659 | -296147.4516 | 2598806.4516 | 2078234 | -520572.4516 | 1485032.2581 | 0 | -1485032.2581
Total |  | 16984000 | 3287225.8065 | 2468398 | -818827.8065 | 3835096.7742 | 3071046 | -764050.7742 | 3835096.7742 | 3455621 | -379475.7742 | 3835096.7742 | 3133976 | -701120.7742 | 2191483.871 | 0 | -2191483.871
* Production Achievement (Based on B/Plan)
>> Coal Production | [22 empty] | Unit : Ton
Pit | Contractor | Plan Y2023 | Jan |  |  | Feb |  |  | Mar |  |  | Apr |  |  | May |  |  | Jun |  |  | 1st Semester
|  |  | Plan | Actual | ΔDiff | Plan | Actual | ΔDiff | Plan | Actual | ΔDiff | Plan | Actual | ΔDiff | Plan | Actual | ΔDiff | Plan | Actual | ΔDiff | Plan | Actual | ΔDiff
RTN | PTP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
RTN | PAMA | 1110000 | 90000 | 54950 | -35050 | 80000 | 50779 | -29221 | 90000 | 73383 | -16617 | 90000 | 48481.4 | -41518.6 | 87096.7742 | 48481.4 | -38615.3742 | 0 | 0 | 0 | 437096.7742 | 276074.8 | -161021.9742
RTN | KMI | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
RS-CF | PAMA | 2320000 | 180000 | 272378 | 92378 | 170000 | 322351 | 152351 | 190000 | 319948 | 129948 | 190000 | 212491.4 | 22491.4 | 182903.2258 | 212491.4 | 29588.1742 | 0 | 0 | 0 | 912903.2258 | 1339659.8 | 426756.5742
RS-G | PAMA | 1320000 | 100000 | 36986 | -63014 | 100000 | 67565 | -32435 | 110000 | 34543 | -75457 | 110000 | 87699.7 | -22300.3 | 104516.129 | 87699.7 | -16816.429 | 0 | 0 | 0 | 524516.129 | 314493.4 | -210022.729
RTM | PTP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
RTM | PAMA | 1950000 | 150000 | 202480 | 52480 | 140000 | 181076 | 41076 | 160000 | 167084 | 7084 | 160000 | 181737.7 | 21737.7 | 148064.5161 | 181737.7 | 33673.1839 | 0 | 0 | 0 | 758064.5161 | 914115.4 | 156050.8839
SSB | BIMA | 840000 | 70000 | 73819 | 3819 | 60000 | 87084 | 27084 | 70000 | 73279 | 3279 | 70000 | 77305.4 | 7305.4 | 60967.7419 | 77305.4 | 16337.6581 | 0 | 0 | 0 | 330967.7419 | 388792.8 | 57825.0581
SAMUBIU | PAMA | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Roto | S-Total | 7540000 | 590000 | 640613 | 50613 | 550000 | 708855 | 158855 | 620000 | 668237 | 48237 | 620000 | 607715.6 | -12284.4 | 583548.3871 | 607715.6 | 24167.2129 | 0 | 0 | 0 | 2963548.3871 | 3233136.2 | 269587.8129
SM AB | SIMS | 6440000 | 500000 | 647737 | 147737 | 470000 | 613388 | 143388 | 520000 | 657249 | 137249 | 530000 | 546510.6 | 16510.6 | 496451.6129 | 546510.6 | 50058.9871 | 0 | 0 | 0 | 2516451.6129 | 3011395.2 | 494943.5871
SM 6 | PAMA | 2630000 | 200000 | 7127 | -192873 | 190000 | 0 | -190000 | 210000 | 7388 | -202612 | 210000 | 61818.7 | -148181.3 | 200322.5806 | 61818.7 | -138503.8806 | 0 | 0 | 0 | 1010322.5806 | 138152.4 | -872170.1806
SM AB | PTP | 570000 | 190000 | 82506 | -107494 | 180000 | 35182 | -144818 | 200000 | 0 | -200000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 570000 | 117688 | -452312
SM AB | PAMA | 1830000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200000 | 65208.6 | -134791.4 | 182903.2258 | 65208.6 | -117694.6258 | 0 | 0 | 0 | 382903.2258 | 130417.2 | -252486.0258
SM C | PAMA | 670000 | 50000 | 0 | -50000 | [9 empty] | 52258.0645 | 0 | -52258.0645
SM D | PTP | 11320000 | 1050000 | 1025342 | -24658 | 980000 | 931872 | -48128 | 1060000 | 893969 | -166031 | 1010000 | 1107215.21 | 97215.21 | 862258.0645 | 1107215.21 | 244957.1455 | 0 | 0 | 0 | 4962258.0645 | 5065613.42 | 103355.3555
SM D | DUM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SM | S-Total | 23460000 | 1990000 | 1762712 | -227288 | 1820000 | 1580442 | -239558 | 1990000 | 1558606 | -431394 | 1950000 | 1780753.11 | -169246.89 | 1794193.5484 | 1780753.11 | -13440.4384 | 0 | 0 | 0 | 9441935.4839 | 8463266.22 | -978669.2639
Total |  | 31000000 | 2580000 | 2403325 | -176675 | 2370000 | 2289297 | -80703 | 2610000 | 2226843 | -383157 | 2570000 | 2388468.71 | -181531.29 | 2377741.9355 | 2388468.71 | 10726.7745 | 0 | 0 | 0 | 12405483.871 | 11696402.42 | -709081.451
Pit | Contractor | Plan Y2023 | Jul |  |  | Aug |  |  | Sep |  |  | Oct |  |  | Nov |  |  | Dec |  |  | YTD 2022
|  |  | Plan | Actual | ΔDiff | Plan | Actual | ΔDiff | Plan | Actual | ΔDiff | Plan | Actual | ΔDiff | Plan | Actual | ΔDiff | Plan | Actual | ΔDiff | Plan | Actual | ΔDiff
RTN | PTP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
RTN | PAMA | 1110000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 437096.7742 | 276074.8 | -161021.9742
RTN | KMI | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
RS-CF | PAMA | 2320000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 912903.2258 | 1339659.8 | 426756.5742
RS-G | PAMA | 1320000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 524516.129 | 314493.4 | -210022.729
RTM | PTP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
RTM | PAMA | 1950000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 758064.5161 | 914115.4 | 156050.8839
SSB | BIMA | 840000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 330967.7419 | 388792.8 | 57825.0581
SAMUBIU | PAMA | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Roto | S-Total | 7540000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2963548.3871 | 3233136.2 | 269587.8129
SM AB | SIMS | 6440000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2516451.6129 | 3011395.2 | 494943.5871
SM 6 | PAMA | 2630000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1010322.5806 | 138152.4 | -872170.1806
SM AB | PTP | 570000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 570000 | 117688 | -452312
SM AB | PAMA | 1830000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 382903.2258 | 130417.2 | -252486.0258
SM C | PAMA | 670000 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SM D | PTP | 11320000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4962258.0645 | 5065613.42 | 103355.3555
SM D | DUM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SM | S-Total | 23460000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9441935.4839 | 8463266.22 | -978669.2639
Total |  | 31000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12405483.871 | 11696402.42 | -709081.451
* Production Achievement (Based on A/Plan) | [16 empty] | Unit : Ton |  | * Remarks :
Pit | Contractor | Plan May | Week I |  |  | Week II |  |  | Week III |  |  | Week IV |  |  | Week V |  |  |  | - Source data : Daily Report Planning Department
|  |  | Plan | Actual | ΔDiff | Plan | Actual | ΔDiff | Plan | Actual | ΔDiff | Plan | Actual | ΔDiff | Plan | Actual | ΔDiff |  | - Coal volume based on RFID system data
RTN | PTP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
RTN | PAMA | 64000 | 12387.0968 | 9411 | -2976.0968 | 14451.6129 | 11068.2 | -3383.4129 | 14451.6129 | 21303.3 | 6851.6871 | 14451.6129 | 11068.2 | -3383.4129 | 8258.0645 |  | -8258.0645
RTN | KMI | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
RS-CF | PAMA | 210000 | 40645.1613 | 40433 | -212.1613 | 47419.3548 | 52950.8 | 5531.4452 | 47419.3548 | 70173.5 | 22754.1452 | 47419.3548 | 52950.8 | 5531.4452 | 27096.7742 |  | -27096.7742
RS-G | PAMA | 50000 | 9677.4194 | 16262 | 6584.5806 | 11290.3226 | 17980.7 | 6690.3774 | 11290.3226 | 30926 | 19635.6774 | 11290.3226 | 17980.7 | 6690.3774 | 6451.6129 |  | -6451.6129
RTM | PTP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
RTM | PAMA | 175000 | 33870.9677 | 38129 | 4258.0323 | 39516.129 | 39240.8 | -275.329 | 39516.129 | 59728 | 20211.871 | 39516.129 | 39240.8 | -275.329 | 22580.6452 |  | -22580.6452
SSB | BIMA | 70000 | 13548.3871 | 11857 | -1691.3871 | 15806.4516 | 21171.3 | 5364.8484 | 15806.4516 | 28622.1 | 12815.6484 | 15806.4516 | 21171.3 | 5364.8484 | 9032.2581 |  | -9032.2581
SAMUBIU | PAMA | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
Roto | S-Total | 569000 | 110129.0323 | 116092 | 5962.9677 | 128483.871 | 142411.8 | 13927.929 | 128483.871 | 210752.9 | 82269.029 | 128483.871 | 142411.8 | 13927.929 | 73419.3548 | 0 | -73419.3548
SM AB | SIMS | 722000 | 139741.9355 | 101839 | -37902.9355 | 163032.2581 | 115160.3 | -47871.9581 | 163032.2581 | 175894.6 | 12862.3419 | 163032.2581 | 115160.3 | -47871.9581 | 93161.2903 |  | -93161.2903
SM 6 | PAMA | 100000 | 19354.8387 | 6051 | -13303.8387 | 22580.6452 | 26818.1 | 4237.4548 | 22580.6452 | 16290.1 | -6290.5452 | 22580.6452 | 26818.1 | 4237.4548 | 12903.2258 |  | -12903.2258
SM AB | PTP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
SM AB | PAMA | 146000 | 28258.0645 | 12503 | -15755.0645 | 32967.7419 | 18171.5 | -14796.2419 | 32967.7419 | 15588.2 | -17379.5419 | 32967.7419 | 18171.5 | -14796.2419 | 18838.7097 |  | -18838.7097
SM C | PAMA | 76000 | 14709.6774 | 0 | -14709.6774 | 17161.2903 | 0 | -17161.2903 | 17161.2903 | 0 | -17161.2903 | 17161.2903 | 0 | -17161.2903 | 9806.4516 |  | -9806.4516
SM D | PTP | 1262000 | 244258.0645 | 237519 | -6739.0645 | 284967.7419 | 275758.9 | -9208.8419 | 284967.7419 | 298480 | 13512.2581 | 284967.7419 | 275758.9 | -9208.8419 | 162838.7097 |  | -162838.7097
SM D | DUM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
SM | S-Total | 2306000 | 446322.5806 | 357912 | -88410.5806 | 520709.6774 | 435908.8 | -84800.8774 | 520709.6774 | 506252.9 | -14456.7774 | 520709.6774 | 435908.8 | -84800.8774 | 297548.3871 | 0 | -297548.3871
Total |  | 2875000 | 556451.6129 | 474004 | -82447.6129 | 649193.5484 | 578320.6 | -70872.9484 | 649193.5484 | 717005.8 | 67812.2516 | 649193.5484 | 578320.6 | -70872.9484 | 370967.7419 | 0 | -370967.7419

## May
bl | DAILY PRODUCTION REPORT | [16 empty] | 26
| 2023-05-27 | [69 empty] | DATE | DEVELOPMENT | [18 empty] | COAL PRODUCTION
| 1. PRODUCTION |  |  | ACTUAL W/DAY (MONTHLY) : |  |  |  | 27 |  |  |  | ACTUAL W/DAY (YEARLY) : |  |  |  |  | 143 | [54 empty] | WASTE ( Bcm ) | [18 empty] | COAL ( Ton )
| DESCRIPTION |  |  |  |  | DAILY |  |  |  | MONTHLY |  |  |  | YEARLY | [57 empty] | B/PLAN | ReForecast | A/PLAN | NORTH | SM C |  | C/D | E/F | M | SM # 6 | SM B | SM.A | SM.B | G | SM.D |  | SSB | TOTAL | % | B/PLAN | ReForecast | A/PLAN | RTN | SM C | C/D | E/F | M | SM # 6 | SM.ABC |  | G | SM.D |  | SSB | TOTAL | % | S/R
[6 empty] | PLAN |  | ACTUAL | DIFF | PLAN | ACTUAL | DIFF | Per Day | B/PLAN | ReForecast | ACTUAL | DIFF (act-bplan) | Per Day | [6 empty] | TTL | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | [37 empty] | PAMA |  |  | PAMA |  |  |  |  | SIMS | Petrosea | PAMA | Petrosea | DUM | BIMA | [5 empty] | PAMA | [5 empty] | SIMS | PAMA | PAMA | Petrosea | DUM | BIMA
| WASTE (BCM) |  |  |  |  | 547871 |  | 399897 | -147974 | 14792516 | 12218471 | -2574045 | 452535.963 | 72714516 | 0 | 59129899 | -13584617 | 427860.1995 | [6 empty] | 143 | 28 | 28 | 31 | 29 | 27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [33 empty] | 21 | 533870.9677 | 0 | 547870.9677 | 4622 |  |  | 60368 | 0 | 30320 | 48339 | 23714 | 56215 |  | 31223 | 192928 | 12584 | 29916 | 490229 | 89.4789 | 88064.5161 | 0 | 92741.9355 | 1241.2 |  | 9051.6 |  | 8671.1 | 3815.9 | 18497.6 | 2275.6 | 3979.5 | 49553.8 | 0 | 2482.8 | 99569.1 | 107.3615 | 4.9235
|  |  | North | Petrosea |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 27 | 27 | 26 | 26 | 1 | 1 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [33 empty] | 22 | 533870.9677 | 0 | 547870.9677 | 19901 |  |  | 49590 | 0 | 28343 | 32945 | 28358 | 55485 |  | 33766 | 202277 | 13266 | 32195 | 496126 | 90.5553 | 88064.5161 | 0 | 92741.9355 | 1477.2 |  | 5183.8 |  | 7357.2 | 3710 | 17856.5 | 3179 | 3078.2 | 43386.3 | 0 | 2586.5 | 87814.7 | 94.6872 | 5.6497
|  |  |  | PAMA |  | 27419.4 |  | 16481 | -10938.4 | 740322.6 | 542286 | -198036.6 | 20084.6667 | 3506774.1935 |  | 3352745 | -154029.1935 | 23445.7692 | 27 | 27 | 26 | 26 | 1 | 1 | 143 | 28 | 28 | 31 | 29 | 27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [33 empty] | 23 | 533870.9677 | 0 | 547870.9677 | 17264 |  |  | 33936 | 0 | 13231 | 38005 | 28498 | 65780 |  | 32791 | 134787 | 9394 | 24463 | 398149 | 72.672 | 88064.5161 | 0 | 92741.9355 | 1873.6 |  | 5969.9 |  | 4856.1 | 5274.9 | 21683 | 1842.5 | 2947.2 | 38096.8 | 0 | 2934.6 | 85478.6 | 92.1682 | 4.6579
|  |  |  | KMI |  |  |  | 0 | 0 |  |  | 0 | 0 |  |  |  | 0 | 0 | 27 | 27 | 10 | 10 | 17 | 17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [33 empty] | 24 | 533870.9677 | 0 | 547870.9677 | 7262 |  |  | 21793 | 0 | 12696 | 20821 | 12565 | 28553 |  | 12331 | 79050 | 3894 | 22737 | 221702 | 40.4661 | 88064.5161 | 0 | 92741.9355 | 79.2 |  | 3478.1 |  | 2355.7 | 2674.3 | 6614 | 1122.4 | 665.3 | 26490.7 | 0 | 2597.4 | 46077.1 | 49.6831 | 4.8115
|  |  | South C/D | PAMA |  | 62193.5 |  | 45610 | -16583.5 | 1679225.8 | 1525820 | -153405.8 | 56511.8519 | 8490967.7419 |  | 7820407 | -670560.7419 | 54688.1608 | 27 | 27 | 26 | 26 | 1 | 1 | 143 | 28 | 28 | 31 | 29 | 27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [33 empty] | 25 | 533870.9677 | 0 | 547870.9677 | 22576 |  |  | 78567 | 0 | 30478 | 36325 | 33273 | 79759 |  | 33981 | 201716 | 12903 | 29271 | 558849 | 102.0038 | 88064.5161 | 0 | 92741.9355 | 2070.2 |  | 9517.4 |  | 9066.4 | 5505.9 | 25907.4 | 3574 | 1943.7 | 46069.4 | 0 | 3135.4 | 106789.8 | 115.1473 | 5.2332
|  |  | South E/F | PAMA |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 27 | 27 | 10 | 10 | 17 | 17 | 87 | 28 | 28 | 31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [33 empty] | 26 | 533870.9677 | 0 | 547870.9677 | 22931 |  |  | 72483 |  | 28141 | 48746 | 25706 | 68754 |  | 39327 | 183287 | 10670 | 28010 | 528055 | 96.3831 | 88064.5161 | 0 | 92741.9355 | 2119.2 |  | 9362.3 |  | 4652.8 | 3761.7 | 22140.4 | 3206 | 3588.2 | 42745.9 |  | 2909.7 | 94486.2 | 101.8808 | 5.5887
|  |  | South G | PAMA |  | 30161.3 |  | 27557 | -2604.3 | 814354.8 | 709859 | -104495.8 | 26291.0741 | 3604193.5484 |  | 3330633 | -273560.5484 | 23291.1399 | 27 | 27 | 26 | 26 | 1 | 1 | 143 | 28 | 28 | 31 | 29 | 27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [33 empty] | 27 | 533870.9677 | 0 | 547870.9677 | 9568 |  |  | 50801 |  | 31015 | 22076 | 12690 | 32211 |  | 31807 | 160094 | 12144 | 28038 | 390444 | 71.2657 | 88064.5161 | 0 | 92741.9355 | 2207.6 |  | 10387.7 |  | 2281.5 | 2075.4 | 2461.4 | 2972 | 1778.6 | 29416 | 0 | 4524.9 | 58105.1 | 62.6525 | 6.7196 | 0
|  |  | South M | PAMA |  | 29967.7 |  | 19503 | -10464.7 | 809129 | 757445 | -51684 | 28053.5185 | 4429677.4194 |  | 3534090 | -895587.4194 | 24713.9161 | 27 | 27 | 26 | 26 | 1 | 1 | 143 | 28 | 28 | 31 | 29 | 27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [34 empty] | Tot | 0 | 3835096.7742 | 104124 | 0 | 0 | 367538 | 0 | 174224 | 247257 | 164804 | 386757 | 0 | 215226 | 1154139 | 74855 | 194630 | 3083554 | 562.8249 | 616451.6129 | 0 | 649193.5484 | 11068.2 |  | 52950.8 | 0 | 39240.8 | 26818.1 | 115160.3 | 18171.5 | 17980.7 | 275758.9 | 0 | 21171.3 | 578320.6 | 623.5805
|  |  | SM B | PAMA |  | 17741.9 |  | 16933 | -808.9 | 479032.3 | 630838 | 151805.7 | 23364 | 2126451.6129 |  | 1039979 | -1086472.6129 | 18571.0536 | 27 | 27 | 26 | 26 | 1 | 1 | 56 | 0 | 0 | 0 | 29 | 27 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | SM #6 | PAMA |  | 43741.9 |  | 27764 | -15977.9 | 1181032.3 | 937947 | -243085.3 | 34738.7778 | 5440000 |  | 4883515 | -556485 | 34150.4545 | 27 | 27 | 26 | 26 | 1 | 1 | 143 | 28 | 28 | 31 | 29 | 27 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | SM A,B | SIMS |  | 101612.9 |  | 57274 | -44338.9 | 2743548.4 | 1723720 | -1019828.4 | 63841.4815 | 13863548.3871 |  | 9607571 | -4255977.3871 | 67185.8112 | 27 | 27 | 26 | 26 | 1 | 1 | 143 | 28 | 28 | 31 | 29 | 27 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | SM B | Petrosea |  |  |  |  | 0 |  | 0 | 0 | 0 | 3120000 |  | 681129 | -2438871 | 7829.069 |  |  | 0 | 0 | 0 | 0 | 87 | 28 | 28 | 31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | SM C #8 | PAMA |  | 6129 |  |  | -6129 | 165483.9 | 0 | -165483.9 | 0 | 1165161.2903 |  | 0 | -1165161.2903 | 0 | 27 | 27 | 26 | 26 | 1 | 1 | 27 | 0 | 0 | 0 | 0 | 27 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | SM D | Petrosea |  | 193548.4 |  | 146484 | -47064.4 | 5225806.5 | 4331770 | -894036.5 | 160435.9259 | 21810000 |  | 19823321 | -1986679 | 138624.6224 | 27 | 27 | 26 | 26 | 1 | 1 | 143 | 28 | 28 | 31 | 29 | 27 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | DUM |  | 8483.9 |  | 9361 | 877.1 | 229064.5 | 281248 | 52183.5 | 10416.5926 | 1165161.2903 |  | 1195963 | 30801.7097 | 8363.3776 | 27 | 27 | 26 | 26 | 1 | 1 | 143 | 28 | 28 | 31 | 29 | 27 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | SSB | BIMA |  | 26871 |  | 32930 | 6059 | 725516.1 | 777538 | 52021.9 | 28797.7037 | 3992580.6452 |  | 3860546 | -132034.6452 | 26996.8252 | 27 | 27 | 26 | 26 | 1 | 1 | 143 | 28 | 28 | 31 | 29 | 27 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| COAL (Ton) |  |  | 0% |  | 92742 |  | 77048.9 | -15693.1 | 2504032 | 2388468.71 | -115563.29 | 88461.8041 | 12657742 |  | 11111117.71 | -1546624.29 | 79389.978 | 0 | [5 empty] | 143 | 28 | 28 | 31 | 29 | 27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2023-05-01 | 2023-05-02 | 2023-05-03 | 2023-05-04 | 2023-05-05 | 2023-05-06 | 2023-05-07 | 2023-05-08 | 2023-05-09 | 2023-05-10 | 2023-05-11 | 2023-05-12 | 2023-05-13 | 2023-05-14 | 2023-05-15 | 2023-05-16 | 2023-05-17 | 2023-05-18 | 2023-05-19 | 2023-05-20 | 2023-05-21 | 2023-05-22 | 2023-05-23 | 2023-05-24 | 2023-05-25 | 2023-05-26 | 2023-05-27 | 2023-05-28 | 2023-05-29 | 2023-05-30 | 2023-05-31 | ttl
|  |  | North | Petrosea |  |  |  |  | 0 |  |  | 0 | 0 |  |  |  | 0 | 0 | 27 | 27 | 10 | 10 | 17 | 17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 24 | 28
|  |  |  | PAMA |  | 2064.5 |  | 1192.6 | -871.9 | 55741.9 | 48481.4 | -7260.5 | 1796 | 437096.7742 |  | 288673.4 | -148423.3742 | 2018.6951 | 27 | 27 | 26 | 26 | 1 | 1 | 143 | 28 | 28 | 31 | 29 | 27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 27 | 29
|  |  | South A/C | Petrosea |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 27 | 27 | 10 | 10 | 17 | 17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29
|  |  | South C/D | PAMA |  | 6774.2 |  | 7640.3 | 866.1 | 182903.2 | 212491.4 | 29588.2 | 7870 | 912903.2258 |  | 1416671.4 | 503768.1742 | 9906.793 | 27 | 27 | 26 | 26 | 1 | 1 | 143 | 28 | 28 | 31 | 29 | 27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 27 | 29
|  |  | South G | PAMA |  | 1612.9 |  | 2735.7 | 1122.8 | 43548.4 | 87699.7 | 44151.3 | 3248 | 524516.129 |  | 261929.7 | -262586.429 | 1831.6762 | 27 | 27 | 26 | 26 | 1 | 1 | 143 | 28 | 28 | 31 | 29 | 27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 27 | 29
|  |  | South M | PAMA |  | 5645.2 |  | 5011 | -634.2 | 152419.4 | 181737.7 | 29318.3 | 6731 | 758064.5161 |  | 895394.7 | 137330.1839 | 6261.5014 | 27 | 27 | 26 | 26 | 1 | 1 | 143 | 28 | 28 | 31 | 29 | 27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 27 | 29
|  |  | SM B | PAMA |  | 4709.7 |  | 5047.8 | 338.1 | 127161.3 | 65208.6 | -61952.7 | 2415 | 382903.2258 |  | 106783.6 | -276119.6258 | 1906.85 | 27 | 27 | 26 | 26 | 1 | 1 | 56 | 0 | 0 | 0 | 29 | 27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 27 | 29
|  |  | SM #6 | PAMA |  | 3225.8 |  | 1690.9 | -1534.9 | 87096.8 | 61818.7 | -25278.1 | 2290 | 1010322.5806 |  | 115800.7 | -894521.8806 | 809.7951 | 27 | 27 | 26 | 26 | 1 | 1 | 143 | 28 | 28 | 31 | 29 | 27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 27 | 29
|  |  | SM A,B | SIMS |  | 23290.3 |  | 12914.3 | -10376 | 628838.7 | 546510.6 | -82328.1 | 20241 | 2516451.6129 |  | 2656478.6 | 140026.9871 | 18576.7734 | 27 | 27 | 26 | 26 | 1 | 1 | 143 | 28 | 28 | 31 | 29 | 27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 27 | 29
|  |  | SM B | Petrosea |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 570000 |  | 117688 | -452312 | 1352.7356 |  |  | 0 | 0 | 0 | 0 | 87 | 28 | 28 | 31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 27 | 29
|  |  | SM C #8 | PAMA |  | 2451.6 |  |  | -2451.6 | 66193.5 | 0 | -66193.5 | 0 | 252258.0645 |  | 0 | -252258.0645 | 0 | 27 | 27 | 26 | 26 | 1 | 1 | 27 | 0 | 0 | 0 | 0 | 27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 27 | 29
|  |  | SM D | Petrosea |  | 40709.7 |  | 37917.2 | -2792.5 | 1099161.3 | 1107215.21 | 8053.91 | 41008 | 4962258.0645 |  | 4863286.21 | -98971.8545 | 34008.9945 | 27 | 27 | 26 | 26 | 1 | 1 | 143 | 28 | 28 | 31 | 29 | 27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 27 | 29
|  |  |  | DUM |  |  |  |  | 0 |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 27 | 27 | 10 | 10 | 17 | 17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 27 | 29
|  |  | SSB | BIMA |  | 2258.1 |  | 2899.1 | 641 | 60967.7 | 77305.4 | 16337.7 | 2863 | 330967.7419 |  | 388411.4 | 57443.6581 | 2716.1636 | 27 | 27 | 26 | 26 | 1 | 1 | 143 | 28 | 28 | 31 | 29 | 27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 27 | 29
| STRIP RATIO |  |  | 0 |  | 5.91 |  | 5.19 | -0.72 | 5.91 | 5.12 | -0.79 |  | 5.74 |  | 5.32 | -0.42
|  |  | North | Petrosea |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0
|  |  |  | PAMA |  | 13.28 | 0 | 13.82 | 0.54 | 13.28 | 11.19 | -2.09 |  | 8.02 | 0 | 11.61 | 3.59
|  |  | South A/C | PAMA |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
|  |  | South C/D | PAMA |  | 9.18 | 0 | 5.97 | -3.21 | 9.18 | 7.18 | -2 |  | 9.3 | 0 | 5.52 | -3.78
|  |  | South G | PAMA |  | 18.7 | 0 | 10.07 | -8.63 | 18.7 | 8.09 | -10.61 |  | 6.87 | 0 | 12.72 | 5.85
|  |  | South M | PAMA |  | 5.31 | 0 | 3.89 | -1.42 | 5.31 | 4.17 | -1.14 |  | 5.84 | 0 | 3.95 | -1.89
|  |  | SM B | PAMA |  | 3.77 | #REF! | 3.35 | -0.42 | 3.77 | 9.67 | 5.9 |  | 5.55 | #REF! | 9.74 | 4.19
|  |  | SM #6 | PAMA |  | 13.56 | 0 | 16.42 | 2.86 | 13.56 | 15.17 | 1.61 |  | 5.38 | 0 | 42.17 | 36.79
|  |  | SM ABC | SIMS |  | 4.36 | 0 | 4.43 | 0.07 | 4.36 | 3.15 | -1.21 |  | 5.51 | 0 | 3.62 | -1.89
|  |  |  | Petrosea |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 5.47 | 0 | 5.79 | 0.32
|  |  | SM C#8 | PAMA |  | 2.5 | 0 | 0 | -2.5 | 2.5 | 0 | -2.5 |  | 4.62 | 0 | 0 | -4.62
|  |  | SM D | Petrosea (DUM Inc.) |  | 4.96 | 0 | 4.11 | -0.85 | 4.96 | 4.17 | -0.79 |  | 4.63 | 0 | 4.32 | -0.31
|  |  |  | DUM |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0
|  |  | SSB | BIMA |  | 11.9 |  | 11.36 | -0.54 | 11.9 | 10.06 | -1.84 |  | 12.06 | 0 | 9.94 | -2.12
| RAIN |  |  | North |  | 0 |  | 14 | 0 | 157.5 | 82.15 | 31.2333 | 4.1994 | 1259.5 |  | 628.5 | 103.7667 |  | 4.3991 | Raintime delay Avg.
|  |  |  | South A/C |  | 0 |  | 0 | 0 | 182.5 | 84.3667 | 28.55 | 4.1821 | 1227.5 |  | 643.1167 | 145.5
|  |  |  | South C/D |  | 0 |  | 9 | 0 | 147 | 82.5333 | 30.2 | 4.1753 | 1180 |  | 643.6333 | 131.1167
|  |  |  | South E1/2 |  | 0 |  | 8.4083 | 0 | 189 | 86.6583 | 44.7083 | 4.8654 | 1153.5 |  | 689.4 | 159.1167
|  |  |  | South F |  | 0 |  | 7.5833 | 0 | 121 | 101.1667 | 33.7 | 4.9951 | 1321.5 |  | 750.5667 | 197.3333
|  |  |  | South G |  | 0 |  | 6.9167 | 0 | 118 | 101 | 33.35 | 4.9759 | 1235 |  | 748.9833 | 181.15
|  | Q'ty - R/Fall - R/Main |  | South M |  | 0 |  | 0 | 0 | 164.5 | 85.95 | 23.1833 | 4.042 | 1200.6 |  | 656.25 | 112.0833
|  |  |  | SM A |  | 55 |  | 14 | 0 | 204 | 89.7333 | 56.3167 | 5.4093 | 915 |  | 477.3333 | 196.8333
|  |  |  | SM B |  | 6 |  | 4.9333 | 8.9333 | 193.5 | 97.1667 | 70.05 | 6.1932 | 1023.6 |  | 550.4667 | 296.6667
|  |  |  | SM D1 |  | 20 |  | 3 | 1.1667 | 291 | 55.9833 | 17.25 | 2.7123 | 1502.3 |  | 454.1167 | 126.85
|  |  |  | SM #6 |  | 0 |  | 0 | 0 | 120.5 | 92.6833 | 35.6667 | 4.7537 | 600 |  | 285.3833 | 97.4667
|  |  |  | SSB |  | 0 |  | 0 | 0 | 168.5 | 43.8667 | 17.8333 | 2.2852 | 1230.4 |  | 376.9833 | 138.25
|  | TIME |  | North |  | 17:00-07:00, , , |  |  |  |  | R/Maint. Time | North | , , ,
|  |  |  | South A/C |  | , , , | [5 empty] | South A/C | , , ,
|  |  |  | South C/D |  | 16:45-01:45, , , | [5 empty] | South C/D | , , ,
|  |  |  | South E1/2 |  | 16:48-01:45, , , | [5 empty] | South E1/2 | , , ,
|  |  |  | South F |  | 18:10-01:45, , , | [5 empty] | South F | , , ,
|  |  |  | South G |  | 18:10-01:05, , , | [5 empty] | South G | , , ,
|  |  |  | South M |  | , , , | [5 empty] | South M | , , ,
|  |  |  | SM A |  | 17:00-07:00, , , | [5 empty] | SM A | , , ,
|  |  |  | SM B |  | 17:08-22:04, , , | [5 empty] | SM B | 22:04-07:00, , ,
|  |  |  | SM D1 |  | 18:00-21:00, , , | [5 empty] | SM D1 | 21:00-22:10, , ,
|  |  |  | SM #6 |  | , , , | [5 empty] | SM #6 | , ,
|  |  |  | SSB |  | , , , | [5 empty] | SSB | , , ,
| 2. HAULING |  |  | ACTUAL W/DAY (MONTHLY) : |  |  |  | 25.5 |  |  |  | ACTUAL W/DAY (YEARLY) : |  |  |  |  | 133.2426
| DESCRIPTION |  |  | Tractor | Trailer | DAILY |  |  |  | MONTHLY |  |  |  | YEARLY
[6 empty] | PLAN |  | ACTUAL | DIFF | PLAN | ACTUAL | DIFF | Per Day | B/PLAN | ReForecast | ACTUAL | DIFF (act-bplan) | Per Day | [6 empty] | TTL | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | 2023-05-01 | 2023-05-02 | 2023-05-03 | 2023-05-04 | 2023-05-05 | 2023-05-06 | 2023-05-07 | 2023-05-08 | 2023-05-09 | 2023-05-10 | 2023-05-11 | 2023-05-12 | 2023-05-13 | 2023-05-14 | 2023-05-15 | 2023-05-16 | 2023-05-17 | 2023-05-18 | 2023-05-19 | 2023-05-20 | 2023-05-21 | 2023-05-22 | 2023-05-23 | 2023-05-24 | 2023-05-25 | 2023-05-26 | 2023-05-27 | 2023-05-28 | 2023-05-29 | 2023-05-30 | 2023-05-31 | ttl
| SAMINDO |  |  | 45 | 90 | 41379.3 |  | 40143 | -1236.3 | 1055172.4 | 982853 | -72319.4 | 38543 | 4808103.4483 | 0 | 4722499 | -85604.4483 | 35375 | 25.5 | 25.5 | 24.5 | 24.5 | 1 | 1 | 133.5 | 26 | 26 | 29 | 27 | 25.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0.5 | 1 | 1 | 1 | 1 | 1 | 1 | 0.5 | 1 | 1 | 1 | 1 | 1 | 1 | 0.5 | 1 | 1 | 1 | 1 | 1 | 1 | 0.5 | 1 | 1 | 1 | 25.5 | 27.5
| TRASINDO |  |  | 39 | 78 | 36206.9 |  | 37445 | 1238.1 | 923275.9 | 937119 | 13843.1 | 36750 | 4808103.4483 | 0 | 4462084 | -346019.4483 | 33424 | 25.5 | 25.5 | 24.5 | 24.5 | 1 | 1 | 133.5 | 26 | 26 | 29 | 27 | 25.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0.5 | 1 | 1 | 1 | 1 | 1 | 1 | 0.5 | 1 | 1 | 1 | 1 | 1 | 1 | 0.5 | 1 | 1 | 1 | 1 | 1 | 1 | 0.5 | 1 | 1 | 1 | 25.5 | 27.5
| MHA |  |  | 29 | 58 | 21551.7 |  | 23875 | 2323.3 | 549569 | 511582 | -37987 | 20062 | 2798793.1034 | 0 | 2494499 | -304294.1034 | 18685 | 25.5 | 25.5 | 24.5 | 24.5 | 1 | 1 | 133.5 | 26 | 26 | 29 | 27 | 25.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0.5 | 1 | 1 | 1 | 1 | 1 | 1 | 0.5 | 1 | 1 | 1 | 1 | 1 | 1 | 0.5 | 1 | 1 | 1 | 1 | 1 | 1 | 0.5 | 1 | 1 | 1 | 25.5 | 27.5
| TOTAL |  |  | 113 | 226 | 99137.9 |  | 101463 | 2325.1 | 2528017 | 2431554 | -96463 | 95355 | 12415000 | 0 | 11679082 | -735918 | 87484 | [6 empty] | 133.2426 | 25.7426 | 26 | 29 | 27 | 25.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0.5 | 1 | 1 | 1 | 1 | 1 | 1 | 0.5 | 1 | 1 | 1 | 1 | 1 | 1 | 0.5 | 1 | 1 | 1 | 1 | 1 | 1 | 0.5 | 1 | 1 | 1 | 25.5
| 3. CRUSHING PLANT | [5 empty] | 0.15826 | 0.14762 | 0.047061
| LINE |  | R/T | R/E | S/F | B/D | M/T | OTHER | Q'ty | Ton/hr | Monthly | Remark
| MCCP | Line A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0
|  | Line B | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Line C | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Line D | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| SMCP | Line 1 (RS) | 0 | 0 | 0 | 0 | 0 | 0 | 19375 | 0 | 637136
| SM2 | Line 2 (SM) | 0 | 0 | 0 | 0 | 0 | 0 | 36116 | 0 | 608592
| SM3 | Line 3 (SM) | 0 | 0 | 0 | 0 | 0 | 0 | 18158 | 0 | 789005
| SM4 | Line 4 (SM) | 0 | 0 | 0 | 0 | 0 | 0 | 27814 | 0 | 396821
| Total |  | 0 | 0 | 0 | 0 | 0 | 0 | 101463 | 0 | 2431554 | [7 empty] | 0
| 4. SHIPMENT | [22 empty] | Transhipment | Aug: Ship.Loading; Nov: -5000; Dec: 5000
| No. | Vessel |  |  |  | TMCT Loading |  | Adangbay Loading |  |  | Barge Loading | [8 empty] | B/Loading | Daily | Actual |  | P | Jan: M; Mar: SM; Aug: P; Sep: M; Oct: SM; Nov: P; Dec: M | SM | [13 empty] | RS |  | 4500 |  | SM |  | Daily |  | RS |  | 4500 |  | SM |  | Accu
|  | Name | Arrival | ETD | Blending | Plan | Barge | 2023-05-27 | Cumulative | Remain |  | Daily | Monthly | B/PLAN | ReForecast | ACTUAL | DIFF (act-bplan) | Per Day |  |  | Tranship. | B/Loading |  | 0 |  | 10960.8 |  | 67844.2 |  | 0 |  |  | 0 | 16654 | 116077 | 24388 | 71669.987 | 4595 | TMCT STOCKPILE |  |  | -0.4 | [9 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
| 1 | MV.ZHENG RONG (DATANG) | 15/May 04:00 | 27/May 23:00 | 100 | 74900 | 74900 | 8164 | 74900 | 0 | Roto | 0 | 559432 | 3150980.4839 | 0 | 3408133 | 257152.5161 | 25578 | -23377 | -23377 | 8164 |  |  | 0 |  | 0 |  | 8164 |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 79300 | BARGE LOADING |  |  | 0 | [9 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
| 2 | MV.IO ANNA POL (SHENERGY) | 24/May 05:00 | - | 100 | 48170 | 48730 | 13248 | 43370 | 4800 | SM | 79300 | 1840948 | 9572584.0323 | 0 | 8403063 | -1169521.0323 | 63066 | 0 |  | 13248 |  |  | 0 |  | 0 |  | 13248 |  | 0 |  |  | 0 | 0 | 43370 | 0 | 39542.2 | 116573.8 |  |  |  | 0.4 | [9 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
| 3 | MV.JIE LI (KUMHO IPP) | 15/May 07:30 | - | 100 | 70890 | 72153 | 30063 | 52414 | 18476 | Total | 79300 | 2400380 | 12723564.5161 | 0 | 11811196 | -912368.5161 | 88644 | 0 | 26628 | 30063 | 26628 |  | 0 |  | 0 |  | 30063 |  | 0 |  |  | 0 | 0 | 52414 | 0 | -0.2 | 0.2 |  |  |  | 0 | [9 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
| 4 | MV.SARAH S (JAWA POWER) | 26/May 07:00 | - | 0-80-20 | 50000 | 52680 | 13701 | 20818 | 29182 | TransShipment | [7 empty] | 0 |  | 13701 |  |  | 0 |  | 10960.8 |  | 2740.2 |  | 0 |  |  | 0 | 16654.4 | 4163.6 | 0 | 39542 | 116574 | ON BARGE |  |  | 0.4 | [9 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
| 5 | MV.XIN DONG GUAN.11 (HUIHUANG 1) | 16/May 03:00 | - | 100 | 70000 | 58817 | 13629 | 16129 | 53871 |  | Daily | Monthly | B/PLAN | ReForecast | ACTUAL | DIFF (act-bplan) | Per Day | 11375 | 41488 | 13629 | 30113 |  | 0 |  | 0 |  | 13629 |  | 0 |  |  | 0 | 0 | 16129 | 24388 | 111211.987 | 121169 | TMCT Incl. OnBrg |  |  | 0 | [9 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
| 6 | MV.SFL PEARL (CCS) | 24/May 15:30 | - | 100 | 75300 | 34561 | 0 | 0 | 75300 | Roto | 10960.8 | 512385.5 | 3150980.4839 | 0 | 3303474.5 | 152494.0161 | 23101 | 12002 | 34561 |  | 22559 |  | 0 |  | 0 |  | 0 |  | 0 |  |  | 0 | 0 | 0 | 24388 | 127865.987 | 237246 |  |  |  | 0 | [9 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
| 7 | [5 empty] | 0 | 0 | 0 | 0 | SM | 67844.2 | 1816640.5 | 9572584.0323 | 0 | 8399948.5 | -1172635.5323 | 58741 | 0 |  |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  |  | 0 | 0 | 0 | 0 | 39542 | 116574 | 0.4 | Diff_OnBrg wth Daily | [10 empty] | 0.4 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
| 8 | [5 empty] | 0 | 0 | 0 | 0 | Total | 78805 | 2329026 | 12723564.5161 | 0 | 11703423 | -1020141.5161 | 81842 | 0 |  |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | [13 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
| 9 | [5 empty] | 0 | 0 | 0 | 0 | Bill of Lading | [7 empty] | 0 |  |  |  |  | 0 | Jan: 0; Mar: 0; May: 0; Aug: 0; Sep: 0; Oct: 0 | [14 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
| 10 | [5 empty] | 0 | 0 | 0 | 0 | Total | 74900 | 2212586 | - |  | 11652232 | - | 81484 | 0 |  |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  |  | 0 | 0 | 0 | 1 | 1 | [14 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
| 11 | [5 empty] | 0 | 0 | 0 | 0 | [8 empty] | 0 |  |  |  |  | 0 | Jan: 0; Mar: 0; May: 0; Aug: 0; Sep: 0; Oct: 0 | 100 | [13 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
| 12 | [5 empty] | 0 | 0 | 0 | 0 | [8 empty] | 0 |  |  |  |  | 0 | Jan: 0; Mar: 0; May: 0; Aug: 0; Sep: 0; Oct: 0 | [14 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
| 5. STOCK |  |  |  | 6. UNIT OPERATION | [13 empty] | 0 | 79300 | 78805 | 79300 |  | 176875
| Description | SMCP | TMCT |  |  |  | R-North | R-Middle | R-South |  |  | SM |  |  |  |  | SSB | TOTAL
| PREMIUM | 73167 | 24388 | 29388 |  |  |  |  | CD | EF | G | A | B | AW |  | D.1,2 | [6 empty] | 4mula-B/Ratio
| MEDIUM | 2389.9 | 111211.987 | 106212.187 | OB | Exca.RFU | 6 | 5 | 21 |  |  | 29 | 4 | 8 |  | 20 | 12 | 105
| SM | 3497.81 | 121169 | 121168.8 |  | Exca.Run | 3 | 3 | 5 | - | 3 | 15 | 1 | 4 |  | 21 | 10 | 65
| Ship.Loading |  | 132731 | 0 | Coal | DT.RFU | 17 | 23 | 89 |  |  | 45 | 10 | 35 |  | 120 | 14 | 353
| TOTAL | 79054.71 | 389499.987 |  |  | DT.Run | 6 | 18 | 36 | - | 13 | 26 | 8 | 23 |  | 107 | 13 | 250 | 0
|  | 79054.71 | 79054.71 | 0 |  |  |  |  | 336779.702 | -69479.387 | #REF!
| TMCT Stock |  |  | Total | 256768.987 |  | = | On_Barge | 156115.6 | + | 100653.387 | MT
| 7. POND ELEVATION |  |  | -533750.987 |  |  |  | 3618822.513 |  |  |  | -533750.987
| 24388 | 24388
| 111211.987 | 71669.987 | [14 empty] | 9374397
| 121169 | 4595 | [14 empty] | 11703423
| 256768.987 | 100652.987 | [5 empty] | Remark Stock SM MCCP:
| adjs.haul | pl | 0 |  | 0 | 0 |  | Stock SM | 973.51 | -17326 | 134210 | 122558.987 |  | 21905.6
|  | m | 0 |  | 19375 | 19375 |  | E/Noor ( SM-C )
|  | sm | 0 |  | 82088 | 82088 |  | BIMA ( SM-A # 5 ) | [13 empty] | 0
|  | bmr | [5 empty] | Kau ( SM-A # 4 ) | 9750 | [12 empty] | 0
| 0 | ttl | 0 |  | 101463 | 101463 |  |  | 9750 | [11 empty] | 0 | 0
[8 empty] | Hauling SM | 0
| pl BPend | ph | 0 | 60% | 0 | 60% |  |  | 10723.51
|  | mh | 0 | 40% | 0 | 40%
| coal | ph | 0 |  | 2388
|  |  | 0 | 0 | 2579.04 | 191.04
|  |  |  | COAL |  |  | HAULING |  |  | SM.1,4
|  |  |  | 40 | 35 |  | 40 | 35 |  | MH+ML
|  |  | P |  | 2388 | 2388 |  | 0 | 0
|  |  | M |  | 14715.2 | 14715.2 |  | 16624 | 16624
|  | -3307.3 | SM |  | 72342.9 | 72342.9 |  | 69081 | 69081
|  |  |  | 0 | 89446.1 | 89446.1 | 0 | 85705 | 85705 | 0
Planner
Spv.
Mgr.
Mgr.
G. Mgr.
O.Dir.
Planner
Spv.
Mgr.
Mgr.
G. Mgr.
O.Dir.